## RA 1
To | [9 empty] | Vendor
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [7 empty] | Date of Submission-27th March 2023
Work order No: SNIPIPL/WO/2022-23/041 | [7 empty] | Date of Finalizing-10th April 2023
Bill No RA1
Structure name Bunker & Hopper
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Excavation in all type of Soil | 160 | m3 |  |  |  |  | 1084.546 | 173527.36 | 1084.546 | 173527.36
2 | BackFilling | 85 | m3 | [5 empty] | 0 | 0 | 0
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  |  |  | 9.768 | 20512.8 | 9.768 | 20512.8
4 | Shuttering upto +/- 3meter from GL | 550 | m3 |  |  |  |  | 142.4 | 78320 | 142.4 | 78320
5 | RCC upto +/- 3.00 meter from GL. | 3350 | m2 |  |  |  |  | 50.736 | 169965.6 | 50.736 | 169965.6
6 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | 6600 | m3 |  |  |  |  | 2.022 | 13345.2 | 2.022 | 13345.2
* | Total | [7 empty] | 455670.96 |  | 455670.96

## RA 2
To | [9 empty] | Vendor
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [7 empty] | Date of Submission-08th May 2023
Work order No: SNIPIPL/WO/2022-23/041 | [7 empty] | Date of Finalizing-27th May 2023
Bill No R2
Structure name Bunker & Hopper
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Excavation in all type of Soil | 160 | m3 |  |  | 1084.546 | 173527.36 |  |  | 1084.546 | 173527.36
2 | BackFilling | 85 | m3
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  | 9.768 | 20512.8 |  |  | 9.768 | 20512.8
4 | Shuttering upto +/- 3meter from GL | 550 | m2 |  |  | 142.4 | 78320 | 96 | 52800 | 238.4 | 131120
5 | Shuttering from +/- 3meter to 6 metre from GL | 605 | m2 |  |  |  |  | 53.52 | 32379.6 | 53.52 | 32379.6
6 | RCC upto +/- 3.00 meter from GL. | 3350 | m2 |  |  | 50.736 | 169965.6 | 15.424 | 51670.4 | 66.16 | 221636
7 | RCC from +/- 3.00 to +/- 6meter from GL. | 3685 | m3 |  |  |  |  | 9.26 | 34123.1 | 9.26 | 34123.1
8 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | 6600 | MT |  |  | 2.022 | 13345.2 | 1.071 | 7068.6 | 3.093 | 20413.8
9 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. | 7260 | MT |  |  |  |  | 0.957 | 6947.82 | 0.957 | 6947.82
10 | MS angle fixing | 13000 | MT |  |  |  |  | 0.2 | 2600 | 0.2 | 2600
11 | Providing and fixing water bar | 220 | RMT |  |  |  |  | 43.2 | 9504 | 43.2 | 9504
* | Total | [5 empty] | 455670.96 |  | 197093.52 |  | 652764.48

## RA 3
To | [9 empty] | Vendor
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [7 empty] | Date of Submission-08th June 2023
Work order No: SNIPIPL/WO/2022-23/041 | [7 empty] | Date of Finalizing-24th June 2023
Bill No RA3
Structure name Bunker & Hopper
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Excavation in all type of Soil 0-3 Mtr | 160 | m3 |  |  | 1084.546 | 173527.36 |  | 0 | 1084.546 | 173527.36
2 | Excavation in all type of Soil 3-6 Mtr | 198 | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
3 | BackFilling 0-3 | 85 | m3 |  |  | 0 | 0 | 411.3243 | 34962.5655 | 411.3243 | 34962.5655
4 | BackFilling 3-6 | 93.5 | m3 |  |  | 0 | 0 | 293.683 | 27459.3605 | 293.683 | 27459.3605 | 53.52 | 550
5 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  | 9.768 | 20512.8 | 5.663 | 11892.3 | 15.431 | 32405.1 | 9.26 | 3350
6 | Shuttering upto +/- 3meter from GL | 550 | m2 |  |  | 238.4 | 131120 | 358.202 | 197011.1 | 596.602 | 328131.1 | 0.957 | 6600
7 | Shuttering from +/- 3meter to 6 metre from GL | 605 | m2 |  |  | 53.52 | 32379.6 | 25.44 | 15391.2 | 78.96 | 47770.8
8 | RCC upto +/- 3.00 meter from GL. | 3350 | m2 |  |  | 66.16 | 221636 | 52.7289 | 176641.815 | 118.8889 | 398277.815
9 | RCC from +/- 3.00 to +/- 6meter from GL. | 3685 | m3 |  |  | 9.26 | 34123.1 | 2.08 | 7664.8 | 11.34 | 41787.9
10 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | 6600 | MT |  |  | 3.093 | 20413.8 | 1.599 | 10553.4 | 4.692 | 30967.2
11 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. | 7260 | MT |  |  | 0.957 | 6947.82 | 0 | 0 | 0.957 | 6947.82
12 | MS angle fixing | 13000 | MT |  |  | 0.2 | 2600 | 0.927 | 12051 | 1.127 | 14651
13 | Providing and fixing water bar | 220 | RMT |  |  | 43.2 | 9504 | 48.6 | 10692 | 91.8 | 20196
* | Total | [5 empty] | 652764.48 |  | 504319.541 |  | 1157084.021
Abhishek Acharya |  |  | Mukesh Lilhare | [7 empty] | Mahesh wandre
Billing Engineer |  |  | Site Incharge | [7 empty] | H.O.D (CiviL)
Nakoda Pipe Impex Pvt Ltd |  |  | AGI | [7 empty] | Nakoda Pipe Impex Pvt Ltd
1241.47
128.47
222.48
236.25
30.25
64.8
240.64
307.7
2808
871
4032
10183.06