## Abstract
To | [8 empty] | Vendor
Nakoda Pipes Pvt Ltd | [8 empty] | AG Infratech
Tilda, Chattisgarh | [8 empty] | Date of Submission-08th June 2023
Work order No: SNIPIPL/WO/2022-23/041 | [8 empty] | Date of Finalizing-24th June 2023
Bill No RA3
Structure name Bunker & Hopper
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Excavation in all type of Soil 0-3 Mtr | 160 | m3 |  |  |  |  | 1088.009 | 174081.44
2 | Excavation in all type of Soil 3-6 Mtr | 198 | m3 | [5 empty] | 0
3 | BackFilling 0-3 | 85 | m3 |  |  |  |  | 411.3243 | 34962.5655
4 | BackFilling 3-6 | 93.5 | m3 |  |  |  |  | 293.683 | 27459.3605
5 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  |  |  | 15.431 | 32405.1
6 | Shuttering upto +/- 3meter from GL | 550 | m2 |  |  |  |  | 675.562 | 371559.1
7 | Shuttering from +/- 3meter to 6 metre from GL | 605 | m2 | [5 empty] | 0
8 | RCC upto +/- 3.00 meter from GL. | 3350 | m2 |  |  |  |  | 130.2289 | 436266.815
9 | RCC from +/- 3.00 to +/- 6meter from GL. | 3685 | m3 | [5 empty] | 0
10 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | 6600 | MT |  |  |  |  | 20.4459 | 134943.1862
11 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. | 7260 | MT | [5 empty] | 0
12 | MS angle fixing | 13000 | MT |  |  |  |  | 0.927 | 12051
13 | Providing and fixing water bar | 220 | RMT |  |  |  |  | 48.6 | 10692
* | Total | [7 empty] | 1234420.5672

## Measurement sheet
Estimate value sheet
Bunker & Hopper
Division- Ferro Alloys
Vendor- AGI
Description | Struc. | Reduced Level |  | L | B | H | Nos | Qnty | Unit | Remarks
|  | From | To
Excavation & Backfilling
0--3 Mtr | Conveyor belt |  |  | 7 | 5.2 | 1.4 | 1 | 50.96 | Cum
0--3 Mtr | Conveyor belt |  |  | 7 | 4 | 1.4 | 3 | 117.6 | Cum
0--3 Mtr | Hopper Slope |  |  | 27.1765 | 2 | 5 | 1 | 271.765 | Cum
0--3 Mtr | Hopper Slope |  |  | 9.2 | 0.5 | 5 | 1 | 23 | Cum
0--3 Mtr | Hopper Slope | [6 empty] | 0 | Cum |  | 258.0002
0--3 Mtr | Hopper Excavation |  |  | 6.95 | 7.2 | 3 | 1 | 150.12 | Cum
0--3 Mtr | Bunker Footing |  |  | 4 | 4 | 2.9 | 4 | 185.6 | Cum
0--3 Mtr | Bunker Footing |  |  | 4.2 | 4.2 | 2.9 | 2 | 102.312 | Cum
0--3 Mtr | Bunker Footing |  |  | 3.8 | 3.8 | 2.9 | 2 | 83.752 | Cum
0--3 Mtr | [7 empty] | 985.109
3--6 Mtr | Hopper Excavation |  |  | 7.35 | 7 | 2 | 1 | 102.9 | Cum
3--6 Mtr | [7 empty] | 102.9
Soil Dressing | Conveyor belt Footing |  |  | 6 | 5.2 |  | 1 | 31.2 | Sqm
Soil Dressing | Conveyor belt Footing |  |  | 6 | 4 |  | 1 | 24 | Sqm
Soil Dressing | Hopper Slope |  |  | 18 | 5 |  | 1 | 90 | Sqm
Soil Dressing | Hopper Excavation |  |  | 6.95 | 7 |  | 1 | 48.65 | Sqm
Soil Dressing | Bunker Footing |  |  | 4 | 4 |  | 1 | 16 | Sqm |  |  | 1088.009
Soil Dressing | Bunker Footing |  |  | 4.1 | 4.1 |  | 1 | 16.81 | Sqm
Soil Dressing | Bunker Footing |  |  | 3.7 | 3.7 |  | 1 | 13.69 | Sqm
Soil Dressing | [7 empty] | 240.35
Backfilling
Total Excavation | [7 empty] | 1013.8302 | Cum
Deducton of RCC | [7 empty] | 293.392 | Cum
Deduction of PCC | [7 empty] | 15.431 | Cum
Backfilling | [7 empty] | 705.0073 | Cum
Plain & reinforced Cement Concrete
PCC
0--3 Mtr | Hopper Slope | NA | NA | 17.3 | 3.5 | 0.1 | 1 | 6.055 | Cum
0--3 Mtr | Hopper | 88.86 | 89.01 | 4 | 4 | 0.15 | 1 | 2.4 | Cum
0--3 Mtr | F1 | 87.93 | 88.03 | 2.6 | 2.6 | 0.1 | 8 | 5.408 | Cum
0--3 Mtr | F3 | 90.72 | 90.82 | 1.4 | 1.4 | 0.1 | 8 | 1.568 | Cum
0--3 Mtr | [7 empty] | 15.431 | Cum
RCC
0--3 Mtr | Hopper Slope | NA | NA | 17.1 | 3.3 | 0.2 | 1 | 11.286 | Cum
0--3 Mtr | Hopper Slab | 88.96 | 89.26 | 3.8 | 3.8 | 0.3 | 1 | 4.332 | Cum
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.8 | 4.84 | 0.2 | 2 | 7.3568 | Cum
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.8 | 4.84 | 0.2 | 1 | 3.6784 | Cum
0--3 Mtr | Hopper wall (Bottom) | 89.16 | 90.36 | 3.8 | 1.2 | 0.2 | 1 | 0.912 | Cum
0--3 Mtr | Hopper Slope Wall |  |  | 17.1 | 2.535 | 0.2 | 2 | 17.3394 | Cum
0--3 Mtr | Hoppper Wall (opening) | 90.36 | 94 | 1.3 | 3.64 | 0.2 | 2 | 1.8928 | Cum
0--3 Mtr | F1 | 88.03 | 88.83 | 2.4 | 2.4 | 0.8 | 8 | 36.864 | Cum
0--3 Mtr | F3 | 90.82 | 91.27 | 1.2 | 1.2 | 0.45 | 8 | 5.184 | Cum
0--3 Mtr | C1 | 88.83 | 93 | 0.85 | 0.85 | 4.17 | 8 | 24.1026 | Cum
0--3 Mtr | C3 | 91.27 | 94.5 | 0.6 | 0.6 | 3.23 | 8 | 9.3024 | Cum
0--3 Mtr | Tie Beam (longer) | 92.25 | 92.7 | 15.45 | 0.3 | 0.45 | 2 | 4.1715 | Cum
0--3 Mtr | Tie Beam (Shorter) | 92.25 | 92.7 | 5.15 | 0.3 | 0.45 | 4 | 2.781 | Cum
0--3 Mtr | Conveyor Beam | 93.75 | 94.2 | 1.9 | 0.3 | 0.45 | 4 | 1.026 | Cum
0--3 Mtr | [7 empty] | 130.2289 | Cum
Formwork (Shuttering)
0--3 Mtr | Hopper Slab | 88.96 | 89.26 | 3.6 |  | 0.3 | 2 | 2.16 | Sqm
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.6 | 4.84 |  | 4 | 69.696 | Sqm
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.6 | 4.84 |  | 2 | 34.848 | Sqm
0--3 Mtr | Hopper wall (Bottom) | 89.16 | 90.36 | 3.6 | 1.2 |  | 2 | 8.64 | Sqm
0--3 Mtr | Hopper Slope Wall |  |  | 17.1 | 2.535 |  | 4 | 173.394 | Sqm
0--3 Mtr | Hoppper Wall (opening) | 90.36 | 94 | 1.1 | 3.64 |  | 4 | 16.016 | Sqm
0--3 Mtr | F1 | 88.03 | 88.83 | 2.55 |  | 0.8 | 16 | 32.64 | Sqm
0--3 Mtr | F3 | 90.82 | 91.27 | 1.35 |  | 0.45 | 16 | 9.72 | Sqm
0--3 Mtr | C1 | 88.83 | 93 | 0.85 |  | 4.17 | 16 | 56.712 | Sqm
0--3 Mtr | C3 | 91.27 | 94.5 | 0.6 |  | 3.23 | 16 | 31.008 | Sqm
0--3 Mtr | Tie Beam (longer) Bottom | 92.7 | 92.7 | 15.45 | 0.3 |  | 2 | 9.27 | Sqm
0--3 Mtr | Tie Beam (Shorter) Bottom | 92.7 | 92.7 | 5.15 | 0.3 |  | 4 | 6.18 | Sqm
0--3 Mtr | Tie Beam (longer) Side | 92.25 | 92.7 | 15.45 |  | 0.45 | 4 | 27.81 | Sqm
0--3 Mtr | Tie Beam (Shorter) Side | 92.25 | 92.7 | 5.15 |  | 0.45 | 8 | 18.54 | Sqm
0--3 Mtr
0--3 Mtr | Hopper Slab | 88.96 | 89.26 |  | 3.6 | 0.3 | 2 | 2.16 | Sqm
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.6 | 4.84 |  | 4 | 69.696 | Sqm
0--3 Mtr | Hopper wall | 89.16 | 94 | 3.6 | 4.84 |  | 2 | 34.848 | Sqm
0--3 Mtr | Hopper wall (Bottom) | 89.16 | 90.36 | 3.6 | 1.2 |  | 2 | 8.64 | Sqm
0--3 Mtr | Hoppper Wall (opening) | 90.36 | 94 | 1.1 | 3.64 |  | 4 | 16.016 | Sqm
0--3 Mtr | F1 | 88.03 | 88.83 |  | 0 | 0.8 | 16 | 0 | Sqm
0--3 Mtr | F3 | 90.82 | 91.27 |  | 1.35 | 0.45 | 16 | 9.72 | Sqm
0--3 Mtr | C1 | 88.83 | 93 |  | 0 | 4.17 | 16 | 0 | Sqm
0--3 Mtr | C3 | 91.27 | 94.5 |  | 0.6 | 3.23 | 16 | 31.008 | Sqm
0--3 Mtr | Conveyor Beam | 94.2 | 94.2 | 1.9 | 0.3 |  | 4 | 2.28
0--3 Mtr | Conveyor Beam | 94.2 | 94.2 | 1.9 | 0.3 |  | 8 | 4.56 | Sqm
0--3 Mtr | [7 empty] | 675.562 | Sqm