## RA 1
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [12 empty] | Date of Submission-27th March 2023
Work order No: SNIPIPL/WO/2022-23/041 | [12 empty] | Date of Finalizing-13th April 2023
Bill No RA1
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Cooling Tower | 160 | m3 |  |  | 0 | 0 | 342 | 54720 | 342 | 54720
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Cooling Tower | 85 | m3 |  |  |  | 0 | 137.266 | 11667.61 | 137.266 | 11667.61
3 |  | Required watering & consolidating either manually or'by mechanical means to the required density as per specification. | Cooling Tower | 60 | m3 |  |  |  |  | 137.266 | 8235.96 | 137.266 | 8235.96
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Cooling Tower | 2100 | m3 |  |  |  |  | 12.6116 | 26484.4125 | 12.6116 | 26484.4125
5 | 13 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing (Cooling Tower) | Cooling Tower | 3350 | m3 |  |  |  |  | 66.8088 | 223809.48 | 66.8088 | 223809.48
| E | Formwork (Shuttering)
7 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. (For Cooling Tower) | Cooling Tower | 550 | m2 |  |  |  |  | 385.0685 | 211787.675 | 385.0685 | 211787.675
Soling Hardcore & Others
7 | 33 | Providing and fixing of PVC water bar 230 | Cooling Tower | 220 | M |  |  |  | 0 | 100.8 | 22176 | 100.8 | 22176
| C | REINFORCEMENT WORK |  |  | m2
9 | 18 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Cooling Tower | 6600 | MT |  |  |  |  | 4.002 | 26413.2 | 4.002 | 26413.2
| * | Total | [6 empty] | 0 |  | 585294.3375 |  | 585294.3375

## RA 2
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [12 empty] | Date of Submission-10th May 2023
Work order No: SNIPIPL/WO/2022-23/041 | [12 empty] | Date of Finalizing-22nd May 2023
Bill No RA2
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Cooling Tower | 160 | m3 |  |  | 342 | 54720 | 0 | 0 | 342 | 54720
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Cooling Tower | 85 | m3 |  |  | 137.266 | 11667.61 | 0 | 0 | 137.266 | 11667.61
3 |  | Required watering & consolidating either manually or'by mechanical means to the required density as per specification. | Cooling Tower | 60 | m3 |  |  | 137.266 | 8235.96 | 0 | 0 | 137.266 | 8235.96
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Cooling Tower | 2100 | m3 |  |  | 12.6116 | 26484.4125 | 0 | 0 | 12.6116 | 26484.4125
5 | 13 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing (Cooling Tower) | Cooling Tower | 3350 | m3 |  |  | 66.8088 | 223809.48 | 0.25645 | 859.1075 | 67.0652 | 224668.5875
| E | Formwork (Shuttering)
7 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. (For Cooling Tower) | Cooling Tower | 550 | m2 |  |  | 385.0685 | 211787.675 | 23.8102 | 13095.61 | 408.8787 | 224883.285
Soling Hardcore & Others
7 | 33 | Providing and fixing of PVC water bar 230 | Cooling Tower | 220 | M |  |  | 100.8 | 22176 | 0 | 0 | 100.8 | 22176
| C | REINFORCEMENT WORK |  |  | m2
9 | 18 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Cooling Tower | 6600 | MT |  |  | 4.002 | 26413.2 | 1.074 | 7088.4 | 5.162 | 34069.2
| * | Total | [6 empty] | 585294.3375 |  | 21043.1175 |  | 606905.055

## RA 3 {Final}
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [12 empty] | Date of Submission-10th june 2023
Work order No: SNIPIPL/WO/2022-23/041 | [12 empty] | Date of Finalizing-30th june May 2023
Bill No RA3
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Cooling Tower | 160 | m3 |  |  | 342 | 54720 |  |  | 342 | 54720
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Cooling Tower | 85 | m3 |  |  | 137.266 | 11667.61 |  |  | 137.266 | 11667.61
3 |  | Required watering & consolidating either manually or'by mechanical means to the required density as per specification. | Cooling Tower | 60 | m3 |  |  | 137.266 | 8235.96 |  |  | 137.266 | 8235.96
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Cooling Tower | 2100 | m3 |  |  | 12.6116 | 26484.4125 |  |  | 12.6116 | 26484.4125
5 | 13 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing (Cooling Tower) | Cooling Tower | 3350 | m3 |  |  | 67.0652 | 224668.5875 |  |  | 67.0652 | 224668.5875
| E | Formwork (Shuttering)
7 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. (For Cooling Tower) | Cooling Tower | 550 | m2 |  |  | 408.8787 | 224883.285 |  |  | 408.8787 | 224883.285
Soling Hardcore & Others
7 | 33 | Providing and fixing of PVC water bar 230 | Cooling Tower | 220 | M |  |  | 100.8 | 22176 |  |  | 100.8 | 22176
| C | REINFORCEMENT WORK |  |  | m2
9 | 18 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Cooling Tower | 6600 | MT |  |  | 5.162 | 34069.2 |  |  | 5.162 | 34069.2
| H | Pocket Fixing Work For Bolt
10 | 42 | Pocket Fixing Work For Bolt | Cooling Tower | 500 |  |  |  | 0 | 0 | 9 | 4500 | 9 | 4500
11 | 43 | Pressure grouting with cement & Slurry | Cooling Tower | 620 |  |  |  | 0 | 0 | 123.24 | 76408.8 | 123.24 | 76408.8
12 | 43 | Net Finishing | Cooling Tower | 185 |  |  |  | 0 | 0 | 185.0875 | 34241.1875 | 185.0875 | 34241.1875
| * | Total | [6 empty] | 606905.055 |  | 115149.9875 |  | 722055.0425