## RA 1
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 1st Ra | [10 empty] | 2023-02-01
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | Ferro |  | 0 | 3040.316 | 486450.56 | 3040.316 | 486450.56
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 | Ferro |  | 0 |  | 0 | 0 | 0
3 |  | Backfilling | m3 | 85 | Ferro |  | 0 |  | 0 | 0 | 0
4 |  | Watering and consolodation | m3 | 60 | Ferro |  | 0 |  | 0 | 0 | 0
5 |  | Sand Filling | m3 | 700 | Ferro |  | 0 |  | 0 | 0 | 0
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | Ferro |  | 0 | 57.39 | 120519 | 57.39 | 120519
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | Ferro |  | 0 |  |  | 0 | 0
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | Ferro |  | 0 | 222.15 | 577590 | 222.15 | 577590
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 | Ferro |  | 0 |  | 0 | 0 | 0
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | Ferro |  | 0 |  | 0 | 0 | 0
10 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Ferro |  | 0 | 318.42 | 127368 | 318.42 | 127368
|  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 | Ferro |  | 0 |  | 0 | 0 | 0
11 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | Ferro |  | 0 | 16.901 | 118307 | 16.901 | 118307
12 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  |  | 0 |  | 0 | 0 | 0
13 | 40 | Pocket Fixing Work | Nos | 500 |  |  |  |  | 0 | 0 | 0
14 |  | RCC For Circular structure | m3 | 750 |  |  |  |  | 0 | 0 | 0
15 |  | Shuttering For Circular structure | m2 | 150 |  |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0
[7 empty] | 0 |  | 1430234.56 |  | 1430234.56

## RA 2
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 2nd Ra | [10 empty] | 2023-03-01
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | Ferro | 3040.316 | 486450.56 |  | 0 | 3040.316 | 486450.56
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 | Ferro |  | 0 |  | 0 | 0 | 0
3 |  | Backfilling | m3 | 85 | Ferro |  | 0 |  | 0 | 0 | 0
4 |  | Watering and consolodation | m3 | 60 | Ferro |  | 0 |  | 0 | 0 | 0
5 |  | Sand Filling | m3 | 700 | Ferro |  | 0 |  | 0 | 0 | 0
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | Ferro | 57.39 | 120519 |  | 0 | 57.39 | 120519
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | Ferro |  | 0 |  |  | 0 | 0
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | Ferro | 222.15 | 577590 | 42.705 | 111032.935 | 264.855 | 688622.935
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 | Ferro |  | 0 |  | 0 | 0 | 0
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | Ferro |  | 0 |  | 0 | 0 | 0
10 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Ferro | 318.42 | 127368 | 174.4858 | 69794.32 | 492.9058 | 197162.32
|  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 | Ferro |  | 0 |  | 0 | 0 | 0
11 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | Ferro | 16.901 | 118307 | 5.473 | 38311 | 22.374 | 156618
12 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  |  | 0 | 1.73 | 22490 | 1.73 | 22490
13 | 40 | Pocket Fixing Work | Nos | 500 |  |  |  |  | 0 | 0 | 0
14 |  | RCC For Circular structure | m3 | 750 |  |  |  |  | 0 | 0 | 0
15 |  | Shuttering For Circular structure | m2 | 150 |  |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0
[7 empty] | 1430234.56 |  | 241628.255 |  | 1671862.815

## RA 3
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 3rd Ra | [10 empty] | 2023-03-01
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | Ferro | 3040.316 | 486450.56 |  | 0 | 3040.316 | 486450.56
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 | Ferro |  | 0 |  | 0 | 0 | 0
3 |  | Backfilling | m3 | 85 | Ferro |  | 0 | 2539.022 | 215816.8702 | 2539.022 | 215816.8702
4 |  | Watering and consolodation | m3 | 60 | Ferro |  | 0 | 2539.022 | 152341.3202 | 2539.022 | 152341.3202
5 |  | Sand Filling | m3 | 700 | Ferro |  | 0 | 35.136 | 24595.2 | 35.136 | 24595.2
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | Ferro | 57.39 | 120519 | 12.9062 | 27103.125 | 70.2963 | 147622.125
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | Ferro |  | 0 |  |  | 0 | 0
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | Ferro | 264.855 | 688622.935 | 54.1309 | 140740.275 | 318.9859 | 829363.21
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 | Ferro |  | 0 | 50.82 | 132132 | 50.82 | 132132
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | Ferro |  | 0 |  | 0 | 0 | 0
10 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Ferro | 492.9058 | 197162.32 | 381.8575 | 152743 | 874.7633 | 349905.32
|  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 | Ferro |  | 0 | 175.152 | 70060.8 | 175.152 | 70060.8
11 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | Ferro | 22.374 | 156618 | 5.99 | 41930 | 28.364 | 198548
12 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  | 1.73 | 22490 | 0.61364 | 7977.32 | 2.3436 | 30467.32
13 | 40 | Pocket Fixing Work | Nos | 500 |  |  |  |  | 0 | 0 | 0
14 |  | RCC For Circular structure | m3 | 750 |  |  |  |  | 0 | 0 | 0
15 |  | Shuttering For Circular structure | m2 | 150 |  |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0
[7 empty] | 1671862.815 |  | 965439.9104 |  | 2637302.7254

## RA 4
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 4th Ra | [10 empty] | 2023-03-01
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | Ferro | 3040.316 | 486450.56 |  | 0 | 3040.316 | 486450.56
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 | Ferro |  | 0 |  | 0 | 0 | 0
3 |  | Backfilling | m3 | 85 | Ferro | 2539.022 | 215816.8702 |  | 0 | 2539.022 | 215816.8702
4 |  | Watering and consolodation | m3 | 60 | Ferro | 2539.022 | 152341.3202 |  | 0 | 2539.022 | 152341.3202
5 |  | Sand Filling | m3 | 700 | Ferro | 35.136 | 24595.2 |  | 0 | 35.136 | 24595.2
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | Ferro | 70.2963 | 147622.125 |  | 0 | 70.2963 | 147622.125
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | Ferro |  | 0 |  |  | 0 | 0
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | Ferro | 318.9859 | 829363.21 |  | 0 | 318.9859 | 829363.21
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 | Ferro | 50.82 | 132132 | 17.65 | 45890 | 68.47 | 178022
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | Ferro |  | 0 |  | 0 | 0 | 0
10 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Ferro | 874.7633 | 349905.32 |  | 0 | 874.7633 | 349905.32
|  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 | Ferro | 175.152 | 70060.8 | 121.56 | 48624 | 296.712 | 118684.8
11 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | Ferro | 28.364 | 198548 | 1.89 | 13230 | 30.254 | 211778
12 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 | Ferro | 2.3436 | 30467.32 |  | 0 | 2.3436 | 30467.32
13 | 40 | Pocket Fixing Work | Nos | 500 | Ferro |  | 0 | 45 | 22500 | 45 | 22500
14 |  | RCC For Circular structure | m3 | 750 | Ferro |  | 0 |  | 0 | 0 | 0
15 |  | Shuttering For Circular structure | m2 | 150 | Ferro |  | 0 |  | 0 | 0 | 0
[7 empty] | 2637302.7254 |  | 130244 |  | 2767546.7254

## RA 5
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 5th Ra
2023-05-01
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | Ferro | 3040.316 | 486450.56 | 323.39 | 51742.4 | 3363.706 | 538192.96 | 2981.62 | -382.086 | -61133.76
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 | Ferro |  | 0 | 94.61 | 16651.36 | 94.61 | 16651.36
3 |  | Backfilling | m3 | 85 | Ferro | 2539.022 | 215816.8702 | 94.61 | 8041.85 | 2633.632 | 223858.7202 | 2464.26 | -169.372 | -14396.6202
4 |  | Watering and consolodation | m3 | 60 | Ferro | 2539.022 | 152341.3202 | 125.5593 | 7533.5594 | 2664.5813 | 159874.8795
5 |  | Sand Filling | m3 | 700 | Ferro | 35.136 | 24595.2 | 63.41 | 44387 | 98.546 | 68982.2
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | Ferro | 70.2963 | 147622.125 | 0 | 0 | 70.2963 | 147622.125 | 56.16 | -14.1363 | -29686.125
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | Ferro |  | 0 | 4.0991 | 9469 | 4.0991 | 9469
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | Ferro | 318.9859 | 829363.21 | 5.84 | 15184 | 324.8259 | 844547.21
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 | Ferro | 68.47 | 178022 |  | 0 | 68.47 | 178022
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | Ferro |  | 0 | 0 | 0 | 0 | 0
11 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Ferro | 874.7633 | 349905.32 | 48.811 | 19524.417 | 923.5743 | 369429.737
12 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 | Ferro | 296.712 | 118684.8 |  | 0 | 296.712 | 118684.8
13 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | Ferro | 30.254 | 211778 |  | 0 | 30.254 | 211778
14 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  | 2.3436 | 30467.32 | 0.48 | 6240 | 2.8236 | 36707.32
15 | 40 | Pocket Fixing Work | Nos | 500 |  | 45 | 22500 |  | 0 | 45 | 22500
16 |  | RCC For Circular structure | m3 | 750 |  |  |  | 0 | 0 | 0 | 0
17 |  | Shuttering For Circular structure | m2 | 150 |  |  |  | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[7 empty] | 2767546.7254 |  | 178773.5863 |  | 2946320.3117
Abhishek Acharya |  |  | Mukesh Lilhare | [7 empty] | Mahesh wandre
Billing Engineer |  |  | Site Incharge | [7 empty] | Assistant Project Manager
Nakoda Pipe Impex Pvt Ltd |  |  | AGI | [7 empty] | Nakoda Pipe Impex Pvt Ltd

## RA 5 measurement
SHREE NAKODA PIPE IMPEX PVT LTD | [9 empty] | Month:- July 2023
FERRO ALLOYS-5TH RA | [9 empty] | Vendor:- AG INFRATECH
DESCRIPTION | Block | Structure | Reduced Level |  | L | B | H | NOS | QTY | Unit
|  |  | From | To
Excavation Up to 0.00 Lvl to +/-3.0 m Gl
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | Ferro | Chimney |  |  | 3.5 | 3.5 | 2.63 | 3.14 | 101.163 | Cum
Ferrow Excavation Below Pcc | Ferro | Ferro |  |  | 25.8 | 18.65 | 0.1 | 1 | 48.117 | Cum
Excavation Up to 0.00 Lvl to +/-3.0 m Gl | Ferro | [7 empty] | 149.28 | Cum
BackFilling
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | Ferro | Chimney |  |  | 3.5 | 3.5 | 2.63 | 3.14 | 101.163 | Cum
High Mass Foundation | Ferro | High Mass |  |  | 3.6 | 3.6 | 2 | 1 | 25.92 | Cum
(-) Deduct For Footing Pcc Qty. | Ferro | [7 empty] | -3.16 | Cum
(-) Deduct For Footing Rcc Qty. | Ferro | [7 empty] | -40.07 | Cum
Total Qty. for Back Filling thise bill | Ferro | [7 empty] | 83.853 | Cum
Dressing
Chimney Foundation Dia-7.0 m (2x3.14x2.85) | Ferro | Chimney |  |  | 3.14 | 2.85 |  | 2 | 17.898 | Sqm
High Mass Foundation | Ferro | High Mass |  |  | 3 | 3 |  | 1 | 9 | Sqm
Ferrow Below Pcc | Ferro | Ferro |  |  | 25.8 | 18.65 |  | 1 | 481.17 | Sqm
Total Qty.For Dressing Work | Ferro | [7 empty] | 508.068 | Sqm
PCC {3--6}Mtr
Chimney Foundation Dia-5.50 m (3.14x2.75x2.75x2.75x0.100=2.37 Cum | Ferro | Chimney |  |  | 2.75 | 2.75 | 0.1 | 3.14 | 2.3746 | Cum
High Mass Foundation | Ferro | High Mass |  |  | 2.8 | 2.8 | 0.1 | 1 | 0.784
Ferrow Below Flooring Pcc | Ferro | Ferro |  |  | 28.8 | 18.65 | 0.1 | 1 | 53.712
Deduction(3.14x4.05x4.05x0.1 | Ferro |  |  |  | 4.05 | 4.05 | 0.1 | -3.14 | -5.1504
Total Qty. for Pcc work in thise bill | Ferro | [7 empty] | 51.7202 | Cum
Ferro
RCC {0--3}Mtr
High Mass Foundation Raft | Ferro | High Mass |  |  | 2.6 | 2.6 | 0.3 | 1 | 2.028
High Mass Foundation Column | Ferro | High Mass |  |  | 1 | 1 | 2.4 | 1 | 2.4
Total Qty. for Footing RCC work | Ferro | [7 empty] | 4.428 | Cum
Ferro
Shuttering {0--3}Mtr
High Mass Foundation Raft(2.6x4=10.4) | Ferro | High Mass |  |  | 10.4 |  | 0.3 | 1 | 3.12
High Mass Foundation Column(1.0x4=4.0) | Ferro | High Mass |  |  | 4 |  | 2.4 | 1 | 9.6
Column C1(1.16+1.16+1.53+1.53=5.38) | Ferro | High Mass |  |  | 5.38 |  | 0.05 | 2 | 0.538
Column C2(0.95+0.95+1.2+1.2=4.30) | Ferro | High Mass |  |  | 4.3 |  | 0.05 | 2 | 0.43
Column C3(0.75+0.75+0.90+0.90=3.30+ | Ferro | High Mass |  |  | 3.3 |  | 0.05 | 11 | 1.815
Column C4(0.9+0.9+1.2+1.2=4.20 | Ferro | High Mass |  |  | 4.2 |  | 0.05 | 1 | 0.21
Column C5(1.42+1.42+0.9+0.9=4.64) | Ferro | High Mass |  |  | 4.64 |  | 0.05 | 4 | 0.928
Column C6(1.25+1.25+0.8+0.8=4.10) | Ferro | High Mass |  |  | 4.1 |  | 0.05 | 6 | 1.23
Column C7(0.8+0.8+0.65+0.65=2.90) | Ferro | High Mass |  |  | 2.9 |  | 0.05 | 6 | 0.87
Total Qty. for Shuttring work | Ferro | [7 empty] | 12.72 | Sqm
Ferro
RCC {3--6}Mtr
1st Floor Slab -Part-A | Ferro | Ferro |  |  | 25.6 | 7.9 | 0.15 | 1 | 30.336
1st Floor Slab -Part-B | Ferro | Ferro |  |  | 10.2 | 5.8 | 0.15 | 1 | 8.874
1st Floor Slab -Part-C | Ferro | Ferro |  |  | 5 | 2.8 | 0.15 | 1 | 2.1
1st Floor Slab -Part-D | Ferro | Ferro |  |  | 10.2 | 9.2 | 0.15 | 1 | 14.076
Deduction | Ferro |  |  |  | 4.7 | 4.5 | 0.15 | -1 | -3.1725
Total Qty. for Footing RCC work | Ferro | [7 empty] | 52.2135 | Cum
Ferro
Shuttering {3--6}Mtr
1st Floor Slab -Part-A | Ferro | Ferro |  |  | 25.6 | 7.9 |  | 1 | 202.24
1st Floor Slab -Part-B | Ferro | Ferro |  |  | 10.2 | 5.8 |  | 1 | 59.16
1st Floor Slab -Part-C | Ferro | Ferro |  |  | 5 | 2.8 |  | 1 | 14
1st Floor Slab -Part-D | Ferro | Ferro |  |  | 10.2 | 9.2 |  | 1 | 93.84
Deduction | Ferro | Ferro |  |  | 4.7 | 4.5 |  | -1 | -21.15
Side=5.0+2.8+10.2+7.9+25.6+7.90+10.2+9.2+10.2+10.6+10.2+2.8=112.60) | Ferro | Ferro |  |  | 112.6 | 0.15 |  | 1 | 16.89
Total Qty. for Shuttring work | Ferro | [7 empty] | 364.98 | Sqm
RCC Chimney
Circular foundation Raft | Ferro | Chimney |  |  | 2.55 | 2.55 | 0.45 | 3.14 | 9.188
Circular foundation Pedestal | Ferro | Chimney |  |  | 2.05 | 2.05 | 3.64 | 3.14 | 48.0329
Total Qty. RCC Work Circular Chimney | Ferro | [7 empty] | 57.2209 | Cum
Shuttering Chimney
Circular foundation Pcc | Ferro | Chimney |  |  | 3.14 | 2.75 | 0.1 | 2 | 1.727
Circular foundation Raft | Ferro | Chimney |  |  | 3.14 | 2.55 | 0.45 | 2 | 7.2063
Circular foundation Pedestral | Ferro | Chimney |  |  | 3.14 | 2.05 | 3.64 | 2 | 46.8614
Shuttering Chimney | Ferro | [7 empty] | 55.7947 | Sqm
Srhinkomp Grouting
Column C1 | Ferro | Ferro |  |  | 1.155 | 1.525 | 0.05 | 2 | 0.17614
Column C2 | Ferro | Ferro |  |  | 0.95 | 1.2 | 0.05 | 2 | 0.114
Column C3 | Ferro | Ferro |  |  | 0.75 | 0.9 | 0.05 | 11 | 0.37125
Column C4 | Ferro | Ferro |  |  | 0.9 | 1.2 | 0.05 | 1 | 0.054
Column C5 | Ferro | Ferro |  |  | 1.42 | 0.9 | 0.05 | 4 | 0.2556
Column C6 | Ferro | Ferro |  |  | 1.25 | 0.8 | 0.05 | 6 | 0.3
Column C7 | Ferro | Ferro |  |  | 0.8 | 0.65 | 0.05 | 6 | 0.156
Total Qty. Grouting Work | Ferro | [7 empty] | 1.427 | Cum

## RA-6
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 6th Ra | [11 empty] | 2023-07-01
2023-07-01
Sl No | Item No | Description | UOM | Rate |  | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
|  |  |  | Old | New |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 |  | Ferro | 3363.706 | 538192.96 |  | 0 | 3363.706 | 538192.96
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 |  | 180 | Ferro |  | 0 | 149.28 | 26870.391 | 149.28 | 26870.391
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 |  | Ferro | 94.61 | 16651.36 |  | 0 | 94.61 | 16651.36
3 |  | Backfilling | m3 | 85 |  | Ferro | 2633.632 | 223858.7202 |  | 0 | 2633.632 | 223858.7202
3 |  | Backfilling | m3 |  | 85 | Ferro |  | 0 | 83.85 | 0 | 83.85 | 0
4 |  | Watering and consolodation | m3 | 60 |  | Ferro | 2664.5813 | 159874.8795 |  | 0 | 2664.5813 | 159874.8795
5 |  | Soil Dressing | m2 | 25 | 25 | Ferro |  | 0 | 508.07 | 12701.75 | 508.07 | 12701.75
6 |  | Sand Filling | m3 | 700 |  | Ferro | 98.546 | 68982.2 |  | 0 | 98.546 | 68982.2
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 |  | Ferro | 70.2963 | 147622.125 | -14.1363 | -29686.125 | 56.16 | 117936
8 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 |  | Ferro | 4.0991 | 9469 | 51.7202 | 119473.7544 | 55.8194 | 128942.7544 |  | 168.1629 | 112.3435
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 |  | Ferro | 324.8259 | 844547.21 |  | 0 | 324.8259 | 844547.21 | 454.9448
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 |  | 2750 | Ferro |  | 0 | 61.6489 | 169534.5479 | 61.6489 | 0
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 |  | Ferro | 68.47 | 178022 |  | 0 | 68.47 | 178022
11 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 |  | 3025 | Ferro | 0 | 0 | 52.2135 | 157945.8375 | 52.2135 | 0
11 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 |  | Ferro | 0 | 0 |  | 0 | 0 | 0
12 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 |  | Ferro | 923.5743 | 369429.737 |  | 0 | 923.5743 | 369429.737
13 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 |  | Ferro | 296.712 | 118684.8 | 55.7947 | 22317.864 | 352.5067 | 141002.664
14 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. to +/- 6 Mtr | m3 | 440 |  | Ferro |  | 0 | 364.98 | 160591.2 | 364.98 | 160591.2
14 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | 8500 | Ferro | 30.254 | 211778 | 1.33 | 11305 | 31.584 | 221088
14 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7700 | 9350 | Ferro |  | 0 | 5.72 | 53482 | 5.72 | 44044
15 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  |  | 2.8236 | 36707.32 |  | 0 | 2.8236 | 36707.32
16 | 40 | Pocket Fixing Work | Nos | 500 |  |  | 45 | 22500 |  | 0 | 45 | 22500
16 | 40 | Shrinkomp Grouting | Cum |  | 4100 |  |  | 0 | 1.427 | 5850.6488 | 1.427 | 0
[7 empty] | 0 |  |  | 0 | 0
[8 empty] | 2946320.3117 |  | 710386.8685 |  | 3311943.1461

## RA 6 Measurement
SHREE NAKODA PIPE IMPEX PVT LTD | [9 empty] | Month:- July 2023
FERRO ALLOYS-5TH RA | [9 empty] | Vendor:- AG INFRATECH
DESCRIPTION | Block | Structure | Reduced Level |  | L | B | H | NOS | QTY | Unit
|  |  | From | To
Excavation Up to 0.00 Lvl to +/-3.0 m Gl
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | Ferro | Chimney |  |  | 3.5 | 3.5 | 2.63 | 3.14 | 101.163 | Cum
Ferrow Excavation Below Pcc | Ferro | Ferro |  |  | 25.8 | 18.65 | 0.1 | 1 | 48.117 | Cum
Excavation Up to 0.00 Lvl to +/-3.0 m Gl | Ferro | [7 empty] | 149.28 | Cum
BackFilling
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | Ferro | Chimney |  |  | 3.5 | 3.5 | 2.63 | 3.14 | 101.163 | Cum
High Mass Foundation | Ferro | High Mass |  |  | 3.6 | 3.6 | 2 | 1 | 25.92 | Cum
(-) Deduct For Footing Pcc Qty. | Ferro | [7 empty] | -3.16 | Cum
(-) Deduct For Footing Rcc Qty. | Ferro | [7 empty] | -40.07 | Cum
Total Qty. for Back Filling thise bill | Ferro | [7 empty] | 83.853 | Cum
Dressing
Chimney Foundation Dia-7.0 m (2x3.14x2.85) | Ferro | Chimney |  |  | 3.14 | 2.85 |  | 2 | 17.898 | Sqm
High Mass Foundation | Ferro | High Mass |  |  | 3 | 3 |  | 1 | 9 | Sqm
Ferrow Below Pcc | Ferro | Ferro |  |  | 25.8 | 18.65 |  | 1 | 481.17 | Sqm
Total Qty.For Dressing Work | Ferro | [7 empty] | 508.068 | Sqm
PCC {3--6}Mtr
Chimney Foundation Dia-5.50 m (3.14x2.75x2.75x2.75x0.100=2.37 Cum | Ferro | Chimney |  |  | 2.75 | 2.75 | 0.1 | 3.14 | 2.3746 | Cum
High Mass Foundation | Ferro | High Mass |  |  | 2.8 | 2.8 | 0.1 | 1 | 0.784
Ferrow Below Flooring Pcc | Ferro | Ferro |  |  | 28.8 | 18.65 | 0.1 | 1 | 53.712
Deduction(3.14x4.05x4.05x0.1 | Ferro |  |  |  | 4.05 | 4.05 | 0.1 | -3.14 | -5.1504
Total Qty. for Pcc work in thise bill | Ferro | [7 empty] | 51.7202 | Cum
Ferro
RCC {0--3}Mtr
High Mass Foundation Raft | Ferro | High Mass |  |  | 2.6 | 2.6 | 0.3 | 1 | 2.028
High Mass Foundation Column | Ferro | High Mass |  |  | 1 | 1 | 2.4 | 1 | 2.4
Total Qty. for Footing RCC work | Ferro | [7 empty] | 4.428 | Cum
Ferro
Shuttering {0--3}Mtr
High Mass Foundation Raft(2.6x4=10.4) | Ferro | High Mass |  |  | 10.4 |  | 0.3 | 1 | 3.12
High Mass Foundation Column(1.0x4=4.0) | Ferro | High Mass |  |  | 4 |  | 2.4 | 1 | 9.6
Column C1(1.16+1.16+1.53+1.53=5.38) | Ferro | High Mass |  |  | 5.38 |  | 0.05 | 2 | 0.538
Column C2(0.95+0.95+1.2+1.2=4.30) | Ferro | High Mass |  |  | 4.3 |  | 0.05 | 2 | 0.43
Column C3(0.75+0.75+0.90+0.90=3.30+ | Ferro | High Mass |  |  | 3.3 |  | 0.05 | 11 | 1.815
Column C4(0.9+0.9+1.2+1.2=4.20 | Ferro | High Mass |  |  | 4.2 |  | 0.05 | 1 | 0.21
Column C5(1.42+1.42+0.9+0.9=4.64) | Ferro | High Mass |  |  | 4.64 |  | 0.05 | 4 | 0.928
Column C6(1.25+1.25+0.8+0.8=4.10) | Ferro | High Mass |  |  | 4.1 |  | 0.05 | 6 | 1.23
Column C7(0.8+0.8+0.65+0.65=2.90) | Ferro | High Mass |  |  | 2.9 |  | 0.05 | 6 | 0.87
Total Qty. for Shuttring work | Ferro | [7 empty] | 12.72 | Sqm
Ferro
RCC {3--6}Mtr
1st Floor Slab -Part-A | Ferro | Ferro |  |  | 25.6 | 7.9 | 0.15 | 1 | 30.336
1st Floor Slab -Part-B | Ferro | Ferro |  |  | 10.2 | 5.8 | 0.15 | 1 | 8.874
1st Floor Slab -Part-C | Ferro | Ferro |  |  | 5 | 2.8 | 0.15 | 1 | 2.1
1st Floor Slab -Part-D | Ferro | Ferro |  |  | 10.2 | 9.2 | 0.15 | 1 | 14.076
Deduction | Ferro |  |  |  | 4.7 | 4.5 | 0.15 | -1 | -3.1725
Total Qty. for Footing RCC work | Ferro | [7 empty] | 52.2135 | Cum
Ferro
Shuttering {3--6}Mtr
1st Floor Slab -Part-A | Ferro | Ferro |  |  | 25.6 | 7.9 |  | 1 | 202.24
1st Floor Slab -Part-B | Ferro | Ferro |  |  | 10.2 | 5.8 |  | 1 | 59.16
1st Floor Slab -Part-C | Ferro | Ferro |  |  | 5 | 2.8 |  | 1 | 14
1st Floor Slab -Part-D | Ferro | Ferro |  |  | 10.2 | 9.2 |  | 1 | 93.84
Deduction | Ferro | Ferro |  |  | 4.7 | 4.5 |  | -1 | -21.15
Side=5.0+2.8+10.2+7.9+25.6+7.90+10.2+9.2+10.2+10.6+10.2+2.8=112.60) | Ferro | Ferro |  |  | 112.6 | 0.15 |  | 1 | 16.89
Total Qty. for Shuttring work | Ferro | [7 empty] | 364.98 | Sqm
RCC Chimney
Circular foundation Raft | Ferro | Chimney |  |  | 2.55 | 2.55 | 0.45 | 3.14 | 9.188
Circular foundation Pedestal | Ferro | Chimney |  |  | 2.05 | 2.05 | 3.64 | 3.14 | 48.0329
Total Qty. RCC Work Circular Chimney | Ferro | [7 empty] | 57.2209 | Cum
Shuttering Chimney
Circular foundation Pcc | Ferro | Chimney |  |  | 3.14 | 2.75 | 0.1 | 2 | 1.727
Circular foundation Raft | Ferro | Chimney |  |  | 3.14 | 2.55 | 0.45 | 2 | 7.2063
Circular foundation Pedestral | Ferro | Chimney |  |  | 3.14 | 2.05 | 3.64 | 2 | 46.8614
Shuttering Chimney | Ferro | [7 empty] | 55.7947 | Sqm
Srhinkomp Grouting
Column C1 | Ferro | Ferro |  |  | 1.155 | 1.525 | 0.05 | 2 | 0.17614
Column C2 | Ferro | Ferro |  |  | 0.95 | 1.2 | 0.05 | 2 | 0.114
Column C3 | Ferro | Ferro |  |  | 0.75 | 0.9 | 0.05 | 11 | 0.37125
Column C4 | Ferro | Ferro |  |  | 0.9 | 1.2 | 0.05 | 1 | 0.054
Column C5 | Ferro | Ferro |  |  | 1.42 | 0.9 | 0.05 | 4 | 0.2556
Column C6 | Ferro | Ferro |  |  | 1.25 | 0.8 | 0.05 | 6 | 0.3
Column C7 | Ferro | Ferro |  |  | 0.8 | 0.65 | 0.05 | 6 | 0.156
Total Qty. Grouting Work | Ferro | [7 empty] | 1.427 | Cum

## RA 7
To
Nakoda Pipe Impex Pvt Ltd
Ferro Alloys 7th Ra | [11 empty] | 2023-08-01
Sl No | Item No | Description | UOM | Rate |  | Division | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
|  |  |  | Old | New |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 |  | Ferro | 3363.706 | 538192.96 |  | 0 | 3363.706 | 538192.96
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 |  | 180 | Ferro | 149.28 | 26870.391 | 66.8065 | 12025.1614 | 216.0864 | 38895.5524
3 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m4 | 176 |  | Ferro | 94.61 | 16651.36 |  | 0 | 94.61 | 16651.36
4 |  | Backfilling | m3 | 85 |  | Ferro | 2633.632 | 223858.7202 |  | 0 | 2633.632 | 223858.7202
5 |  | Backfilling | m3 |  | 85 | Ferro | 83.85 | 0 | 376.4365 | 31997.0985 | 460.2865 | 0
6 |  | Watering and consolodation | m3 | 60 |  | Ferro | 2664.5813 | 159874.8795 |  | 0 | 2664.5813 | 159874.8795
7 |  | Soil Dressing | m2 | 25 | 25 | Ferro | 508.07 | 12701.75 |  | 0 | 508.07 | 12701.75
8 |  | Sand Filling | m3 | 700 |  | Ferro | 98.546 | 68982.2 |  | 0 | 98.546 | 68982.2
9 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 |  | Ferro | 56.16 | 117936 |  | 0 | 56.16 | 117936
10 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 |  | 2300
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 |  | Ferro | 55.8194 | 128942.7544 |  | 0 | 55.8194 | 128942.7544
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 |  | 2530 |  |  |  | 59.0261 | 149336.052
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 |  | Ferro | 324.8259 | 844547.21 |  | 0 | 324.8259 | 844547.21
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 |  | 2750 | Ferro | 61.6489 | 0 | 64.6225 | 177712.0125 | 126.2715 | 0
15 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 2600 |  | Ferro | 68.47 | 178022 |  | 0 | 68.47 | 178022
16 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 |  | 3025 | Ferro | 52.2135 | 0 |  | 0 | 52.2135 | 0
17 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 |  | Ferro | 0 | 0 |  | 0 | 0 | 0
18 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 |  | 3300 | Ferro |  |  |  |  | 0 | 0
19 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 9 M t o +/-12Mtrs heights/depth with proper compaction and curing | m3 |  | 3575 | Ferro |  |  | 50.1135 | 179155.7625 | 50.1135 | 0
20 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 |  | Ferro | 923.5743 | 369429.737 | -15.6903 | -6276.12 | 907.884 | 363153.617
21 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. {Circular foundation} | m2 | 400 |  | Ferro | 352.5067 | 141002.664 |  | 0 | 352.5067 | 141002.664
22 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. to +/- 6 Mtr | m2 | 440 |  | Ferro | 364.98 | 160591.2 |  | 0 | 364.98 | 160591.2
23 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M. to +/-9 Mtr | m2 | 480 |  | Ferro |  |  |  |  | 0 | 0
24 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 9M. to +/- 12 Mtr | m2 | 520 |  | Ferro |  |  | 350.98 | 182509.6 | 350.98 | 182509.6
25 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | 8500 | Ferro | 31.584 | 221088 | 7.17 | 60945 | 38.754 | 271278
26 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 7700 | 9350 | Ferro | 5.72 | 44044 |  | 0 | 5.72 | 44044
27 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT |  | 10200 | Ferro
28 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.9-12 | MT |  | 11050 | Ferro |  |  | 5.5 | 60775
29 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 |  |  | 2.8236 | 36707.32 | 0.71502 | 9295.26 | 3.5387 | 46002.58
30 | 40 | Pocket Fixing Work | Nos | 500 |  |  | 45 | 22500 |  | 0 | 45 | 22500
31 | 40 | Shrinkomp Grouting | Cum |  | 4100 |  | 1.427 | 0 | 0.289 | 1184.9 | 1.716 | 0
[7 empty] | 0 |  |  | 0 | 0
[8 empty] | 3311943.1461 |  | 858659.7269 |  | 3559687.0475

## RA 7 Measuremet
SHREE NAKODA PIPE IMPEX PVT LTD
DETAIL OF MEASURMENT & CALCULATION OF QUANTITY FERRO ALLOYS-7th
AG INFRATECH
DESCRIPTION | NOS | LENGTH (M) | WIDTH (M) | H/D | QTY | Unit
1. Earth Excavation Work Up to 0.00 Lvl to +/-3.0 m Gl
Ferro Alloys 1st part (Grid-1 to 6- A to E) | 1 | 30.35 | 23.8 | 3.114 | 2249.3356
Ferro Alloys 2nd part (Grid-1 to 6-F ) | 1 | 30.45 | 4.525 | 3.114 | 429.0664
Ferro Alloys 3rd part (Grid-1 to 6- G) | 1 | 30.4 | 4.4 | 3 | 401.28
Ferro Alloys 4th part (Grid-E to F Plinth Beam Excavation)(Avg ngl=95.089-plinth beam bottom soil RL=93.95=1.139 Depth of Excavation) | 2 | 7.6 | 1.5 | 1.139 | 25.9692
Ferro Alloys 5th Part (Grid-F To G plinth Beam Excavation) | 2 | 10.5 | 1.5 | 1.139 | 35.8785
Ferro Alloys 6th Part (Grid-E to F Middle Part Excavation)(Avg. NGl RL=95.089-Excavation RL=94.729=0.36 Depth) | 2 | 27.4 | 7.6 | 0.36 | 149.9328
Ferro Alloys 5th Part (Grid-F To G plinth Beam Excavation) | 2 | 27.4 | 10.5 | 0.36 | 207.144
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | 3.14 | 3.5 | 3.5 | 2.63 | 101.163
High Mass Foundation | 1 | 3.6 | 3.6 | 2 | 25.92
Ferrow Excavation Below Pcc | 1 | 25.8 | 18.65 | 0.1 | 48.117
Total Qty. |  |  |  | A | 3673.8065 | Cum
Previous Bill Qty. |  |  |  | B | 3607 | Cum
Total Qty. for Excavation in Thise Bill up to +/-3.0 m GL |  |  |  | A-B | 66.8065 | Cum
2. Back Filling Work
Ferro Alloys 1st part (Grid-1 to 6- A to E) | 1 | 30.35 | 23.8 | 3.114 | 2249.3356
Ferro Alloys 2nd part (Grid-1 to 6-F ) | 1 | 30.45 | 4.525 | 3.114 | 429.0664
Ferro Alloys 3rd part (Grid-1 to 6- G) | 1 | 30.4 | 4.4 | 3 | 401.28
Ferro Alloys 4th part (Grid-E to F Plinth Beam Excavation)(Avg ngl=95.089-plinth beam bottom soil RL=93.95=1.139 Depth of Excavation) | 2 | 7.6 | 1.5 | 1.139 | 25.9692
Ferro Alloys 5th Part (Grid-F To G plinth Beam Excavation) | 2 | 10.5 | 1.5 | 1.139 | 35.8785
Ferro Alloys 6th Part (Grid-E to F Middle Part Excavation)(Avg. NGl RL=95.089-Excavation RL=94.729=0.36 Depth) | 2 | 27.4 | 7.6 | 0.36 | 149.9328
Ferro Alloys 5th Part (Grid-F To G plinth Beam Excavation) | 2 | 27.4 | 10.5 | 0.36 | 207.144
Chimney Foundation Dia-7.0 m (3.14x3.5x3.5x2.63=101.16 Cum | 3.14 | 3.5 | 3.5 | 2.63 | 101.163
High Mass Foundation | 1 | 3.6 | 3.6 | 2 | 25.92
Ferrow Excavation Below Pcc | 1 | 25.8 | 18.65 | 0.1 | 48.117
Total Qty. |  |  |  | Total | 3673.8065 | Cum
(-) Deduct For Footing Pcc Qty. |  |  |  |  | -57.39 | Cum
(-) Deduct For Footing Rcc Qty. |  |  |  |  | -222.15 | Cum
(-) Deduct For Column Rcc up to 0.00 Lvl Qty. |  |  |  |  | -35.26 | Cum
(-) Deduct For Column Rcc up to 0.00 Lvl Qty. |  |  |  |  | -174.1 | Cum
(-) Deduct For Below plinth beam Pcc Qty. |  |  |  |  | -12.91 | Cum
(-) Deduct For Plinth Beam Rcc Qty. |  |  |  |  | -34.85 | Cum
(-) Deduct For Footing Pcc Qty. |  |  |  |  | -3.16 | Cum
(-) Deduct For Footing Rcc Qty. |  |  |  |  | -40.07 | Cum
Total Qty. |  |  |  | A | 3093.9165 | Cum
Previous Bill Qty. |  |  |  | B | 2717.48 | Cum
Total Qty. for Back Filling thise bill |  |  |  | A-B | 376.4365 | Cum
3. Footing Pcc Work +/-3.0 m GL
Ferro Alloys Footing F1 (Grid-E-3-5) | 2 | 4.7 | 4.7 | 0.118 | 5.2132
Ferro Alloys Footing F2 (Grid-B-3-5) | 2 | 4.7 | 4.7 | 0.15 | 6.627
Ferro Alloys Footing F3 (Grid-A-1 to 6/c-6) | 7 | 2.95 | 2.95 | 0.15 | 9.1376
Ferro Alloys Footing F3A (Grid-A-B-C-D-1) | 4 | 2.95 | 2.95 | 0.15 | 5.2215
Ferro Alloys Footing F4 (Grid-D-2) | 1 | 3.45 | 3.45 | 0.15 | 1.7854
Ferro Alloys Footing F5 (Grid-E-1-2-4-6) | 4 | 3.7 | 3.7 | 0.15 | 8.214
Ferro Alloys Footing F6 (Grid-F-1 to 6) | 6 | 2.7 | 2.7 | 0.15 | 6.561
Ferro Alloys Footing F7 (Grid-G-1 to 6) | 6 | 1.7 | 1.7 | 0.15 | 2.601
Ferro Alloys Footing F8 (Grid-B-2-4/c-2-5) | 13 | 1.2 | 1.2 | 0.15 | 2.808
Ferro Alloys Center Circular Footing (3.14x4.55x4.55x0.15=9.75cum) | 3.14 | 4.55 | 4.55 | 0.15 | 9.7509
Pcc Below Plinth Beam(A-1 to 6)(3.75+3.75+4.75+4.75+4.75=21.75 | 1 | 21.75 | 0.5 | 0.1 | 1.0875
Plinth Beam(B-1 to 6)(3.9+3.9+10.1+4.6=22.50 | 1 | 22.5 | 0.5 | 0.1 | 1.125
Plinth Beam(C-1 to 2)(=3.9) | 1 | 3.9 | 0.5 | 0.1 | 0.195
Plinth Beam(C"-5 to 6)(=4.90) | 1 | 4.9 | 0.5 | 0.1 | 0.245
Plinth Beam(D-1 to 3)(3.6+3.9=7.5) | 1 | 7.5 | 0.5 | 0.1 | 0.375
Plinth Beam(E-1 to 6)(3.6+3.288+4.288+4.288+4.288=19.75) | 1 | 19.75 | 0.5 | 0.1 | 0.9875
Plinth Beam(F-1 to 6)(3.7+3.7+4.7+4.7+4.7=21.5) | 1 | 21.5 | 0.5 | 0.1 | 1.075
Plinth Beam(G-1 to 6)(3.85+3.85+4.85+4.85+4.85=22.25) | 1 | 22.25 | 0.5 | 0.1 | 1.1125
Plinth Beam(A-G-1)(13.975+12.275+3.415+3.75+3.75+3.675=40.84) | 1 | 40.84 | 0.5 | 0.1 | 2.042
Plinth Beam(A-E-2)(3.175+12.45=15.625) | 1 | 15.625 | 0.5 | 0.1 | 0.78125
Plinth Beam(A-E-3)(12.51+3.45=15.96) | 1 | 15.96 | 0.5 | 0.1 | 0.798
Plinth Beam(A-B-4)(3.90) | 1 | 3.9 | 0.5 | 0.1 | 0.195
Plinth Beam(A-E-5)(12.51+3.45=15.96) | 1 | 15.96 | 0.5 | 0.1 | 0.798
Plinth Beam(A-G-6)(13.975+12.275+5.95+5.925+3.675=41.79) | 1 | 41.79 | 0.5 | 0.1 | 2.0895
Furnace top portion ofter sand filling 100 mm Pcc iiner volume (3.14x3.25x3.25x0.1=3.31cum | 3.31 | 1 | 1 | 1 | 3.31
Chimney Foundation Dia-5.50 m (3.14x2.75x2.75x2.75x0.100=2.37 Cum | 3.14 | 2.75 | 2.75 | 0.1 | 2.3746
High Mass Foundation | 1 | 2.8 | 2.8 | 0.1 | 0.784
Ferrow Below Flooring Pcc | 1 | 28.8 | 18.65 | 0.1 | 53.712
Deduction(3.14x4.05x4.05x0.1 | -3.14 | 4.05 | 4.05 | 0.1 | -5.1504
Total Qty. |  |  |  | A | 125.8561 | Cum
Previous Bill Qty. |  |  |  | B | 66.83 | Cum
Total Qty. for Footing Pcc work in thise bill |  |  |  | A-B | 59.0261 | Cum
4. RCC Work
Ferro Alloys Footing F1 (Grid-E-3-5) | 2 | 4.5 | 4.5 | 0.9 | 36.45
Ferro Alloys Footing F2 (Grid-B-3-5) | 2 | 4.5 | 4.5 | 0.9 | 36.45
Ferro Alloys Footing F3 (Grid-A-1 to 6/c-6) | 7 | 2.75 | 2.75 | 0.6 | 31.7625
Ferro Alloys Footing F3A (Grid-A-B-C-D-1) | 4 | 2.75 | 2.75 | 0.6 | 18.15
Ferro Alloys Footing F4 (Grid-D-2) | 1 | 3.25 | 3.25 | 0.75 | 7.9219
Ferro Alloys Footing F5 (Grid-E-1-2-4-6) | 4 | 3.5 | 3.5 | 0.7 | 34.3
Ferro Alloys Footing F6 (Grid-F-1 to 6) | 6 | 2.5 | 2.5 | 0.5 | 18.75
Ferro Alloys Footing F7 (Grid-G-1 to 6) | 6 | 1.5 | 1.5 | 0.45 | 6.075
Ferro Alloys Footing F8 (Grid-B-2-4/c-2-5) | 13 | 1 | 1 | 0.3 | 3.9
Ferro Alloys Center Circular Footing (3.14x4.45x4.45x0.50=30.08cum) | 3.14 | 4.45 | 4.45 | 0.5 | 31.0899
Concentric Circular foundation(A=3.14x(3.85x3.85-3.25x3.25)x2.4=32.10Cum | 1 | 1 | 1 | 32.1 | 32.1
Inner side wall | 2 | 6.5 | 0.6 | 2.5 | 19.5
Ferro Alloys Pedestal F1 (Grid-E-3-5) | 2 | 1.525 | 1.15 | 1.99 | 6.9799
Ferro Alloys Pedestral F2 (Grid-B-3-5) | 2 | 1.2 | 0.95 | 1.98 | 4.5144
Ferro Alloys Pedestral F3 (Grid-A-1 to 6/c-6) | 7 | 0.9 | 0.75 | 2.33 | 11.0092
Ferro Alloys PedestralFooting F3A (Grid-A-B-C-D-1) | 4 | 0.9 | 0.75 | 2.33 | 6.291
Ferro Alloys Pedestral F4 (Grid-D-2) | 1 | 1.2 | 0.9 | 2.23 | 2.4084
Ferro Alloys PedestralFooting F5 (Grid-E-1-2-4-6) | 4 | 1.42 | 0.9 | 2.25 | 11.502
Ferro Alloys Auxiliry column up to plinth beam bott. (Grid-E-2-4-C-2-C'-5-D-3) | 13 | 0.3 | 0.3 | 2.9 | 3.393
Ferro Alloys Pedestral F6 (Grid-F-1 to 6) | 6 | 1.25 | 0.8 | 2 | 12
Ferro Alloys Pedestral F7 (Grid-G-1 to 6) | 6 | 0.8 | 0.65 | 2 | 6.24
Plinth Beam(A-1 to 6)(3.75+3.75+4.75+4.75+4.75=21.75 | 1 | 21.75 | 0.3 | 0.45 | 2.9362
Plinth Beam(B-1 to 6)(3.9+3.9+10.1+4.6=22.50 | 1 | 22.5 | 0.3 | 0.45 | 3.0375
Plinth Beam(C-1 to 2)(=3.9) | 1 | 3.9 | 0.3 | 0.45 | 0.5265
Plinth Beam(C"-5 to 6)(=4.90) | 1 | 4.9 | 0.3 | 0.45 | 0.6615
Plinth Beam(D-1 to 3)(3.6+3.9=7.5) | 1 | 7.5 | 0.3 | 0.45 | 1.0125
Plinth Beam(E-1 to 6)(3.6+3.288+4.288+4.288+4.288=19.75) | 1 | 19.75 | 0.3 | 0.45 | 2.6662
Plinth Beam(F-1 to 6)(3.7+3.7+4.7+4.7+4.7=21.5) | 1 | 21.5 | 0.3 | 0.45 | 2.9025
Plinth Beam(G-1 to 6)(3.85+3.85+4.85+4.85+4.85=22.25) | 1 | 22.25 | 0.3 | 0.45 | 3.0038
Plinth Beam(A-G-1)(13.975+12.275+3.415+3.75+3.75+3.675=40.84) | 1 | 40.84 | 0.3 | 0.45 | 5.5134
Plinth Beam(A-E-2)(3.175+12.45=15.625) | 1 | 15.625 | 0.3 | 0.45 | 2.1094
Plinth Beam(A-E-3)(12.51+3.45=15.96) | 1 | 15.96 | 0.3 | 0.45 | 2.1546
Plinth Beam(A-B-4)(3.90) | 1 | 3.9 | 0.3 | 0.45 | 0.5265
Plinth Beam(A-E-5)(12.51+3.45=15.96) | 1 | 15.96 | 0.3 | 0.45 | 2.1546
Plinth Beam(A-G-6)(13.975+12.275+5.95+5.925+3.675=41.79) | 1 | 41.79 | 0.3 | 0.45 | 5.6416
Circular Foundation Above Beam | 1 | 7.244 | 0.3 | 1.3 | 2.8252
Circular Foundation Above Beam | 2 | 6.954 | 0.3 | 1.3 | 5.4241
Circular Foundation Above Beam | 2 | 6.174 | 0.3 | 1.3 | 4.8157
Circular Foundation Above Beam | 2 | 4.665 | 0.3 | 1.3 | 3.6387
Circular Foundation Above Beam | 2 | 1.212 | 0.3 | 1.3 | 0.94536
High Mass Foundation Raft | 1 | 2.6 | 2.6 | 0.3 | 2.028
High Mass Foundation Column | 1 | 1 | 1 | 2.4 | 2.4
Groung floor Rcc Work | 1 | 25.8 | 18.65 | 0.15 | 72.1755
Deduction For Farnace part | -3.14 | 3.6 | 3.6 | 0.15 | -6.1042
Total Qty |  |  |  | A | 463.7826 | Cum
Previous Bill Qty. |  |  |  | B | 399.16 | Cum
Total Qty. for Footing RCC work in thise bill |  |  |  | A-B | 64.6225 | Cum
5.0 Shuttring Work
Pcc
Ferro Alloys Footing F1 (Grid-E-3-5) (4.7x4=18.80 m) | 2 | 18.8 |  | 0.15 | 5.64
Ferro Alloys Footing F2 (Grid-B-3-5) | 2 | 18.8 |  | 0.15 | 5.64
Ferro Alloys Footing F3 (Grid-A-1 to 6/c-6) (2.95x4=11.80) | 7 | 11.8 |  | 0.15 | 12.39
Ferro Alloys Footing F3A (Grid-A-B-C-D-1) | 4 | 11.8 |  | 0.15 | 7.08
Ferro Alloys Footing F4 (Grid-D-2) (3.45x4=13.80) | 1 | 13.8 |  | 0.15 | 2.07
Ferro Alloys Footing F5 (Grid-E-1-2-4-6) (3.7x4=14.80) | 4 | 18.8 |  | 0.15 | 11.28
Ferro Alloys Footing F6 (Grid-F-1 to 6) (2.7x4=10.80) | 6 | 10.8 |  | 0.15 | 9.72
Ferro Alloys Footing F7 (Grid-G-1 to 6) (1.7x4=6.80) | 6 | 6.8 |  | 0.15 | 6.12
Ferro Alloys Footing F8 (Grid-B-2-4/c-2-5) (1.2x4=4.80) | 13 | 4.8 |  | 0.15 | 9.36
Ferro Alloys Center Circular Footing (2x3.14x4.55x0.15=4.281 sqm) | 4.28 | 1 |  | 1 | 4.28
Rcc |  |  |  |  | 0
Ferro Alloys Footing F1 (Grid-E-3-5) (4.5x4=18 m) | 2 | 18 |  | 0.9 | 32.4
Ferro Alloys Footing F2 (Grid-B-3-5) | 2 | 18 |  | 0.9 | 32.4
Ferro Alloys Footing F3 (Grid-A-1 to 6/c-6)(2.75x4=11) | 7 | 11 |  | 0.6 | 46.2
Ferro Alloys Footing F3A (Grid-A-B-C-D-1) | 4 | 11 |  | 0.6 | 26.4
Ferro Alloys Footing F4 (Grid-D-2) (3.25x4=13 ) | 1 | 13 |  | 0.75 | 9.75
Ferro Alloys Footing F5 (Grid-E-1-2-4-6) (3.5x4=14) | 4 | 14 |  | 0.7 | 39.2
Ferro Alloys Footing F6 (Grid-F-1 to 6)(2.5x410) | 6 | 10 |  | 0.5 | 30
Ferro Alloys Footing F7 (Grid-G-1 to 6) (1.5x4=6.0) | 6 | 6 |  | 0.45 | 16.2
Ferro Alloys Footing F8 (Grid-B-2-4/c-2-5)(1x4=4) | 13 | 4 |  | 0.3 | 15.6
Ferro Alloys Center Circular Footing (2x3.14x4.45x0.50=13.97 sqm) | 13.97 | 1 | 1 | 1 | 13.97
Circumference outer side Circular foundation(A=2x3.14x3.85=24.17 | 1 | 24.17 |  | 2.5 | 60.425
Circumference inner side Circular foundation(A=2x3.14x3.25=20.41 | 1 | 20.41 |  | 2.5 | 51.025
Inner side wall (6.5+6.5+0.6+0.6=14.20) | 2 | 14.2 |  | 2.5 | 71
Ferro Alloys Pedestal F1 (Grid-E-3-5)(1.53+1.53+1.15+1.15=5.36) | 2 | 5.36 |  | 1.99 | 21.3328
Ferro Alloys Pedestral F2 (Grid-B-3-5)(1.2+1.2+0.95+0.95=4.30) | 2 | 4.3 |  | 1.98 | 17.028
Ferro Alloys Pedestral F3 (Grid-A-1 to 6/c-6) (0.9+0.9+0.75+0.75=3.30) | 7 | 3.3 |  | 2.33 | 53.823
Ferro Alloys PedestralFooting F3A (Grid-A-B-C-D-1) | 4 | 3.3 |  | 2.33 | 30.756
Ferro Alloys Pedestral F4 (Grid-D-2)(1.2+1.2+0.9+0.9=4.20) | 1 | 4.2 |  | 2.23 | 9.366
Ferro Alloys PedestralFooting F5 (Grid-E-1-2-4-6)(1.42+1.42+0.9+0.9=4.64) | 4 | 4.64 | 9 | 2.25 | 41.76
Pcc |  |  |  |  | 0
Pcc Below Plinth Beam(A-1 to 6)(3.75+3.75+4.75+4.75+4.75=21.75 | 2 | 21.75 |  | 0.1 | 4.35
Plinth Beam(B-1 to 6)(3.9+3.9+10.1+4.6=22.50 | 2 | 22.5 |  | 0.1 | 4.5
Plinth Beam(C-1 to 2)(=3.9) | 2 | 3.9 |  | 0.1 | 0.78
Plinth Beam(C"-5 to 6)(=4.90) | 2 | 4.9 |  | 0.1 | 0.98
Plinth Beam(D-1 to 3)(3.6+3.9=7.5) | 2 | 7.5 |  | 0.1 | 1.5
Plinth Beam(E-1 to 6)(3.6+3.288+4.288+4.288+4.288=19.75) | 2 | 19.75 |  | 0.1 | 3.95
Plinth Beam(F-1 to 6)(3.7+3.7+4.7+4.7+4.7=21.5) | 2 | 21.5 |  | 0.1 | 4.3
Plinth Beam(G-1 to 6)(3.85+3.85+4.85+4.85+4.85=22.25) | 2 | 22.25 |  | 0.1 | 4.45
Plinth Beam(A-G-1)(13.975+12.275+3.415+3.75+3.75+3.675=40.84) | 2 | 40.84 |  | 0.1 | 8.168
Plinth Beam(A-E-2)(3.175+12.45=15.625) | 2 | 15.625 |  | 0.1 | 3.125
Plinth Beam(A-E-3)(12.51+3.45=15.96) | 2 | 15.96 |  | 0.1 | 3.192
Plinth Beam(A-B-4)(3.90) | 2 | 3.9 |  | 0.1 | 0.78
Plinth Beam(A-E-5)(12.51+3.45=15.96) | 2 | 15.96 |  | 0.1 | 3.192
Plinth Beam(A-G-6)(13.975+12.275+5.95+5.925+3.675=41.79) | 2 | 41.79 |  | 0.1 | 8.358
Rcc |  |  |  |  | 0
Ferro Alloys Auxiliry column up to plinth beam bott. (Grid-E-2-4-C-2-C'-5-D-3) (0.3x4=1.20) | 13 | 1.2 |  | 2.9 | 45.24
Ferro Alloys Pedestral F6 (Grid-F-1 to 6)(1.25+1.25+0.80+0.80=4.10) | 6 | 4.1 |  | 2 | 49.2
Ferro Alloys Pedestral F7 (Grid-G-1 to 6)(0.65+0.65+0.8+0.8=2.90) | 6 | 2.9 |  | 2 | 34.8
Plinth Beam(A-1 to 6)(3.75+3.75+4.75+4.75+4.75=21.75 | 2 | 21.75 |  | 0.45 | 19.575
Plinth Beam(B-1 to 6)(3.9+3.9+10.1+4.6=22.50 | 2 | 22.5 |  | 0.45 | 20.25
Plinth Beam(C-1 to 2)(=3.9) | 2 | 3.9 |  | 0.45 | 3.51
Plinth Beam(C"-5 to 6)(=4.90) | 2 | 4.9 |  | 0.45 | 4.41
Plinth Beam(D-1 to 3)(3.6+3.9=7.5) | 2 | 7.5 |  | 0.45 | 6.75
Plinth Beam(E-1 to 6)(3.6+3.288+4.288+4.288+4.288=19.75) | 2 | 19.75 |  | 0.45 | 17.775
Plinth Beam(F-1 to 6)(3.7+3.7+4.7+4.7+4.7=21.5) | 2 | 21.5 |  | 0.45 | 19.35
Plinth Beam(G-1 to 6)(3.85+3.85+4.85+4.85+4.85=22.25) | 2 | 22.25 |  | 0.45 | 20.025
Plinth Beam(A-G-1)(13.975+12.275+3.415+3.75+3.75+3.675=40.84) | 2 | 40.84 |  | 0.45 | 36.756
Plinth Beam(A-E-2)(3.175+12.45=15.625) | 2 | 15.625 |  | 0.45 | 14.0625
Plinth Beam(A-E-3)(12.51+3.45=15.96) | 2 | 15.96 |  | 0.45 | 14.364
Plinth Beam(A-B-4)(3.90) | 2 | 3.9 |  | 0.45 | 3.51
Plinth Beam(A-E-5)(12.51+3.45=15.96) | 2 | 15.96 |  | 0.45 | 14.364
Plinth Beam(A-G-6)(13.975+12.275+5.95+5.925+3.675=41.79) | 2 | 41.79 |  | 0.45 | 37.611
Circular Foundation Above Beam (1.3x2=2.60) | 1 | 7.244 |  | 2.6 | 18.8344
Stopper | 2 | 0.3 |  | 1.3 | 0.78
Circular Foundation Above Beam | 2 | 6.954 |  | 2.6 | 36.1608
Stopper | 2 | 0.3 |  | 1.3 | 0.78
Circular Foundation Above Beam | 2 | 6.174 |  | 2.6 | 32.1048
Stopper | 2 | 0.3 |  | 1.3 | 0.78
Circular Foundation Above Beam | 2 | 4.665 |  | 2.6 | 24.258
Stopper | 2 | 0.3 |  | 1.3 | 0.78
Circular Foundation Above Beam | 2 | 1.212 |  | 2.6 | 6.3024
Stopper | 2 | 0.3 |  | 1.3 | 0.78
High Mass Foundation Raft(2.6x4=10.4) | 1 | 10.4 |  | 0.3 | 3.12
High Mass Foundation Column(1.0x4=4.0) | 1 | 4 |  | 2.4 | 9.6
Column C1(1.16+1.16+1.53+1.53=5.38) | 2 | 5.38 |  | 0.05 | 0.538
Column C2(0.95+0.95+1.2+1.2=4.30) | 2 | 4.3 |  | 0.05 | 0.43
Column C3(0.75+0.75+0.90+0.90=3.30+ | 11 | 3.3 |  | 0.05 | 1.815
Column C4(0.9+0.9+1.2+1.2=4.20 | 1 | 4.2 |  | 0.05 | 0.21
Column C5(1.42+1.42+0.9+0.9=4.64) | 4 | 4.64 |  | 0.05 | 0.928
Column C6(1.25+1.25+0.8+0.8=4.10) | 6 | 4.1 |  | 0.05 | 1.23
Column C7(0.8+0.8+0.65+0.65=2.90) | 6 | 2.9 |  | 0.05 | 0.87
Groung floor Rcc Work | 2 | 25.8 |  | 0.15 | 7.74
Groung floor Rcc Work | 2 | 18.65 |  | 0.15 | 5.595
Banker Column Grouting work(0.85x4=3.40) | 8 | 3.4 |  | 0.05 | 1.36
Total Qty. |  |  |  | A | 1260.3897 | Sqm
Previous Bill Qty. |  |  |  | B | 1276.08 | Sqm | 1276
Total Qty. for Shuttring work in thise Bill |  |  |  | A-B | -15.6903 | Sqm
5. Pedestal MS Bolt Fixing Work |  | NO | Total Nos | Per Bolt Weight in KG | Total Weight in KG
Ferro Alloys Pedestal F1 (Grid-E-3-5) 1600 mm Long | 2 | 8 | 16 | 14.78 | 236.48
Ferro Alloys Pedestral F2 (Grid-B-3-5) 1600mm Long | 2 | 6 | 12 | 14.78 | 177.36
Ferro Alloys Pedestral F3 (Grid-A-1 to 6/c-6) 1250 Long | 7 | 6 | 42 | 11.4 | 478.8
Ferro Alloys PedestralFooting F3A (Grid-A-B-C-D-1) 1250 long | 4 | 6 | 24 | 11.4 | 273.6
Ferro Alloys Pedestral F4 (Grid-D-2) 1600mm Long | 1 | 6 | 6 | 14.87 | 89.22
Ferro Alloys PedestralFooting F5 (Grid-E-1-2-4-6) 1600 mm Long | 4 | 8 | 32 | 14.78 | 472.96
Ferro Alloys Pedestal F6 (Grid-F-1 to 6) 1600 mm Long | 6 | 8 | 48 | 14.78 | 709.44
Ferro Alloys Pedestral F7 (Grid-G-1 to 6) 950mm Long | 6 | 7 | 42 | 8.98 | 377.16
Circular Chimney m32 (2000mm Long | 1 | 36 | 36 | 20 | 720
Total Qty. for Pedestal MS Bolt Fixing work |  |  |  |  | 3535.02 | Kg
Total Qty. |  |  |  | A | 3.535 | MT
Previous Bill Qty. |  |  |  | B | 2.82 | MT
Total Qty. for Pedestal MS Bolt Fixing work in thise Bill |  |  |  | A-B | 0.71502 | MT
6. RCC Work Above+9.0 to 12.0 m GL
1st Floor Slab -Part-A | 1 | 25.6 | 7.9 | 0.15 | 30.336
1st Floor Slab -Part-B | 1 | 10.2 | 5.8 | 0.15 | 8.874
1st Floor Slab -Part-C | 1 | 10.2 | 9.2 | 0.15 | 14.076
Deduction | -1 | 4.7 | 4.5 | 0.15 | -3.1725
Total Qty. for Footing RCC work |  |  |  |  | 50.1135 | Cum
7. Shuttring Work Above+9.0 to 12.0 mm GL
1st Floor Slab -Part-A | 1 | 25.6 | 7.9 |  | 202.24
1st Floor Slab -Part-B | 1 | 10.2 | 5.8 |  | 59.16
1st Floor Slab -Part-C | 1 | 10.2 | 9.2 |  | 93.84
Deduction | -1 | 4.7 | 4.5 |  | -21.15
Side=5.0+2.8+10.2+7.9+25.6+7.90+10.2+9.2+10.2+10.6+10.2+2.8=112.60) | 1 | 112.6 | 0.15 |  | 16.89
Total Qty. for Shuttring work |  |  |  |  | 350.98 | Sqm
8. RCC Work Circular Chimney
Circular foundation Raft | 3.14 | 2.55 | 2.55 | 0.45 | 9.188
Circular foundation Pedestral | 3.14 | 2.05 | 2.05 | 3.64 | 48.0329
Total Qty. RCC Work Circular Chimney |  |  |  |  | 57.2209 | Cum
9. Shuttring Work Circular Chimney
Circular foundation Pcc | 2 | 3.14 | 2.75 | 0.1 | 1.727
Circular foundation Raft | 2 | 3.14 | 2.55 | 0.45 | 7.2063
Circular foundation Pedestral | 2 | 3.14 | 2.05 | 3.64 | 46.8614
Total Qty. RCC Work Circular Chimney |  |  |  |  | 55.7947 | Sqm
10. Shrinkomp cement Grouting Work {Bunker & Hopper}
Banker Column C1 | 8 | 0.85 | 0.85 | 0.05 | 0.289
Total Qty. Grouting Work |  |  |  |  | 0.289 | Cum