## Abstract
To
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Estimate
Ferro Alloys
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Estimated Value
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all | m3 | 160 | [5 empty] | 3575.8176 | 572130.8216 | Chimney Quantity added
|  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all (3-6)Mtr | m3 | 176 | [5 empty] | 94.6128 | 16651.8506 |  | 94.61
2 |  | Backfilling | m3 | 85 | [5 empty] | 3236.9109 | 275137.4286 | Chimney Quantity added
3 |  | Soil Dressing | m3 | 25 | [5 empty] | 726.33 | 18158.25
4 |  | Sand Filling | m3 | 700 | [5 empty] | 104.688 | 73281.5811
5 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2100 | [5 empty] | 56.155 | 117925.584
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2310 | [5 empty] | 168.1629 | 388456.2947
7 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2600 | [5 empty] | 472.3674 | 1228155.1444
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 2860 | [5 empty] | 68.85 | 196911
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 9 M t o +/-12Mtrs heights/depth with proper compaction and curing | m3 | 3380 | [5 empty] | 68.85 | 232713
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 15 M t o +/-18Mtrs heights/depth with proper compaction and curing | m3 | 3900 | [5 empty] | 68.85 | 268515
11 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | [5 empty] | 1220.291 | 488116.417
12 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- (3--6)M. | m2 | 440 | [5 empty] | 472.05 | 207702
13 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- (9--12)M. | m2 | 520 | [5 empty] | 472.05 | 245466
14 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- (15--18)M. | m2 | 600 | [5 empty] | 472.05 | 283230
15 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 7000 | [6 empty] | 0
16 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. (6--9) Mtr | MT | 7700 | [5 empty] | 10.5754 | 81430.272
17 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. (9--12)Mtr | MT | 9100 | [5 empty] | 10.5754 | 96235.776
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete (15--18)Mtr | MT | 10500 | [5 empty] | 10.5754 | 111041.28
19 |  | Bolt Fixing of anchor and foundation Bolt | MT | 13000 | [6 empty] | 0
20 | 40 | Pocket Fixing Work | Nos | 500 | [6 empty] | 0
21 |  | RCC For Circular structure | m3 | 750 | [6 empty] | 0
22 |  | Shuttering For Circular structure | m2 | 150 | [6 empty] | 0
0
[7 empty] | 0 |  | 0 |  | 4901257.6999

## Measurement Sheet
To Nakoda Impex Pvt Ltd
Ferro Furnace
Division:- ferro alloys
Estimate Balance sheet
Sl No | Description | Block | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit
[5 empty] | From | To
Excavation & Backfilling
Excavation
1 | 0--3 Mtr | Ferro | Raft |  | 91.584 | 94.584 | 30.35 | 23.8 | 3 | 1 | 2166.99 | Cum | 2249.3356 | -82.3456
| 0--3 Mtr | Ferro | Raft |  | 91.584 | 94.584 | 30.4 | 4.4 | 3 | 1 | 401.28 | Cum | 429.0664 | -27.7864
| 0--3 Mtr | Ferro | Raft |  | 91.584 | 94.584 | 30.45 | 4.525 | 3 | 1 | 413.3587 | Cum | 401.28 | 12.0788
| 0--3 Mtr | Ferro | Raft |  | 93.589 | 95.089 | 7.6 | 1.5 | 1.139 | 2 | 25.9692 | Cum
| 0--3 Mtr | Ferro | Raft |  | 93.589 | 95.089 | 10.5 | 1.5 | 1.139 | 2 | 35.8785 | Cum
| 0--3 Mtr | Ferro | Raft |  | 87.489 | 95.089 | 27.4 | 7.6 | 0.36 | 2 | 149.9328 | Cum
| 0--3 Mtr | Ferro | Raft |  | 84.589 | 95.089 | 27.4 | 10.5 | 0.36 | 2 | 207.144 | Cum
| 0--3 Mtr | Ferro | Chimney |  | 91.954 | 94.584 | 3.142 | 12.25 | 2.63 | 1 | 101.2274 | Cum
| 0--3 Mtr | Ferro | Hish Mask |  | 92.584 | 94.584 | 3.6 | 3.6 | 2 | 1 | 25.92 | Cum
| 0--3 Mtr | Ferro | ferro |  | 94.484 | 94.584 | 25.8 | 18.65 | 0.1 | 1 | 48.117 | Cum
| 0--3 Mtr | [9 empty] | 3575.8176 | Cum
2 | 3--6 Mtr | Ferro | Raft |  | 91.474 | 91.584 | 30.35 | 23.8 | 0.11 | 1 | 79.4563 | Cum |  | 0.11
| 3--6 Mtr | Ferro | Raft |  | 91.584 | 91.584 | 30.4 | 4.4 | 0 | 1 | 0 | Cum
| 3--6 Mtr | Ferro | Raft |  | 91.474 | 91.584 | 30.45 | 4.525 | 0.11 | 1 | 15.1565 | Cum
| 3--6 Mtr | [9 empty] | 94.6128 | Cum
| Soil Dressing | [12 empty] | 3670.4304
3 | Soil Dressing | Ferro | Raft |  | 91.466 |  | 30.35 | 23.8 |  | 1 | 722.33 | Sqm
| Soil Dressing | Ferro | Beam | [6 empty] | 2 | 2 | Sqm
| Soil Dressing | Ferro | Beam | [6 empty] | 2 | 2 | Sqm
| Soil Dressing | [9 empty] | 726.33 | Sqm
Sand Filling
4 | Total volume of furnace | Ferro | Well |  | 91.884 | 94.5 | 3.142 | 10.5625 | 2.616 | 1 | 86.8182 | Cum
| Deduction of walls(-) | Ferro | Wall |  | 91.884 | 94.175 | 6.5 | 0.6 | 2.291 | 2 | 17.8698 | Cum
Cum
| Sand Filling | [9 empty] | 104.688 | Cum
Backfilling
5 | Total Excavation | Ferro | [8 empty] | 3670.4304 | Cum
| Deducton of RCC | Ferro | [7 empty] | 1 | 293.0545 | Cum
| Deduction of PCC | Ferro | [8 empty] | 224.3179 | Cum
| Backfilling | [9 empty] | 3153.058 | Cum
Plain & Reinforced Cement concrete
| PCC | [10 empty] | 0
6 | 3--6 Mtr | Ferro | E3,E5 |  | 91.466 | 91.584 | 4.7 | 4.7 | 0.118 | 2 | 5.2132 | Cum
| 3--6 Mtr | Ferro | B3,B5 |  | 91.466 | 91.584 | 4.7 | 4.7 | 0.118 | 2 | 5.2132 | Cum
| 3--6 Mtr | Ferro | C6 |  | 91.466 | 91.584 | 2.95 | 2.95 | 0.118 | 7 | 7.1883 | Cum
| 3--6 Mtr | Ferro | B1,B6,C1,D1 |  | 91.466 | 91.584 | 2.95 | 2.95 | 0.118 | 4 | 4.1076 | Cum
| 3--6 Mtr | Ferro | D2 |  | 91.466 | 91.584 | 3.45 | 3.45 | 0.118 | 1 | 1.4045 | Cum |  |  |  | 4.86 | 55 | 267.3
| 3--6 Mtr | Ferro | E1,E2,E4,E6 |  | 91.466 | 91.584 | 3.7 | 3.7 | 0.118 | 4 | 6.4617 | Cum | [5 empty] | 286
| 3--6 Mtr | Ferro |  | F row | 91.466 | 91.584 | 2.7 | 2.7 | 0.118 | 6 | 5.1613 | Cum | [5 empty] | 553.3
| 3--6 Mtr | Ferro |  | G row | 91.466 | 91.584 | 1.7 | 1.7 | 0.118 | 6 | 2.0461 | Cum
| 3--6 Mtr | Ferro | SC |  | 91.466 | 91.584 | 1.2 | 1.2 | 0.118 | 6 | 1.0195 | Cum
| 3--6 Mtr | Ferro | Furnace |  |  |  | 3.142 | 16.81 | 0.15 | 1 | 7.9226 | Cum
| 3--6 Mtr | Ferro | Furnace | [8 empty] | Cum
| 3--6 Mtr | Ferro | Plinth Beam | A1-G1 | 94.43 | 94.58 | 40.525 | 0.3 | 0.15 | 2 | 3.6472 | Cum
| 3--6 Mtr | Ferro | Plinth Beam | A1-A6 | 94.43 | 94.58 | 21.5 | 0.3 | 0.15 | 5 | 4.8375 | Cum
| 3--6 Mtr | Ferro | Plinth Beam | A1-E1 | 94.43 | 94.58 | 15.3 | 0.3 | 0.15 | 3 | 2.0655 | Cum
| 3--6 Mtr | Ferro | Plinth Beam |  | 94.43 | 94.58 |  | 0.3 | 0.15 |  | 0.045 | Cum
| 3--6 Mtr | Ferro | Plinth Beam |  |  |  | 9.7571 |  | 1.638 |  | 8.1191 | Cum
| 3--6 Mtr | Ferro | Furnace |  | 91.375 | 94.5 | 3.142 | 10.5625 | 3.125 | 1 | 103.7105 | Cum
| 3--6 Mtr | [9 empty] | 168.1629 | Cum
7 | 0--3 Mtr | Ferro | E3,E5 |  | 91.584 | 91.616 | 4.7 | 4.7 | 0.032 | 2 | 1.4138 | Cum
| 0--3 Mtr | Ferro | B3,B5 |  | 91.584 | 91.616 | 4.7 | 4.7 | 0.032 | 2 | 1.4138 | Cum
| 0--3 Mtr | Ferro | C6 |  | 91.584 | 91.616 | 2.95 | 2.95 | 0.032 | 7 | 1.9494 | Cum
| 0--3 Mtr | Ferro | B1,B6,C1,D1 |  | 91.584 | 91.616 | 2.95 | 2.95 | 0.032 | 4 | 1.1139 | Cum
| 0--3 Mtr | Ferro | D2 |  | 91.584 | 91.616 | 3.45 | 3.45 | 0.032 | 1 | 0.38088 | Cum
| 0--3 Mtr | Ferro | E1,E2,E4,E6 |  | 91.584 | 91.616 | 3.7 | 3.7 | 0.032 | 4 | 1.7523 | Cum
| 0--3 Mtr | Ferro |  | F row | 91.584 | 91.616 | 2.7 | 2.7 | 0.032 | 6 | 1.3997 | Cum
| 0--3 Mtr | Ferro |  | G row | 91.584 | 91.616 | 1.7 | 1.7 | 0.032 | 6 | 0.55488 | Cum
| 0--3 Mtr | Ferro | SC |  | 91.584 | 91.616 | 1.2 | 1.2 | 0.032 | 6 | 0.27648 | Cum
| 0--3 Mtr | Ferro |  |  | 94.4 | 94.5 | 25.5 | 18 | 0.1 | 1 | 45.9 | Cum
| 0--3 Mtr | [9 empty] | 56.155 | Cum
RCC
8 | 0--3 Mtr | Ferro | Footing | E3,E5 | 91.616 | 92.516 | 4.5 | 4.5 | 0.9 | 2 | 36.45 | Cum
| 0--3 Mtr | Ferro | Footing | B3,B5 | 91.584 | 92.484 | 4.5 | 4.5 | 0.9 | 2 | 36.45 | Cum
| 0--3 Mtr | Ferro | Footing | C6 | 91.584 | 92.184 | 2.75 | 2.75 | 0.6 | 7 | 31.7625 | Cum
| 0--3 Mtr | Ferro | Footing | B1,B6,C1,D1 | 91.584 | 92.184 | 2.75 | 2.75 | 0.6 | 4 | 18.15 | Cum
| 0--3 Mtr | Ferro | Footing | D2 | 91.584 | 92.334 | 3.25 | 3.25 | 0.75 | 1 | 7.9219 | Cum
| 0--3 Mtr | Ferro | Footing | E1,E2,E4,E6 | 91.584 | 92.284 | 3.5 | 3.5 | 0.7 | 4 | 34.3 | Cum
| 0--3 Mtr | Ferro | G Row |  | 91.584 | 92.084 | 2.5 | 2.5 | 0.5 | 6 | 18.75 | Cum
| 0--3 Mtr | Ferro | F row |  | 91.584 | 92.034 | 1.5 | 1.5 | 0.45 | 6 | 6.075 | Cum
| 0--3 Mtr | Ferro | Footing | SC | 91.584 | 91.884 | 1 | 1 | 0.3 | 8 | 2.4 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.516 | 95.034 | 1.15 | 1.525 | 2.518 | 2 | 8.8319 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.484 | 95.034 | 0.95 | 1.2 | 2.55 | 2 | 5.814 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 | 0.75 | 0.9 | 2.85 | 7 | 13.4663 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 | 0.75 | 0.9 | 2.85 | 4 | 7.695 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.334 | 95.034 | 0.9 | 1.2 | 2.7 | 1 | 2.916 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.284 | 95.034 | 0.9 | 1.42 | 2.75 | 4 | 14.058 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.084 | 95.034 | 0.8 | 1.25 | 2.95 | 6 | 17.7 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 92.034 | 95.034 | 0.65 | 0.8 | 3 | 6 | 9.36 | Cum
| 0--3 Mtr | Ferro | Pedastal |  | 91.884 | 95.034 | 0.3 | 0.3 | 3.15 | 8 | 2.268 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | A1-G1 | 94.13 | 94.58 | 40.525 | 0.3 | 0.45 | 2 | 10.9417 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | A1-A6 | 94.13 | 94.58 | 21.5 | 0.3 | 0.45 | 5 | 14.5125 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | A1-E1 | 94.13 | 94.58 | 15.3 | 0.3 | 0.45 | 3 | 6.1965 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | D1-D3 | 95.13 | 95.58 | 7.4 | 0.3 | 0.45 | 1 | 0.999 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | C1 C2 | 96.13 | 96.58 | 3.7 | 0.3 | 0.45 | 1 | 0.4995 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | D5-D6 | 97.13 | 97.58 | 4.7 | 0.3 | 0.45 | 1 | 0.6345 | Cum
| 0--3 Mtr | Ferro | Plinth Beam | A4 B4 | 98.13 | 98.58 | 3.7 | 0.3 | 0.45 | 1 | 0.4995 | Cum
| 0--3 Mtr | Ferro | Furnace | Raft | 91.584 | 91.884 | 3.142 | 20.7025 | 0.3 | 1 | 19.5142 | Cum
| 0--3 Mtr | Ferro | Furnace | Wall Circle | 91.884 | 94.8 | 3.142 | 14.8225 | 2.916 | 1 | 135.8048 | Cum
| 0--3 Mtr | Ferro | Furnace | Wall Circle | 91.884 | 94.8 | 3.142 | 10.5625 | 2.916 | 1 | 96.7744 | Cum
| 0--3 Mtr | Ferro | Furnace | [7 empty] | 39.0304 | Cum
| 0--3 Mtr | Ferro | Furnace | Wall | 91.884 | 94.8 | 6.5 | 0.6 | 2.916 | 2 | 22.7448 | Cum
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 1.212 | 0.3 | 1 | 2 | 0.7272 | Cum
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 4.665 | 0.3 | 1 | 2 | 2.799 | Cum
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 6.174 | 0.3 | 1 | 2 | 3.7044 | Cum
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 6.954 | 0.3 | 1 | 2 | 4.1724 | Cum
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 7.244 | 0.3 | 1 | 1 | 2.1732 | Cum
| 0--3 Mtr | Ferro |  |  | 94.5 | 94.65 | 25.5 | 18 | 0.15 | 1 | 68.85 | Cum
| 0--3 Mtr | [9 empty] | 472.3674 | Cum | 324.8259 |  | 147.5415
| 3--6 Mtr | Ferro | Slab 5.35 Mtr |  | 5.35 | 5.5 | 25.5 | 18 | 0.15 |  | 68.85 | Cum | Furnace Not Deducted
| 3--6 Mtr | [9 empty] | 68.85 | Cum
| 9--12 Mtr | Ferro | Slab 10.35 Mtr |  | 10.2 | 10.35 | 25.5 | 18 | 0.15 |  | 68.85 | Cum | Furnace Not Deducted
| 9--12 Mtr | [9 empty] | 68.85 | Cum
| 15--18 Mtr | Ferro | Slab 16.85 Mtr |  | 16.7 | 16.85 | 25.5 | 18 | 0.15 |  | 68.85 | Cum | Furnace Not Deducted
| 15--18 Mtr | [9 empty] | 68.85 | Cum
Formwork & Shuttering
Shuttering
9 | 0--3 Mtr | Ferro | Footing | E3,E5 | 91.616 | 92.516 | 4.5 |  | 0.9 | 4 | 16.2 | Sqm
| 0--3 Mtr | Ferro | Footing | B3,B5 | 91.584 | 92.484 | 4.5 |  | 0.9 | 4 | 16.2 | Sqm
| 0--3 Mtr | Ferro | Footing | C6 | 91.584 | 92.184 | 2.75 |  | 0.6 | 14 | 23.1 | Sqm
| 0--3 Mtr | Ferro | Footing | B1,B6,C1,D1 | 91.584 | 92.184 | 2.75 |  | 0.6 | 8 | 13.2 | Sqm
| 0--3 Mtr | Ferro | Footing | D2 | 91.584 | 92.334 | 3.25 |  | 0.75 | 2 | 4.875 | Sqm
| 0--3 Mtr | Ferro | Footing | E1,E2,E4,E6 | 91.584 | 92.284 | 3.5 |  | 0.7 | 8 | 19.6 | Sqm
| 0--3 Mtr | Ferro | G Row |  | 91.584 | 92.084 | 2.5 |  | 0.5 | 12 | 15 | Sqm
| 0--3 Mtr | Ferro | F row |  | 91.584 | 92.034 | 1.5 |  | 0.45 | 12 | 8.1 | Sqm
| 0--3 Mtr | Ferro | Footing | SC | 91.584 | 91.884 | 1 |  | 0.3 | 16 | 4.8 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.516 | 95.034 | 1.15 |  | 2.518 | 4 | 11.5828 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.484 | 95.034 | 0.95 |  | 2.55 | 4 | 9.69 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 | 0.75 |  | 2.85 | 14 | 29.925 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 | 0.75 |  | 2.85 | 8 | 17.1 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.334 | 95.034 | 0.9 |  | 2.7 | 2 | 4.86 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.284 | 95.034 | 0.9 |  | 2.75 | 8 | 19.8 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.084 | 95.034 | 0.8 |  | 2.95 | 12 | 28.32 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.034 | 95.034 | 0.65 |  | 3 | 12 | 23.4 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 91.884 | 95.034 | 0.3 |  | 3.15 | 16 | 15.12 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-G1 | 94.13 | 94.58 | 40.525 |  | 0.45 | 4 | 72.945 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-A6 | 94.13 | 94.58 | 21.5 |  | 0.45 | 10 | 96.75 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-E1 | 94.13 | 94.58 | 15.3 |  | 0.45 | 6 | 41.31 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | D1-D3 | 95.13 | 95.58 | 7.4 |  | 0.45 | 2 | 6.66 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | C1 C2 | 96.13 | 96.58 | 3.7 |  | 0.45 | 2 | 3.33 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | D5-D6 | 97.13 | 97.58 | 4.7 |  | 0.45 | 2 | 4.23 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A4 B4 | 98.13 | 98.58 | 3.7 |  | 0.45 | 2 | 3.33 | Sqm
| 0--3 Mtr | Ferro | Furnace | Wall | 91.884 | 94.8 | 6.5 |  | 2.916 | 4 | 75.816 | Sqm
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 1.212 |  | 1 | 4 | 4.848 | Sqm
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 4.665 |  | 1 | 4 | 18.66 | Sqm
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 6.174 |  | 1 | 4 | 24.696 | Sqm
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 6.954 |  | 1 | 4 | 27.816 | Sqm
| 0--3 Mtr | Ferro | Furnace | Beam EGL | 94.5 | 95.5 | 7.244 |  | 1 | 2 | 14.488 | Sqm
| 0--3 Mtr | Ferro | Footing | E3,E5 | 91.616 | 92.516 |  | 4.5 | 0.9 | 4 | 16.2 | Sqm
| 0--3 Mtr | Ferro | Footing | B3,B5 | 91.584 | 92.484 |  | 4.5 | 0.9 | 4 | 16.2 | Sqm
| 0--3 Mtr | Ferro | Footing | C6 | 91.584 | 92.184 |  | 2.75 | 0.6 | 14 | 23.1 | Sqm
| 0--3 Mtr | Ferro | Footing | B1,B6,C1,D1 | 91.584 | 92.184 |  | 2.75 | 0.6 | 8 | 13.2 | Sqm
| 0--3 Mtr | Ferro | Footing | D2 | 91.584 | 92.334 |  | 3.25 | 0.75 | 2 | 4.875 | Sqm
| 0--3 Mtr | Ferro | Footing | E1,E2,E4,E6 | 91.584 | 92.284 |  | 3.5 | 0.7 | 8 | 19.6 | Sqm
| 0--3 Mtr | Ferro | G Row |  | 91.584 | 92.084 |  | 2.5 | 0.5 | 12 | 15 | Sqm
| 0--3 Mtr | Ferro | F row |  | 91.584 | 92.034 |  | 1.5 | 0.45 | 12 | 8.1 | Sqm
| 0--3 Mtr | Ferro | Footing | SC | 91.584 | 91.884 |  | 1 | 0.3 | 16 | 4.8 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.516 | 95.034 |  | 1.525 | 2.518 | 4 | 15.3598 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.484 | 95.034 |  | 1.2 | 2.55 | 4 | 12.24 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 |  | 0.9 | 2.85 | 14 | 35.91 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.184 | 95.034 |  | 0.9 | 2.85 | 8 | 20.52 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.334 | 95.034 |  | 1.2 | 2.7 | 2 | 6.48 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.284 | 95.034 |  | 1.42 | 2.75 | 8 | 31.24 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.084 | 95.034 |  | 1.25 | 2.95 | 12 | 44.25 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 92.034 | 95.034 |  | 0.8 | 3 | 12 | 28.8 | Sqm
| 0--3 Mtr | Ferro | Pedastal |  | 91.884 | 95.034 |  | 0.3 | 3.15 | 16 | 15.12 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-G1 | 94.58 | 94.58 | 40.525 | 0.3 |  | 2 | 24.315 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-A6 | 94.58 | 94.58 | 21.5 | 0.3 |  | 5 | 32.25 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A1-E1 | 94.58 | 94.58 | 15.3 | 0.3 |  | 3 | 13.77 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | D1-D3 | 95.58 | 95.58 | 7.4 | 0.3 |  | 1 | 2.22 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | C1 C2 | 96.58 | 96.58 | 3.7 | 0.3 |  | 1 | 1.11 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | D5-D6 | 97.58 | 97.58 | 4.7 | 0.3 |  | 1 | 1.41 | Sqm
| 0--3 Mtr | Ferro | Plinth Beam | A4 B4 | 98.58 | 98.58 | 3.7 | 0.3 |  | 1 | 1.11 | Sqm
| 0--3 Mtr | Ferro | Furnace | Raft | 91.584 | 91.884 | 24.1934 |  | 0.3 | 1 | 7.258 | Sqm
| 0--3 Mtr | Ferro | Furnace | Wall Circle | 91.884 | 94.8 | 24.1934 |  | 2.916 | 1 | 70.548 | Sqm
| 0--3 Mtr | Ferro | Furnace | Wall Circle | 91.884 | 94.8 | 20.423 |  | 2.916 | 1 | 59.5535 | Sqm
| 0--3 Mtr | [9 empty] | 1220.291 | Sqm
| 3--6 Mtr | Ferro | Slab 5.35 Mtr |  | 5.35 | 5.35 | 25.5 | 18 |  | 1 | 459 | Sqm | Furnace Not Deducted
| 3--6 Mtr | Ferro | Slab 5.35 Mtr |  | 5.35 | 5.5 |  | 18 | 0.15 | 2 | 5.4 | Sqm
| 3--6 Mtr | Ferro | Slab 5.35 Mtr |  | 5.35 | 5.5 | 25.5 |  | 0.15 | 2 | 7.65 | Sqm
| 3--6 Mtr | [9 empty] | 472.05 | Sqm
| 9--12 Mtr | Ferro | Slab 10.35 Mtr |  | 10.35 | 10.35 | 25.5 | 18 |  | 1 | 459 | Cum | Furnace Not Deducted
| 9--12 Mtr | Ferro | Slab 10.35 Mtr |  | 10.2 | 10.35 | 25.5 |  | 0.15 | 2 | 7.65 | Cum
| 9--12 Mtr | Ferro | Slab 10.35 Mtr |  | 10.2 | 10.35 |  | 18 | 0.15 | 2 | 5.4 | Cum
| 9--12 Mtr | [9 empty] | 472.05 | Cum
| 15--18 Mtr | Ferro | Slab 16.85 Mtr |  | 16.85 | 16.85 | 25.5 | 18 |  | 1 | 459 | Cum | Furnace Not Deducted
| 15--18 Mtr | Ferro | Slab 16.85 Mtr |  | 16.7 | 16.85 | 25.5 |  | 0.15 | 2 | 7.65 | Cum
| 15--18 Mtr | Ferro | Slab 16.85 Mtr |  | 16.7 | 16.85 |  | 18 | 0.15 | 2 | 5.4 | Cum
| 15--18 Mtr | [9 empty] | 472.05 | Cum