## RA 1
To | [9 empty] | 2023-01-01
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [10 empty] | Bill No RA1
Work order No | [10 empty] | Structure name GI Mill
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Dressing & Compaction | 50 | m3 |  |  |  |  | 810.048 | 40502.4 | 810.048 | 40502.4
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  |  |  | 19.998 | 41995.8 | 19.998 | 41995.8
4 | PCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 | [5 empty] | 0 | 0 | 0
5 | PCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 | [5 empty] | 0 | 0 | 0
6 | Shuttering upto +/- 3meter from GL | 370 | m2 |  |  |  |  | 611 | 226070 | 611 | 226070
7 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL |  | m2 | [5 empty] | 0 | 0 | 0
8 | RCC upto +/- 3.00 meter from GL. | 2500 | m3 |  |  |  |  | 159.496 | 398740 | 159.496 | 398740
9 | RCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 | [5 empty] | 0 | 0 | 0
10 | RCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 | [5 empty] | 0 | 0 | 0
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | 6000 | MT |  |  |  |  | 11.12 | 66720 | 11.12 | 66720
12 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. |  | MT | [5 empty] | 0 | 0 | 0
13 | Reinforcement of steel upto +/- 6.0 to +/- 9.0 meter from ground level. |  | MT | [5 empty] | 0 | 0 | 0
14 | Brickwork | 2800 | m3 |  |  |  |  | 23.273 | 65164.4 | 23.273 | 65164.4
16 | Plaster | 120 | m2 |  |  |  |  | 96 | 11520 | 96 | 11520
| Total | [9 empty] | 850712.6

## RA 2
To | [9 empty] | 2023-03-01
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [10 empty] | Bill No RA2
Work order No | [10 empty] | Structure name GI Mill
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Dressing & Compaction | 50 | m3 |  |  | 810.048 | 40502.4 |  |  | 810.048 | 40502.4
1 | Dressing & Compaction (New Rate) | 60 | m3 |  |  |  |  | 1808.8 | 108528 | 1808.8 | 108528
2 | Backflling | 85 | m3 |  |  |  |  | 1808.8 | 153748 | 1808.8 | 153748
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  | 19.998 | 41995.8 | 25.29 | 53109 | 45.288 | 95104.8
4 | PCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3
5 | PCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3
6 | Shuttering upto +/- 3meter from GL | 370 | m2 |  |  | 611 | 226070 |  |  | 611 | 226070
6 | Shuttering upto +/- 3meter from GL (New Rate) | 400 | m2 |  |  |  |  | 356.59 | 142636 | 356.59 | 142636
7 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL |  | m2
8 | RCC upto +/- 3.00 meter from GL. | 2500 | m3 |  |  | 159.496 | 398740 |  | 0 | 159.496 | 398740
8 | RCC upto +/- 3.00 meter from GL. (New Rate) | 2600 | m3 |  |  |  |  | 80.3966 | 209031.16 | 80.3966 | 209031.16
9 | RCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3
10 | RCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 6000 | MT |  |  | 11.12 | 66720 |  |  | 11.12 | 66720
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 7000 | MT |  |  |  |  | 8.2 | 57399.9993 | 8.2 | 57399.9993
12 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. |  | MT
13 | Reinforcement of steel upto +/- 6.0 to +/- 9.0 meter from ground level. |  | MT
14 | Brickwork | 2800 | m3 |  |  | 23.273 | 65164.4 |  |  | 23.273 | 65164.4
14 | Brickwork (New Rate) | 3100 | m3 |  |  |  |  | 0.57979 | 1797.349 | 0.57979 | 1797.349
15 | Plaster | 120 | m2 |  |  | 96 | 11520 |  |  | 96 | 11520
16 | MS Foundation Bolt Fixing | 13000 | MT |  |  |  |  | 0.7671 | 9972.3 | 0.7671 | 9972.3
| Total | [5 empty] | 850712.6 |  | 736221.8083 |  | 1586934.4083

## RA 3
To | [9 empty] | 2023-04-01
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [10 empty] | Bill No RA 3
Work order No | [10 empty] | Structure name GI Mill
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Dressing & Compaction | 50 | m3 |  |  | 810.048 | 40502.4 |  | 0 | 810.048 | 40502.4
1 | Dressing & Compaction (New Rate) | 60 | m3 |  |  | 1808.8 | 108528 |  | 0 | 1808.8 | 108528
2 | Backflling | 80 | m3 |  |  | 1808.8 | 144704 |  | 0 | 1808.8 | 144704
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  | 45.288 | 95104.8 |  | 0 | 45.288 | 95104.8
4 | PCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 |  |  |  | 0 |  | 0 | 0 | 0
5 | PCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 |  |  |  | 0 |  | 0 | 0 | 0
6 | Shuttering upto +/- 3meter from GL | 370 | m2 |  |  | 611 | 226070 |  | 0 | 611 | 226070
6 | Shuttering upto +/- 3meter from GL (New Rate) | 400 | m2 |  |  | 356.59 | 142636 | 455.95 | 182380 | 812.54 | 325016
7 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL |  | m2 |  |  |  | 0 |  | 0 | 0 | 0
8 | RCC upto +/- 3.00 meter from GL. | 2500 | m3 |  |  | 159.496 | 398740 |  | 0 | 159.496 | 398740
8 | RCC upto +/- 3.00 meter from GL. (New Rate) | 2600 | m3 |  |  | 80.3966 | 209031.16 | 41.441 | 107746.6 | 121.8376 | 316777.76
9 | RCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 |  |  |  | 0 |  | 0 | 0 | 0
10 | RCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 |  |  |  | 0 |  | 0 | 0 | 0
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 6000 | MT |  |  | 11.12 | 66720 |  | 0 | 11.12 | 66720
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 7000 | MT |  |  | 8.2 | 57399.9993 | 5.199 | 36393 | 13.399 | 93792.9993
12 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. |  | MT |  |  |  | 0 |  | 0 | 0 | 0
13 | Reinforcement of steel upto +/- 6.0 to +/- 9.0 meter from ground level. |  | MT |  |  |  | 0 |  | 0 | 0 | 0
14 | Brickwork | 2800 | m3 |  |  | 23.273 | 65164.4 |  | 0 | 23.273 | 65164.4
14 | Brickwork (New Rate) | 3100 | m3 |  |  | 0.57979 | 1797.349 |  | 0 | 0.57979 | 1797.349
15 | Plaster | 120 | m2 |  |  | 96 | 11520 |  | 0 | 96 | 11520
16 | MS Foundation Bolt Fixing | 13000 | MT |  |  | 0.7671 | 9972.3 | 0.896 | 11648 | 1.6631 | 21620.3
| Total | [5 empty] | 1577890.4083 |  | 338167.6 |  | 1916058.0083

## RA 4
To | [9 empty] | Month - May 2023
Nakoda Pipes Pvt Ltd | [9 empty] | AG Infratech
Tilda, Chattisgarh | [10 empty] | Bill No RA 4
Work order No | [10 empty] | Structure name GI Mill
Sl No | Description | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | Dressing & Compaction | 50 | m3 |  |  | 810.048 | 40502.4 |  | 0 | 810.048 | 40502.4
1 | Dressing & Compaction (New Rate) | 60 | m3 |  |  | 1808.8 | 108528 | 79.56 | 4773.6 | 1888.36 | 113301.6 | #REF!
2 | Backflling | 85 | m3 |  |  | 1808.8 | 153748 | 79.56 | 6762.6 | 1888.36 | 160510.6
3 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | m3 |  |  | 45.288 | 95104.8 | 14.4 | 30240 | 59.688 | 125344.8
4 | PCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
5 | PCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
6 | Shuttering upto +/- 3meter from GL | 370 | m2 |  |  | 611 | 226070 |  | 0 | 611 | 226070
6 | Shuttering upto +/- 3meter from GL (New Rate) | 400 | m2 |  |  | 812.54 | 325016 | 27.01 | 10804 | 839.55 | 335820
7 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL |  | m2 |  |  | 0 | 0 |  | 0 | 0 | 0
8 | RCC upto +/- 3.00 meter from GL. | 2500 | m3 |  |  | 159.496 | 398740 |  | 0 | 159.496 | 398740
8 | RCC upto +/- 3.00 meter from GL. (New Rate) | 2600 | m3 |  |  | 121.8376 | 316777.76 | 36.77 | 95602 | 158.6076 | 412379.76
9 | RCC upto +/- 3.00 to +/- 6.00 meter from GL |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
10 | RCC upto +/- 6.00 to +/- 9.00 meter from GL |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 6000 | MT |  |  | 11.12 | 66720 |  | 0 | 11.12 | 66720
11 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 7000 | MT |  |  | 13.399 | 93792.9993 | 1.66 | 11620 | 15.059 | 105412.9993
12 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. |  | MT |  |  | 0 | 0 |  | 0 | 0 | 0
13 | Reinforcement of steel upto +/- 6.0 to +/- 9.0 meter from ground level. |  | MT |  |  | 0 | 0 |  | 0 | 0 | 0
14 | Brickwork | 2800 | m3 |  |  | 23.273 | 65164.4 |  | 0 | 23.273 | 65164.4
15 | Brickwork (New Rate) | 3100 | m3 |  |  | 0.57979 | 1797.349 | 8.38 | 25978 | 8.9598 | 27775.349
16 | Plaster | 120 | m2 |  |  | 96 | 11520 |  | 0 | 96 | 11520
17 | Plaster (New Rate) | 160 | m2 |  |  | 96 | 15360 | 727.98 | 116476.8 | 823.98 | 131836.8
18 | MS Foundation Bolt Fixing | 13000 | MT |  |  | 1.6631 | 21620.3 |  | 0 | 1.6631 | 21620.3
19 | Net Cement Finishig | 185 | Sqm |  |  |  |  | 716.73 | 132595.05
| Total | [5 empty] | 1940462.0083 |  | 434852.05 |  | 2242719.0083

## RA 5
To | [12 empty] | Month - August 2023
Nakoda Pipes Pvt Ltd | [12 empty] | AG Infratech
Tilda, Chattisgarh | [12 empty] | Bill No RA 5
Work order No | [12 empty] | Structure name GI Mill
Sl No | Item No | Description | Rate |  | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
|  |  | Old | New |  | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 2(a) | Dressing & Compaction | 50 |  | m3 |  |  | 810.048 | 40502.4 |  | 0 | 810.048 | 40502.4
2 | 2(a) | Dressing & Compaction (New Rate) | 60 |  | m3 |  |  | 1888.36 | 113301.6 |  | 0 | 1888.36 | 113301.6
3 | 52 | Dressing & Levelling |  | 25 | m2 |  |  |  |  | 947.752 | 23693.8
4 | 2 | Backflling | 85 |  | m3 |  |  | 1888.36 | 160510.6 |  | 0 | 1888.36 | 160510.6
Plain & Reinforced Cement concrete
5 | 6 | PCC upto 0.00 to +/- 3.00 meter from GL | 2100 | 2300 | m3 |  |  | 59.688 | 125344.8 | 93.3677 | 214745.6801 | 153.0557 | 321416.9427
6 |  | PCC upto +/- 3.00 to +/- 6.00 meter from GL |  |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
7 |  | PCC upto +/- 6.00 to +/- 9.00 meter from GL |  |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
8 | 21 | Shuttering upto +/- 3meter from GL | 370 |  | m2 |  |  | 611 | 226070 |  | 0 | 611 | 226070
9 | 24 | Shuttering upto +/- 3meter from GL (New Rate) | 400 | 400 | m2 |  |  | 839.55 | 335820 | 51.36 | 20544 | 890.91 | 356364
10 | 24 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL |  |  | m2 |  |  | 0 | 0 |  | 0 | 0 | 0
11 | 7 | RCC upto +/- 3.00 meter from GL. | 2500 |  | m3 |  |  | 159.496 | 398740 |  | 0 | 159.496 | 398740
12 |  | RCC upto +/- 3.00 meter from GL. (New Rate) | 2600 | 2750 | m3 |  |  | 158.6076 | 412379.76 | 191.4743 | 526554.3459 | 350.0819 | 910212.9598
13 | 15 | RCC upto +/- 3.00 to +/- 6.00 meter from GL |  |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
14 | 15 | RCC upto +/- 6.00 to +/- 9.00 meter from GL |  |  | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
Steel Reinforcement
15 | 16 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 6000 |  | MT |  |  | 11.12 | 66720 |  | 0 | 11.12 | 66720
16 |  | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. (New Rate) | 7000 | 8500 | MT |  |  | 15.059 | 105412.9993 | 7.4069 | 62958.5338 | 22.4659 | 157261.2036
17 | 19 | Reinforcement of steel upto +/- 3.0 to +/- 6.0 meter from ground level. |  |  | MT |  |  | 0 | 0 |  | 0 | 0 | 0
18 | 19 | Reinforcement of steel upto +/- 6.0 to +/- 9.0 meter from ground level. |  |  | MT |  |  | 0 | 0 |  | 0 | 0 | 0
Mason Works
19 |  | Brickwork | 2800 |  | m3 |  |  | 23.273 | 65164.4 |  | 0 | 23.273 | 65164.4
20 | 25 | Brickwork | 3100 | 3300 | m3 |  |  | 8.9598 | 27775.349 | 30.8017 | 101645.5836 | 39.7615 | 123260.5942
21 |  | Plaster | 120 |  | m2 |  |  | 96 | 11520 |  | 0 | 96 | 11520
22 | 28 | Plaster (New Rate) | 160 |  | m2 |  |  | 823.98 | 131836.8 |  | 0 | 823.98 | 131836.8
23 | 20 | MS Foundation Bolt Fixing | 13000 |  | MT |  |  | 1.6631 | 21620.3 |  | 0 | 1.6631 | 21620.3
24 |  | Net Cement Finishig | 185 |  | Sqm | [5 empty] | 0 | 0 | 0
25 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | 130 |  | Sqm |  |  |  |  | 859.983 | 111797.79 | 859.983 | 111797.79
|  | Total | [6 empty] | 2242719.0083 |  | 1061939.7334 |  | 3216299.5903

## RA 5 Measurement
SHREE NAKODA PIPE IMPEX PVT LTD | [8 empty] | Bill Month:- August 2023
Bill Name:- GI PLANT | [8 empty] | Type of work:- Civl works
Bill No:-RA 5 | [8 empty] | Vendor:- AG INFRATECH
Sl no | DESCRIPTION | Struc. | Grid | Nos | L | B | H | QTY | Unit
1.Dressing & levelling
1 |  | RCC flooring below Pcc work(Part-A) |  | 1 | 23.85 | 28.4 |  | 677.34 | m³
2 |  | RCC flooring below Pcc work(Part-B) |  | 1 | 23.85 | 9 |  | 214.65 | m³
3 |  | RCC flooring below Pcc work(Part-C`) | N/A | 1 | 12.37 | 5.6 |  | 69.272 | m²
4 |  | RCC flooring below Pcc work(Part-D) | N/A | 1 | 6.7 | 9.23 |  | 61.841 | m²
|  | Deduction | N/A | -1 | 11 | 14 |  | -154 | m²
|  | Deduction | N/A | -1 | 7.6 | 1.2 |  | -9.12 | m²
5 |  | Cyclone brick foundation | N/A | 1 | 4.9 | 5.05 |  | 24.745 | m²
6 |  | Near Acid tank Scrabber circle foundation | N/A | 2 | 3.14 | 1.525 |  | 9.577 | m²
7 |  | Near Acid tank Scrabber Rectangular foundation | N/A | 1 | 4.7 | 2.7 |  | 12.69 | m²
8 |  | Near Zink tank Scrabber circle foundation | N/A | 2 | 3.14 | 1.525 |  | 9.577 | m²
9 |  | Near Zink tank Scrabber Rectangular foundation | N/A | 1 | 4.5 | 2.6 |  | 11.7 | m²
10 |  | Near Zink tank Blower Rectangular foundation | N/A | 2 | 1.6 | 1.8 |  | 5.76 | m²
11 |  | Chimney Foundation | N/A | 1 | 3.15 | 3.2 |  | 10.08 | m²
12 |  | Plinth Beam Up to Drain | N/A | 1 | 1.05 | 1.2 |  | 1.26 | m²
13 |  | Brick Fodn.near zink Drain wall | N/A | 1 | 1.7 | 1.4 |  | 2.38 | m²
| Total Qty.For Dressing Work | [6 empty] | 947.752 | m²
2. Pcc Work for GI Plant
14 |  | RCC flooring below Pcc work(Part-A) |  | 1 | 23.85 | 28.2 | 0.1 | 67.257 | m³
15 |  | RCC flooring below Pcc work(Part-B) |  | 1 | 23.85 | 8.8 | 0.1 | 20.988 | m³
16 |  | RCC flooring below Pcc work(Part-C) |  | 1 | 12.37 | 5.4 | 0.1 | 6.6798 | m³
17 |  | RCC flooring below Pcc work(Part-D) |  | 1 | 6.7 | 9.03 | 0.1 | 6.0501 | m³
18 |  | Deduction |  | -1 | 10.8 | 13.8 | 0.1 | -14.904 | m³
19 |  | Deduction |  | -1 | 7.4 | 1 | 0.1 | -0.74 | m³
20 |  | Cyclone brick foundation |  | 1 | 4.7 | 4.85 | 0.1 | 2.2795 | m³
21 |  | Near Acid tank Scrabber circle foundation |  | 3.14 | 2.94 | 1.325 | 0.1 | 1.2232 | m³
22 |  | Near Acid tank Scrabber Rectangular foundation |  | 1 | 4.5 | 2.5 | 0.1 | 1.125 | m³
23 |  | Near Zink tank Scrabber circle foundation |  | 2 | 2.94 | 1.325 | 0.1 | 0.7791 | m³
24 |  | Near Zink tank Scrabber Rectangular foundation |  | 1 | 4.3 | 2.4 | 0.1 | 1.032 | m³
25 |  | Near Zink tank Blower Rectangular foundation |  | 2 | 1.4 | 1.6 | 0.1 | 0.448 | m³
26 |  | Chimney Foundation |  | 1 | 2.95 | 3 | 0.1 | 0.885 | m³
27 |  | Plinth Beam Up to Drain |  | 1 | 0.85 | 1 | 0.1 | 0.085 | m³
28 |  | Brick Fodn.near zink Drain wall |  | 1 | 1.5 | 1.2 | 0.1 | 0.18 | m³
| Total Qty. for Pcc work | [6 empty] | 93.3677 | Cum
3. RCC Work for GI Plant
29 |  | RCC flooring below Pcc work(Part-A) |  | 1 | 23.85 | 28.4 | 0.15 | 101.601
30 |  | RCC flooring below Pcc work(Part-B) |  | 1 | 23.85 | 9 | 0.15 | 32.1975
31 |  | RCC flooring below Pcc work(Part-C) |  | 1 | 12.37 | 5.6 | 0.15 | 10.3908
32 |  | RCC flooring below Pcc work(Part-D) |  | 1 | 6.7 | 9.23 | 0.15 | 9.2761
|  | Deduction |  | -1 | 11 | 14 | 0.15 | -23.1
|  | Deduction |  | -1 | 7.6 | 1.2 | 0.15 | -1.368
33 |  | Cyclone foundation Rcc Filling-A |  | 6 | 0.44 | 0.44 | 1.3 | 1.5101
34 |  | Cyclone foundation Rcc Filling-B |  | 1 | 1.19 | 1.44 | 1.3 | 2.2277
35 |  | Cyclone foundation Rcc Filling-C |  | 1 | 1.3 | 0.64 | 1.3 | 1.0816
36 |  | Cyclone foundation Rcc Filling-C |  | 1 | 1.2 | 0.44 | 1.3 | 0.6864
37 |  | Cyclone foundation Rcc Filling-D |  | 2 | 1.6 | 0.55 | 1.3 | 2.288
38 |  | Cyclone foundation Rcc Filling-D |  | 4 | 0.7 | 0.22 | 1.3 | 0.8008
39 |  | Near Acid tank Scrabber circle foundation |  | 3.14 | 1.199 |  | 1.8 | 6.7769
40 |  | Near Acid tank Scrabber Rectangular foundation |  | 2 | 1.805 | 1.84 | 1.8 | 11.9563
41 |  | Near Zink tank Scrabber circle foundation |  | 3.14 | 1.199 |  | 1.8 | 6.7769
42 |  | Near Zink tank Scrabber Rectangular foundation |  | 2 | 1.705 | 1.74 | 1.55 | 9.1968
43 |  | Near Zink tank Blower Rectangular foundation |  | 2 | 0.74 | 0.94 | 0.65 | 0.90428
44 |  | Chimney Foundation 1st Raft |  | 1 | 2.75 | 2.8 | 0.3 | 2.31
45 |  | Chimney Foundation 2nd Raft |  | 1 | 2.12 | 2.2 | 0.3 | 1.3992
46 |  | Wall Long side |  | 2 | 2.2 | 0.2 | 1.8 | 1.584
47 |  | short side |  | 2 | 2.15 | 0.2 | 1.8 | 1.548
48 |  | Connected Drain wall |  | 2 | 1.05 | 0.15 | 1.8 | 0.567
49 |  | Drain wall Middle Filling Work |  | 1 | 1.7 | 1.7 | 1.8 | 5.202
50 |  | (-) Deduction of chimney |  | 1 | 3.142 | 0.1225 | 1.8 | 0.69281
51 |  | Total Drain wall Middle Filling Work | [5 empty] | 4.5092
52 |  | Middle Drain m/C Foundation Pocket Filling |  | 1 | 2.8 | 1.6 | 1.2 | 5.376
53 |  | Brick Fodn.near zink Drain wall |  | 1 | 0.84 | 0.97 | 1.2 | 0.97776
| Total Qty.For RCC Work for GI Plant | [6 empty] | 191.4743 | Cum
4.Shuttering Work
PCC
|  | Cyclone brick foundation |  | 2 | 4.7 |  | 0.1 | 0.94
|  | Cyclone brick foundation |  | 2 | 4.85 |  | 0.1 | 0.97
|  | Near Acid tank Scrabber circle foundation |  | 2 | 1.425 |  | 0.1 | 0.285
|  | Near Acid tank Scrabber Rectangular foundation |  | 2 | 4.5 |  | 0.1 | 0.9
|  | Near Acid tank Scrabber Rectangular foundation |  | 2 | 2.5 |  | 0.1 | 0.5
|  | Near Zink tank Scrabber circle foundation |  | 2 | 1.425 |  | 0.1 | 0.285
|  | Near Zink tank Scrabber Rectangular foundation |  | 2 | 4.2 |  | 0.1 | 0.84
|  | Near Zink tank Scrabber Rectangular foundation |  | 2 | 2.4 |  | 0.1 | 0.48
|  | Near Zink tank Blower Rectangular foundation |  | 2 | 1.4 |  | 0.1 | 0.28
|  | Near Zink tank Blower Rectangular foundation |  | 2 | 1.6 |  | 0.1 | 0.32
|  | Chimney Foundation |  | 2 | 2.95 |  | 0.1 | 0.59
|  |  |  | 2 | 3 |  | 0.1 | 0.6
|  | Plinth Beam Up to Drain |  | 2 | 1.05 |  | 0.1 | 0.21
[7 empty] | 0.1 | 0.1
|  | Brick Fodn.near zink Drain wall |  | 2 | 1.5 |  | 0.1 | 0.3
|  |  |  | 2 | 1.3 |  | 0.1 | 0.26
|  | RCC | [5 empty] | 0
|  | Chimney Foundation 1st Raft |  | 2 | 2.75 |  | 0.3 | 1.65
|  |  |  | 2 | 2.8 |  | 0.3 | 1.68
|  | Chimney Foundation 2nd Raft |  | 2 | 2.15 |  | 0.3 | 1.29
|  |  |  | 2 | 2.2 |  | 0.3 | 1.32
|  | Wall Outer side(2.2+2.2+2.15+2.15=8.70) |  | 1 | 8.7 |  | 1.8 | 15.66
|  | Wall Inner side(1.8+1.8+1.75+1.75=7.10) |  | 1 | 7.1 |  | 1.8 | 12.78
|  | Connected Drain wall |  | 4 | 1 |  | 1.8 | 7.2
|  | Middle Drain m/C Foundation Pocket Filling |  | 1 | 1.6 |  | 1.2 | 1.92
| Total Qty. for Shuttring work | [6 empty] | 51.36 | Sqm
5. Brick Work for GI Plant
|  | Cyclone brick foundation- A Long wall |  | 12 | 0.9 | 0.23 | 1.3 | 3.2292
|  | Cyclone brick foundation- A short wall |  | 12 | 0.44 | 0.23 | 1.3 | 1.5787
|  | Middle wall |  | 4 | 0.7 | 0.23 | 1.3 | 0.8372
|  | Middle wall |  | 3 | 0.55 | 0.23 | 1.3 | 0.49335
|  | Cyclone brick foundation- B Long wall |  | 2 | 1.65 | 0.23 | 1.3 | 0.9867
|  | Cyclone brick foundation- B short wall |  | 2 | 1.44 | 0.23 | 1.3 | 0.86112
|  | Cyclone brick foundation- C Long wall |  | 1 | 2.2 | 0.23 | 1.3 | 0.6578
|  | Cyclone brick foundation- C Long wall |  | 1 | 0.9 | 0.23 | 1.3 | 0.2691
|  | Cyclone brick foundation- C short wall |  | 1 | 1.64 | 0.23 | 1.3 | 0.49036
|  | Cyclone brick foundation- C short wall |  | 1 | 1.2 | 0.23 | 1.3 | 0.3588
|  | Cyclone brick foundation- C short wall |  | 1 | 1.3 | 0.23 | 1.3 | 0.3887
|  | Cyclone brick foundation- C short wall |  | 1 | 1.1 | 0.23 | 1.3 | 0.3289
|  | Near Acid tank Scrabber circle foundation |  | 1 | 8.321 | 0.23 | 1.8 | 3.4449
|  | Near Acid tank Scrabber Rectangular foundation |  | 2 | 4.3 | 0.23 | 1.8 | 3.5604
|  | Near Acid tank Scrabber Rectangular foundation |  | 3 | 1.84 | 0.23 | 1.8 | 2.2853
|  | Near Zink tank Scrabber circle foundation |  | 1 | 8.321 | 0.23 | 1.8 | 3.4449
|  | Near Zink tank Scrabber Rectangular foundation |  | 2 | 4.1 | 0.23 | 1.55 | 2.9233
|  | Near Zink tank Scrabber Rectangular foundation |  | 3 | 1.74 | 0.23 | 1.55 | 1.8609
|  | Near Zink tank Blower Rectangular foundation |  | 4 | 0.74 | 0.23 | 0.64 | 0.43571
|  | Near Zink tank Blower Rectangular foundation |  | 4 | 0.94 | 0.23 | 0.65 | 0.56212
|  | Chimney Foundation internal Brick work |  | 1 | 2.198 | 0.23 | 1.8 | 0.90997
|  | Brick Fodn.near zink Drain wall |  | 2 | 0.97 | 0.23 | 1.2 | 0.53544
|  | Brick Fodn.near zink Drain wall |  | 1 | 1.3 | 0.23 | 1.2 | 0.3588
| Total Qty. for Brick work | [6 empty] | 30.8017 | Cum
6. Floater Finish Work for GI Plant
|  | RCC flooring below Pcc work(Part-A) |  | 1 | 23.85 | 28.4 |  | 677.34
|  | RCC flooring below Pcc work(Part-B) |  | 1 | 23.85 | 9 |  | 214.65
|  | RCC flooring below Pcc work(Part-C) |  | 1 | 12.37 | 5.6 |  | 69.272
|  | RCC flooring below Pcc work(Part-D) |  | 1 | 6.7 | 9.23 |  | 61.841
|  | Deduction |  | -1 | 11 | 14 |  | -154
|  | Deduction |  | -1 | 7.6 | 1.2 |  | -9.12
| Total Qty. for Floater Finish work work | [6 empty] | 859.983 | Sqm

## RA 5 BBS
BAR BENDING SCHEDULE (GI PLANT) RA-5 (AUG-2023)
S.No | Description | Dia in MM | No of member | No. of Bar | Cutting Length | DIA WISE LENGTH OF REINFORCEMENT IN METER
[6 empty] | 8MM | 10MM | 12MM | 16MM
1 | RCC FLOORING WORK PART -A (23.85X28.40)
| BOTTOM BAR-200 C/C | 10 | 1 | 144 | 23.85 |  | 3434.4
| OVERLAP | 10 | 1 | 144 | 0.5 |  | 72
| TOP BAR -200 C/C | 10 | 1 | 120 | 28.4 |  | 3408
| OVERLAP | 10 | 2 | 120 | 0.5 |  | 120
2 | RCC FLOORING WORK PART -B (23.85X9.0)
| BOTTOM BAR-200 C/C | 10 | 1 | 46 | 23.85 |  | 1097.1
| OVERLAP | 10 | 1 | 46 | 0.5 |  | 23
| TOP BAR -200 C/C | 10 | 1 | 120 | 9 |  | 1080
| OVERLAP | 10 | 1 | 120 | 0.5 |  | 60
3 | RCC FLOORING WORK PART -C (12.370X5.60)
| BOTTOM BAR-200 C/C | 10 | 1 | 29 | 12.37 |  | 358.73
| OVERLAP | 10 | 1 | 29 | 0.5 |  | 14.5
| TOP BAR -200 C/C | 10 | 1 | 62 | 5.6 |  | 347.2
4 | RCC FLOORING WORK PART -D (12.370X5.60)
| BOTTOM BAR-200 C/C | 10 | 1 | 47 | 6.7 |  | 314.9
| TOP BAR -200 C/C | 10 | 1 | 62 | 9.23 |  | 572.26
CHIMNEY FOUNDATION RAFT
| BOTTOM & TOP BAR-150 C/C | 12 | 2 | 19 | 2.95 |  |  | 112.1
| BOTTOM & TOP BAR -150 C/C | 12 | 2 | 19 | 3 |  |  | 114
| VERTICAL BAR-150 C/C-0.8 TIME | 12 | 8 | 15 | 2.6 |  |  | 312
| BINDER BAR-150 C/C-8TIME | 12 | 8 | 13 | 2.1 |  |  | 218.4
| CHAIR | 12 | 1 | 8 | 1.2 |  |  | 9.6
[5 empty] | RMT | 0 | 10902.09 | 766.1 | 0
[5 empty] | UNIT. W | 0.395 | 0.617 | 0.888 | 1.58
[6 empty] | 0 | 6726.5895 | 680.2968 | 0
[6 empty] | TOTAL.MT |  | 7406.8863
[8 empty] | 7.4069 | MT