## RA 1
Comparision Chart
Bill Name:- GI-2
Bill No RA 1
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity |  | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
2 | BackFilling | m3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 2
3 | Watering & Consolidation ( Dressing & Compaction) | m3 | 1084.36 | 810.048 | 810.048 | 50 | 54218 | 40502.4 | 40502.4 | 13715.6 | 13715.6 | RA 2
4 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 | 19.998 | 19.998 | 19.99 | 2100 | 41995.8 | 41995.8 | 41979 | 0 | 16.8 | RA 2
5 | Shuttering upto +/- 3meter from GL | m3 | 611 | 611 | 610.896 | 370 | 226070 | 226070 | 226031.52 | 0 | 38.48 | RA 2
6 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 2
7 | RCC upto +/- 3.00 meter from GL. | m3 | 159.496 | 159.496 | 161.7516 | 2500 | 398740 | 398740 | 404379 | 0 | -5639 | RA 2
8 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 2
9 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | m3 | 11.12 | 11.12 | 11.2 | 6000 | 66720 | 66720 | 67200 | 0 | -480 | RA 2
10 | Brick Work | m3 | 23.273 | 23.273 | 23.64 | 2800 | 65164.4 | 65164.4 | 66192 | 0 | -1027.6 | RA 2
11 | Plaster | m2 | 96 | 96 | 96 | 120 | 11520 | 11520 | 11520 | 0 | 0 | RA 2
12 | MS Foundation Bolt fixing | m2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 2
13 | Net Cement Finishng | m2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 2
[7 empty] | 864428.2 | 850712.6 | 857803.92 | 13715.6
Billng Department |  |  |  |  | Site Incharge | [6 empty] | H.O.D (Civil)
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd
Abhishek Acharya | [11 empty] | Mahesh Wandre

## RA 2
Comparision Chart
Bill Name:- GI-2
Bill No RA 2
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity |  | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
2 | BackFilling | m3 | 1808.8 | 1808.8 | 1808.8 | 85 | 153748 | 153748 | 153748 | 0 | 0 | RA 2
3 | Watering & Consolidation ( Dressing & Compaction) | m3 | 1808.8 | 1808.8 | 1808.8 | 60 | 108528 | 108528 | 108528 | 0 | 0 | RA 2 | Dressing & Compaction Written By AGI
4 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 | 25.29 | 25.29 | 25.3 | 2100 | 53109 | 53109 | 53130 | 0 | -21 | RA 2
5 | Shuttering upto +/- 3meter from GL | m3 | 356.59 | 356.59 | 355.39 | 400 | 142636 | 142636 | 142156 | 0 | 480 | RA 2
6 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 | 30.24 |  | 30.24 | 40 | 1209.6 | 0 | 1209.6 | 1209.6 | 0 | RA 2
7 | RCC upto +/- 3.00 meter from GL. | m3 | 80.4 | 80.3966 | 80.3966 | 2600 | 209040 | 209031.16 | 209031.16 | 8.84 | 8.84 | RA 2
8 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 | 6.05 |  | 6.05 | 260 | 1573 | 0 | 1573 | 1573 | 0 | RA 2
9 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | m3 | 8.2 | 8.2 | 8.2 | 7000 | 57400 | 57399.9993 | 57399.9993 | 0.0007 | 0.0007 | RA 2
10 | Brick Work | m3 | 0.59 | 0.57979 | 0.588 | 3100 | 1829 | 1797.349 | 1822.8 | 31.651 | 6.2 | RA 2
11 | Plaster | m2 |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | RA 2
| Plaster (From AGI) | m2 |  |  |  | 300 | 0 | 0 | 0 | 0 | 0 | RA 2
12 | MS Foundation Bolt fixing | m2 | 0.77 | 0.7671 | 0.768 | 13000 | 10010 | 9972.3 | 9984 | 37.7 | 26 | RA 2
13 | Net Cement Finishng | m2 |  |  |  | 185 | 0 | 0 | 0 | 0 | 0 | RA 2
[7 empty] | 739082.6 | 736221.8083 | 738582.5593 | 2860.7917

## RA 3
Comparision Chart
Bill Name:- GI-2
Bill No RA 3
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity |  | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | Dressing & Compaction | m3 |  |  |  | 60
2 | BackFilling | m3 |  |  |  | 85 | 0 | 0 | 0 | 0 | 0 | RA 3
3 | Watering & Consolidation | m3 |  |  |  | 60 | 0 | 0 | 0 | 0 | 0 | RA 3
4 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 |  |  |  | 2100 | 0 | 0 | 0 | 0 | 0 | RA 3
5 | Shuttering upto +/- 3meter from GL | m3 | 455.95 | 455.95 | 456 | 400 | 182380 | 182380 | 182400 | 0 | -20 | RA 3
6 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 | 35.28 |  | 35.28 | 40 | 1411.2 | 0 | 1411.2 | 1411.2 | 0 | RA 3
7 | RCC upto +/- 3.00 meter from GL. | m3 | 41.44 | 41.441 | 41.46 | 2600 | 107744 | 107746.6 | 107796 | -2.6 | -52 | RA 3
8 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 | 7.06 |  | 7.056 | 260 | 1835.6 | 0 | 1834.56 | 1835.6 | 1.04 | RA 3
9 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | m3 | 5.2 | 5.199 | 5.2 | 7000 | 36400 | 36393 | 36400 | 7 | 0 | RA 3
10 | Brick Work | m3 |  |  |  | 3100 | 0 | 0 | 0 | 0 | 0 | RA 3
11 | Plaster | m2 |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | RA 3
| Plaster (From AGI) | m2 |  |  |  | 300 | 0 | 0 | 0 | 0 | 0 | RA 3
12 | MS Foundation Bolt fixing | m2 | 0.896 | 0.896 | 0.9 | 13000 | 11648 | 11648 | 11700 | 0 | -52 | RA 3
13 | Net Cement Finishng | m2 |  |  |  | 185 | 0 | 0 | 0 | 0 | 0 | RA 3
[7 empty] | 341418.8 | 338167.6 | 341541.76 | 3251.2 | -122.96
Billng Department |  |  |  |  | Site Incharge | [6 empty] | H.O.D (Civil)
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd
Abhishek Acharya | [11 empty] | Mahesh Wandre

## RA 4
Comparision Chart
Bill Name:- GI-2
Bill No RA 4
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity |  | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | Dressing & Compaction | m3 |  |  |  | 50
2 | BackFilling | m3 | 79.56 | 79.56 | 79.57 | 85 | 6762.6 | 6762.6 | 6763.45 | 0 | -0.85 | RA 4
3 | Watering & Consolidation | m3 | 79.56 | 79.56 | 79.56 | 60 | 4773.6 | 4773.6 | 4773.6 | 0 | 0 | RA 4
4 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 | 14.4 | 14.4 | 14.41 | 2100 | 30240 | 30240 | 30261 | 0 | -21 | RA 4
5 | Shuttering upto +/- 3meter from GL | m3 | 27.01 | 27.01 | 27.01 | 400 | 10804 | 10804 | 10804 | 0 | 0 | RA 4
6 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 |  |  |  | 40 |  |  |  | 0 | 0 | RA 4
7 | RCC upto +/- 3.00 meter from GL. | m2 | 36.77 | 36.77 | 36.77 | 2600 | 95602 | 95602 | 95602 | 0 | 0 | RA 4
8 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m2 |  |  |  | 260 |  |  |  | 0 | 0 | RA 4
9 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | m3 | 1.66 | 1.66 | 1.66 | 7000 | 11620 | 11620 | 11620 | 0 | 0 | RA 4
10 | Brick Work | m3 | 8.38 | 8.38 | 8.38 | 3100 | 25978 | 25978 | 25978 | 0 | 0 | RA 4
11 | Plaster | m2 |  | 727.98 |  | 160 |  | 116476.8 |  | -116476.8 | 0 | RA 4
| Plaster (From AGI) | m2 | 727.98 |  | 727.97 | 300 | 218394 |  | 218391 | 218394 | 3 | RA 4
12 | MS Foundation Bolt fixing | m2 |  |  |  | 13000 |  |  |  | 0 | 0 | RA 4
13 | Net Cement Finishng | m2 | 716.73 | 716.73 | 716.7 | 185 | 132595.05 | 132595.05 | 132589.5 | 0 | 5.55 | RA 4
[7 empty] | 536769.25 | 434852.05 | 536782.55 | 101917.2 | -13.3
Billng Department |  |  |  |  | Site Incharge | [6 empty] | H.O.D (Civil)
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd
Abhishek Acharya | [11 empty] | Mahesh Wandre

## Sheet1
Comparision Chart
Bill Name:- GI-2 | [11 empty] | Month:- August 2023
Bill No RA 5
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity |  | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | Dressing & Levelling | m² | 947.75 | 947.752 |  | 25 | 23693.75 | 23693.8 |  | -0.05 | 23693.75 | RA 5
2 | BackFilling | m3 |  |  |  |  | 0 | 0 |  | 0 | 0 | RA 5
3 | Watering & Consolidation | m3 |  |  |  |  | 0 | 0 |  | 0 | 0 | RA 5
4 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 | 93.6 | 93.3677 |  | 2300 | 215280 | 214745.6801 |  | 534.3199 | 215280 | RA 5
5 | Shuttering upto +/- 3meter from GL | m3 | 51.64 | 51.36 |  | 400 | 20656 | 20544 |  | 112 | 20656 | RA 5
6 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 | [7 empty] | 0 | 0 | RA 5
7 | RCC upto +/- 3.00 meter from GL. | m2 | 191.48 | 191.4743 |  | 2750 | 526570 | 526554.3459 |  | 15.6541 | 526570 | RA 5
8 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m2 | [7 empty] | 0 | 0 | RA 5
9 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | m3 | 7.41 | 7.4069 |  | 8500 | 62985 | 62958.5338 |  | 26.4662 | 62985 | RA 5
10 | Brick Work | m3 | 30.8 | 30.8017 |  | 3300 | 101640 | 101645.5836 |  | -5.5836 | 101640 | RA 5
11 | Plaster | m2 |  |  |  | 160 |  | 0 |  | 0 | 0 | RA 5
12 | Plaster (From AGI) | m2 |  |  |  | 300 | 0 |  |  | 0 | 0 | RA 5
13 | MS Foundation Bolt fixing | m2 |  |  |  | 13000 |  |  |  | 0 | 0 | RA 5
14 | Floor Finishing | m2 | 859.98 | 859.983 |  | 130 | 111797.4 | 111797.79 |  | -0.39 | 111797.4 | RA 5
[7 empty] | 1062622.15 | 1061939.7334 |  | 682.4166
Billng Department |  |  |  |  | Site Incharge | [6 empty] | H.O.D (Civil)
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd
Abhishek Acharya | [11 empty] | Mahesh Wandre