## Abstracty
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Division: -Pipe Division
Block:- GI-2
Sl No | Item No | Description | Rate | UOM | Division | Upto Prev Bill |  | This Bill |  | Estimated Value
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
Excavation & Backfilling
1 |  | Excavation 0-3 Mtr |  | m3
2 |  | Excavation 3-6 Mtr |  | m3
3 |  | Excavation 6-9 Mtr |  | m3
4 |  | Watering & Consolidation | 80 | m2 | [5 empty] | 3289 | 263120
5 |  | Hard Rock breaking 0-3 |  | m3
6 |  | Hard Rock breaking 3-6 |  | m3
7 |  | Hard Rock breaking 6-9 |  | m3
8 |  | Sand Filling |  | m3
9 |  | Aggregate Filling |  | m3
10 |  | Rock Soling |  | m3
11 |  | Backfilling | 85 | m3 | [5 empty] | 1901.86 | 161658.1
Plain cement concrete
12 |  | PCC 0-3 Mtr | 2100 | m3 | [5 empty] | 308.42 | 647682
13 |  | PCC 3-6 Mtr |  | m3
14 |  | PCC 3-9 Mtr |  | m3
Reinforced cement concrete
15 |  | RCC 0-3 Mtr | 2600 | m3 | [5 empty] | 717 | 1864200
16 |  | RCC 3-6 Mtr | 2860 | m3 | [5 empty] | 13.22 | 37809.2
17 |  | RCC 6-9 Mtr |  | m3
18 |  | RCC 9-12 Mtr |  | m3
19 |  | RCC 12-15 Mtr |  | m3
Formwork & Shuttering
20 |  | 0--3 Mtr | 400 | m2 | [5 empty] | 1702 | 680800 | Cooling Tank, AFO tank, Chimney Foundation Tank Det6ails not specified till now. Quantity has not been calculated yet
21 |  | 3--6 Mtr | 440 | m2 | [5 empty] | 74 | 32560 | Cooling Tank, AFO tank, Chimney Foundation Tank Det6ails not specified till now. Quantity has not been calculated yet
22 |  | 6--9 Mtr |  | m2 | [7 empty] | Cooling Tank, AFO tank, Chimney Foundation Tank Det6ails not specified till now. Quantity has not been calculated yet
23 |  | 9--12 Mtr |  | MT | [7 empty] | Cooling Tank, AFO tank, Chimney Foundation Tank Det6ails not specified till now. Quantity has not been calculated yet
24 |  | 12--15 Mtr |  | MT | [7 empty] | Cooling Tank, AFO tank, Chimney Foundation Tank Det6ails not specified till now. Quantity has not been calculated yet
Reinforcement of TMT Bars
25 |  | 0--3 Mtr | 7000 | MT | [5 empty] | 47.34 | 331380
26 |  | 3--6 Mtr |  | MT
27 |  | 6--9 Mtr |  | MT
28 |  | 9--12 Mtr |  | MT
29 |  | 12--15 Mtr |  | MT
Fabrication & Fixing
30 |  | Fixing of MS Insert Plate |  | MT
31 |  | Facbrication & Fixing of MS Insert Plates |  | MT
32 |  | Fixing of Foundation Bolts upto 32mm Dia |  | Nos
33 |  | Fixing of Foundation Bolts above 32mm Dia | 13000 | MT | [5 empty] | 1.68 | 21840
Water bar
|  | Fixing of Water Bar |  | RM | [5 empty] | 286.5
Brickwork & Masonary
|  | Brick work 1:6 | 3100 | Cum | [5 empty] | 54 | 167400
|  | Plaster | 160 | Sqm | [5 empty] | 989 | 158240
|  | Net Finish | 185 | Sqm | [5 empty] | 820 | 151700
4518389.3
10260574
109616.75
93.6041

## GI 2
Estimate value sheet
GI-2
Division-Pipe
Vendor- AGI
Sl No | Description | Struc. | Item | L | B | H | Nos | No of ele | U.Weight | Qnty | Unit | Ref | Claimed in
[9 empty] | 96 | 25 | 0.15 | 360