## RA 1
To
Nakoda Pipe Implex
Tilda, Chattisgarh
Work order No: SNIPIPL/WO/2022-23/041
Bill No RA 1 | [10 empty] | 2023-02-10
Sl No | Item no | Description | Block | Rate | Unit | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Excavation 0--3 Mtr With a lead of 1000 Mtr | Pipe Mill | 160 | m3 |  | 0 |  | 0 | 0 | 0
2 | 2 | Backfilling | Pipe Mill | 85 | m3 |  | 0 |  | 0 | 0 | 0
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 | m3 |  | 0 |  | 0 | 0 | 0
| B | Plain & reinforced Cement Concrete
4 | 6 | Plain Cement concrete 0--3 Mtr | Pipe Mill | 2100 | m3 |  | 0 |  | 0 | 0 | 0
5 | 7 | Reinforced cement concrete (all grade) 0--3 Mtr | Pipe Mill | 2600 | m3 |  | 0 |  | 0 | 0 | 0
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 | m3 |  | 0 |  | 0 | 0 | 0
| E | Formwork (Shuttering)
7 | 21 | Shuttering With 12 mm ply {0--3}Mtr (For Cooling Tower) | Pipe Mill | 550 | m2 |  | 0 |  | 0 | 0 | 0
Soling Hardcore & Others
8 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 | M |  | 0 |  | 0 | 0 | 0
9 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 | m2 |  | 0 |  | 0 | 0 | 0
| C | REINFORCEMENT WORK |  |  | m2
10 | 16 | Reinforcement Work {0--3}Mtr | Pipe Mill | 7000 | MT |  | 0 |  | 0 | 0 | 0
11 |  | Reinforcement Work {0--3}Mtr For Cooling Tower | Pipe Mill | 6600 |  |  | 0 |  | 0 | 0 | 0
| * | Total |  |  |  |  | 0 |  | 0 |  | 0

## RA 2
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [7 empty] | Date of Submission-27th March 2023
Work order No: SNIPIPL/WO/2022-23/041 | [7 empty] | Date of Finalizing-13th April 2023
Bill No RA2
Sl No | Item no | Description | Block | Rate | Unit | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Excavation 0--3 Mtr With a lead of 1000 Mtr | Pipe Mill | 160 | m3 | 72.6 | 11616 | 0 | 0 | 72.6 | 11616
2 | 2 | Backfilling | Pipe Mill | 85 | m3 |  | 0 | 19.536 | 1660.56 | 19.536 | 1660.56
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 | m3 | 1087.7 | 65262 | 19.536 | 1172.16 | 1107.236 | 66434.16
| B | Plain & reinforced Cement Concrete
4 | 6 | Plain Cement concrete 0--3 Mtr | Pipe Mill | 2100 | m3 | 217.54 | 456834 | 0 | 0 | 217.54 | 456834
5 | 7 | Reinforced cement concrete (all grade) 0--3 Mtr | Pipe Mill | 2600 | m3 | 6 | 15600 | 212.25 | 551850 | 218.25 | 567450
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 | m3 | 0 | 0 | 16.68 | 55878 | 16.68 | 55878
| E | Formwork (Shuttering)
7 | 21 | Shuttering With 12 mm ply {0--3}Mtr (For Cooling Tower) | Pipe Mill | 550 | m2 | 5.4 | 2970 | 112.2 | 61710 | 117.6 | 64680
Soling Hardcore & Others
8 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 | M |  | 0 | 51 | 11220 | 51 | 11220
9 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 | m2 |  | 0 | 1061.25 | 137962.5 | 1061.25 | 137962.5
| C | REINFORCEMENT WORK |  |  | m2
10 | 16 | Reinforcement Work {0--3}Mtr | Pipe Mill | 7000 | MT | 1.44 | 10080 | 16.92 | 118440 | 18.36 | 128520
11 |  | Reinforcement Work {0--3}Mtr For Cooling Tower | Pipe Mill | 6600 |  |  | 0 |  | 0 | 0 | 0
| * | Total |  |  |  |  | 562362 |  | 939893.22 |  | 1502255.22

## RA 3
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-15th May 2023
Work order No: SNIPIPL/WO/2022-23/041 | [9 empty] | Date of Finalizing-27th May 2023
Bill No RA3
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Pipe Mill | 160 | m3 |  |  | 72.6 | 11616 |  |  | 72.6 | 11616
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Pipe Mill | 85 | m3 |  |  | 19.536 | 1660.56 |  |  | 19.536 | 1660.56
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 | m3 |  |  | 1107.236 | 66434.16 |  |  | 1107.236 | 66434.16
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Pipe Mill | 2100 | m3 |  |  | 217.54 | 456834 |  |  | 217.54 | 456834
5 | 7 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | Pipe Mill | 2600 | m3 |  |  | 218.25 | 567450 | 476.88 | 1239888 | 695.13 | 1807338
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 | m3 |  |  | 16.68 | 55878 |  |  | 16.68 | 55878
| E | Formwork (Shuttering)
7 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. (For Cooling Tower) | Pipe Mill | 400 | m2 |  |  |  |  | 321.67 | 128668 | 321.67 | 128668
8 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. (For Cooling Tower) | Pipe Mill | 550 | m2 |  |  | 117.6 | 64680 |  |  | 117.6 | 64680
Soling Hardcore & Others
9 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 | M |  |  | 51 | 11220 |  |  | 51 | 11220
10 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 | m2 |  |  | 1061.25 | 137962.5 | 486.78 | 63281.4 | 1548.03 | 201243.9
11 |  | Pocket Fixing work | Pipe Mill | 500 | Nos |  |  |  |  | 291 | 145500 | 291 | 145500
| C | REINFORCEMENT WORK
12 | 16 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Pipe Mill | 7000 | MT |  |  | 14.363 | 100541 | 46.55 | 325850 | 60.913 | 426391
13 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Pipe Mill | 6600 |  |  |  | 3.997 | 26380.2 |  |  | 3.997 | 26380.2
| * | Total | [6 empty] | 1500656.42 |  | 1903187.4 |  | 3403843.82

## RA 4
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [7 empty] | Date of Submission-15th May 2023
To Nakoda Pipe Impex Povt Ltd | [10 empty] | Date of Finalizing-27th june 2023
Work order No: SNIPIPL/WO/2022-23/041 | [10 empty] | Block:- pipe Mill
Bill No RA4
Sl No | Item no | Description | Block | Rate | Unit | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Pipe Mill | 160 | m3 | 72.6 | 11616 |  |  | 72.6 | 11616
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Pipe Mill | 85 | m3 | 19.536 | 1660.56 |  |  | 19.536 | 1660.56
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 | m3 | 1107.236 | 66434.16 |  |  | 1107.236 | 66434.16
| B | Plain & reinforced Cement Concrete
PCC
4 | 6 | 0--3 Mtr | Pipe Mill | 2100 | m3 | 217.54 | 456834 | 5.7425 | 12059.25 | 223.2825 | 468893.25
RCC
5 | 7 | 0--3 Mtr | Pipe Mill | 2600 | m3 | 695.13 | 1807338 | 81.1223 | 210917.9826 | 776.2523 | 2018255.9826
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 | m3 | 16.68 | 55878 | 19.38 | 64923 | 36.06 | 120801
| E | Formwork (Shuttering)
7 |  | 0--3 Mtr | Pipe Mill | 400 | m2 | 321.67 | 128668 | 139.8158 | 55926.32 | 461.4858 | 184594.32
8 | 21 | Shuttering Work for Cooling Tower | Pipe Mill | 550 | m2 | 117.6 | 64680 | 127.89 | 70339.5 | 245.49 | 135019.5
Soling Hardcore & Others
9 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 | M | 51 | 11220 | 67.2 | 14784 | 118.2 | 26004
10 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 | m2 | 1548.03 | 201243.9 | 865.1555 | 112470.215 | 2413.1855 | 313714.115
11 |  | Pocket Fixing work | Pipe Mill | 500 | Nos | 291 | 145500 |  |  | 291 | 145500
12 | 53(a) | Skilled Labour Supply-8 Hrs | Pipe Mill | 500 | Rate |  |  | 12.625 | 6312.5 | 12.625 | 6312.5
13 | 53(b) | Un-Skilled Labour Supply-8 Hrs | Pipe Mill | 330 | Rate |  |  | 48.625 | 16046.25 | 48.625 | 16046.25
16 | 36 | RCC Dismantling | Pipe Mill | 3000 | m3 |  |  | 5.6 | 16800 | 5.6 | 16800
| C | REINFORCEMENT WORK
14 | 16 | 0--3 Mtrs | Pipe Mill | 7000 | MT | 60.913 | 426391 | 0.47 | 3290 | 61.383 | 429681
15 |  | TMT Work for Cooling tower | Pipe Mill | 6600 | MT | 3.997 | 26380.2 | 1.83 | 12078 | 5.827 | 38458.2
Mason Works
17 | 25 | Brickwork 0--3 Mtr | Pipe Mill | 3100 |  |  |  | 23.7153 | 73517.43 | 23.7153 | 73517.43
18 | 27 | Brickwork 3--6 Mtr | Pipe Mill | 3410 |  |  |  | 3.7855 | 12908.7153 | 3.7855 | 12908.7153
Plastering & Finishing Items
19 | 28 | Plaster 0--3 Mtr | Pipe Mill | 160 |  |  |  | 231.06 | 36969.6 | 231.06 | 36969.6
20 | 29 | Plaster 3--6 Mtr | Pipe Mill | 176 |  |  |  | 43.8083 | 7710.2608 | 43.8083 | 7710.2608
| * | Total |  |  |  |  | 3403843.82 |  | 727053.0237 |  | 4130896.8437

## RA 5
To Nakoda Pipe Impex Povt Ltd | [10 empty] | Date of Finalizing-30th july 2023
Work order No: SNIPIPL/WO/2022-23/041 | [10 empty] | Block:- pipe Mill
Bill No RA5
Sl No | Item no | Description | Block | Rate | Unit | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Pipe Mill | 160 | m3 | 72.6 | 11616 |  |  | 72.6 | 11616
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Pipe Mill | 85 | m3 | 19.536 | 1660.56 |  |  | 19.536 | 1660.56
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 | m3 | 1107.236 | 66434.16 |  |  | 1107.236 | 66434.16
| B | Plain & reinforced Cement Concrete
PCC
4 | 6 | 0--3 Mtr | Pipe Mill | 2100 | m3 | 223.2825 | 468893.25 |  | 0 | 223.2825 | 468893.25
RCC
5 | 7 | 0--3 Mtr | Pipe Mill | 2600 | m3 | 776.2523 | 2018255.9826 |  | 0 | 776.2523 | 2018255.9826
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 | m3 | 36.06 | 120801 |  | 0 | 36.06 | 120801
| 11 | {Shrikomp} Grouting work | Pipe Mill | 4100 | m3 |  |  | 7.2 | 29520 | 7.2 | 29520
| E | Formwork (Shuttering)
7 |  | 0--3 Mtr | Pipe Mill | 400 | m2 | 461.4858 | 184594.32 |  | 0 | 461.4858 | 184594.32
8 | 21 | Shuttering Work for Cooling Tower | Pipe Mill | 550 | m2 | 245.49 | 135019.5 |  | 0 | 245.49 | 135019.5
Soling Hardcore & Others
9 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 | M | 118.2 | 26004 |  | 0 | 118.2 | 26004
10 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 | m2 | 2413.1855 | 313714.115 |  | 0 | 2413.1855 | 313714.115
11 |  | Pocket Fixing work | Pipe Mill | 500 | Nos | 291 | 145500 |  |  | 291 | 145500
12 | 53(a) | Skilled Labour Supply-8 Hrs | Pipe Mill | 500 | Rate | 12.625 | 6312.5 | 3 | 1500 | 15.625 | 7812.5
13 | 53(b) | Un-Skilled Labour Supply-8 Hrs | Pipe Mill | 330 | Rate | 48.625 | 16046.25 | 1 | 330 | 49.625 | 16376.25
16 | 36 | RCC Dismantling | Pipe Mill | 3000 | m3 | 5.6 | 16800 |  | 0 | 5.6 | 16800
| 42 | Pressure grouting | Pipe Mill | 620 | m2 |  |  | 92.4 | 57288 | 92.4 | 57288
| C | REINFORCEMENT WORK
14 | 16 | 0--3 Mtrs | Pipe Mill | 7000 | MT | 61.383 | 429681 |  | 0 | 61.383 | 429681
15 |  | TMT Work for Cooling tower | Pipe Mill | 6600 | MT | 5.827 | 38458.2 |  | 0 | 5.827 | 38458.2
Mason Works
17 | 25 | Brickwork 0--3 Mtr | Pipe Mill | 3100 | m3 | 23.7153 | 73517.43 |  | 0 | 23.7153 | 73517.43
18 | 27 | Brickwork 3--6 Mtr | Pipe Mill | 3410 | m3 | 3.7855 | 12908.7153 |  | 0 | 3.7855 | 12908.7153
Plastering & Finishing Items
19 | 28 | Plaster 0--3 Mtr | Pipe Mill | 160 | m2 | 231.06 | 36969.6 |  | 0 | 231.06 | 36969.6
20 | 29 | Plaster 3--6 Mtr | Pipe Mill | 176 | m2 | 43.8083 | 7710.2608 |  | 0 | 43.8083 | 7710.2608
| * | Total |  |  |  |  | 4130896.8437 |  | 88638 |  | 4219534.8437

## Sheet1
AG INFRATECH
SITE -:SHREENAK0DA PIPE & IMPEX PVT.LTD. KHAMARIYA RAIPUR
BILL OF QUANTITIES (ABSTRACT ) PIPE MILL AREA NEW 4TH RA BILL (fUNE-2023)
S.NO | Description of Work | Unit | Thise bill Qty | Previous Bill Qty | Total Qty. | Rate |  | Thise bill Amt. | Previous Bill Amt. | Total Amt.
1 | RCC DISMANTING WORK(36) | m3 | 5.6 | 0 | 5.6 | 3000 |  | 16800 | 0 | 16800
2 | Earth Excavation Work | m3 | 0 | 72.6 | 72.6 | 160 |  | 0 | 11616 | 11616
3 | Back Filling Work | m3 | 0 | 32.06 | 32.06 | 85 |  | 0 | 2724.76 | 2724.76
4 | Watering & consolidating Work | m3 | 0 | 1107.24 | 1107.24 | 60 |  | 0 | 66434.16 | 66434.16
5 | PCC Work | m3 | 5.74 | 217.54 | 223.28 | 2100 |  | 12054 | 456834 | 468893.25
6 | RCC For Cooling Tower | m3 | 19.38 | 16.68 | 36.06 | 3350 |  | 64923 | 55878 | 120801
7 | Shuttering Work for cooling Tower | m2 | 127.89 | 117.6 | 245.49 | 550 |  | 70339.5 | 64680 | 135019.5
8 | R/F Work for cooling tower | MT | 1.83 | 0 | 1.83 | 6600 |  | 12078 | 0 | 12045.05
9 | RCC Work for M/C Foundation | m3 | 81.12 | 1172.01 | 1253.13 | 2600 |  | 210912 | 3047226 | 3258143.98
10 | Shuttering Work for M/C Foundation | m2 | 139.82 | 643.34 | 783.16 | 400 |  | 55928 | 257336 | 313262.18
11 | Providing & Fixing Water Bar | RM | 67.2 | 51 | 51 | 220 |  | 14784 | 11220 | 11220
12 | Re-inforcement Work | MT | 0.47 | 64.91 | 65.38 | 7000 |  | 3290 | 454370 | 457632
13 | Flooring flotter Finishing work | m2 | 865.16 | 2034.81 | 2899.97 | 130 |  | 112470.8 | 264525.3 | 376995.52
14 | Shuttering pocket Fixing Work | m2 | 0 | 582 | 582 | 500 |  | 0 | 291000 | 291000
15 | Brickwork Upto 3 Mtr | m3 | 27.5 | 0 | 27.5 | 3100 |  | 85250 | 0 | 85252.63
16 | Brickwork Above 3 Mtr | m3 | 3.79 | 3.79 | 0 | 310 |  | 1174.9 | 0 | 1173.52
17 | Plaster Work Upto 3 Mtr | m2 | 274.87 | 274.87 | 0 | 210 |  | 57722.7 | 0 | 57722.34
18 | Plaster Work Above 3 Mtr | m2 | 43.81 | 43.81 | 0 | 21 |  | 920.01 | 0 | 919.97
19 | Labour Supply 8 Hrs (Skilled) | RATE | 12.625 | 12.625 | 0 | 550 |  | 6943.75 | 0 | 6943.75
20 | Labour Supply 8 Hrs (Un-Skilled) | RATE | 48.625 | 48.625 | 0 | 330 |  | 16046.25 | 0 | 16046.25
[7 empty] | TOTAL:- | 741636.91 | 4983844.Z2 | 5708629.86
724785.64
[8 empty] | 16851.27 | Difference

## RA 5 Measurement
SHREE NAKODA PIPE IMPEX PVT LTD
DETAIL OF MEASURMENT & CALCULATION Or qUANTITY PIPE MILL-3
AG INFRATECH
DESCRIPTION | NOS | LENGTH | WIDTH | H/D | QTY | REMARK
RCC Dismantling work
Man Panel Room Mill-01 Electric Cable Trench | 1 | 8 | 1 | 0.7 | 5.6 | m3
[5 empty] | 5.6 | m3
,. . . , . ..... . . . . . ,
PCC work
Man Panel Room Mill-01 Electric Cable Trench | 1 | 8 | 1 | 0.1 | 0.8 | m3
Cooling Tower Near W-Bridge | 1 | 5.2 | 5.2 | 0.1 | 2.704 | m3
Cooling Tower Near W-Bridge Pump Foundation | 1 | 3.3 | 1.75 | 0.1 | 0.5775 | m3
1st Electric panel room bottom drain | 1 | 5.8 | 1.1 | 0.1 | 0.638 | m3
2nd Electric panel room bottom drain | 1 | 9.3 | 1.1 | 0.1 | 1.023 | m3
[5 empty] | 5.7425 | m3
RCC Work for M/C Foundation
0.05 mm Thick
Man Panel Room Mill-01 Electric Cable Trench | 2 | 8 | 0.15 | 0.6 | 1.44 | m3
0.05mm Thick Rcc Part-1 | 1 | 19.2 | 5.6 | 0.05 | 5.376 | m3
(-) Deduct Pocket | -2 | 2.9 | 0.15 | 0.05 | -0.0435 | m3
(-) Deduct Pocket | -39 | 0.15 | 0.15 | 0.05 | -0.043875 | m3
(-) Deduct Pocket | -12 | 0.2 | 0.2 | 0.05 | -0.024 | m3
0.05mm Thick Rcc Part-2(circle-3.14x5x5=78.50) | 1 | 1 | 78.5 | 0.05 | 3.925 | m3
(-) Deduct Pocket | -80 | 0.15 | 0.15 | 0.05 | -0.09 | m3
(-) Deduct Pocket | -20 | 0.2 | 0.2 | 0.05 | -0.04 | m3
0.050mm Thick Rcc Part-3 | 1 | 5 | 5.25 | 0.05 | 1.3125 | m3
0.050mm Thick Rcc Part-4 | 1 | 79.98 | 6.7 | 0.05 | 26.7933 | m3
Offset | 1 | 1.75 | 1.1 | 0.05 | 0.09625 | m3
(-) Deduct Pocket | -82 | 0.15 | 0.15 | 0.05 | -0.09225 | m3
(-) Deduct Pocket | -14 | 0.2 | 0.2 | 0.05 | -0.028 | m3
0.050mm Thick Rcc Part-5 (4.4+1.2 +3.82 +18.40=27.82) | 1 | 27.8 | 6.2 | 0.05 | 8.618 | m3
(-) Deduct Pocket | -24 | 0.15 | 0.15 | 0.05 | -0.027 | m3
(-) Deduct Pocket | -20 | 0.2 | 0.2 | 0.05 | -0.04 | m3
0.050mm Thick Rcc Part-6 | 1 | 3.82 | 0.8 | 0.05 | 0.1528 | m3
(-) Deduct for to duct | -2 | 1.2 | 0.5 | 0.05 | -0.06 | m3
(-) Deduct for to Chamber | -2 | 1.95 | 1.4 | 0.05 | -0.273 | m3
(-) Deduct for All Drain (3.1+1.155+38.6+38.6+2.5+6.650+1.1+12.30+1.25+1. 25+3.820+3.650+17.38+17.380=147.48) | -1 | 147.48 | 0.3 | 0.05 | -2.2122 | m3
(-) Deduct for to duct | -2 | 0.65 | 0.65 | 0.05 | -0.04225 | m3
c foundation total Drain sloping part avg thick-0.15 mm | 1 | 147.48 | 0.3 | 0.15 | 6.6366 | m3
1st Electric panel room Column | 4 | 0.23 | 0.23 | 3.37 | 0.71309 | m3
Lintel beam long side | 2 | 4.95 | 0.23 | 0.15 | 0.34155 | m3
Lintel beam short side | 2 | 3.65 | 0.23 | 0.15 | 0.25185 | m3
2nd Electric panel room Column | 8 | 0.23 | 0.23 | 3.37 | 1.4262 | m3
Lintel beam long side | 2 | 8.65 | 0.23 | 0.15 | 0.59685 | m3
Lintel beam short side | 2 | 3.6 | 0.23 | 0.15 | 0.2484 | m3
Total Quantity | . |  | ' . | A | 54.9123 | m3
Prev Bill Quantity |  |  |  | B | 26.21 | m3
Total Quantity for RCC in This Bill |  |  |  | A+B | 81.1223 | m3
Shuttering Work for M/C Foundation
0.050 mm Thick
Man Panel Room Mill-01 Electric Cable Trench | 2 | 8 |  | 0.6 | 9.6 | m2
0.450mm Thick Rcc Part-1 | 1 | 19.2 |  | 0.05 | 0.96 | m2
| 1 | 19.2 |  | 0.05 | 0.96 | m2
| 1 | 5.6 |  | 0.05 | 0.28 | m2
Drain (2.9+2.9+0.15=5.95) | 1 | 5.95 |  | 0.05 | 0.2975 | m2
0.050mm Thick Rcc Part-2 /circumference(2x3.14x5=31.40) | 1 | 31.4 |  | 0.05 | 1.57 | m2
0.050mm Thick Rcc Part-3 | 1 | 5.25 |  | 0.05 | 0.2625 | m2
0.050mm Thick Rcc Part-3 | 1 | 5.25 |  | 0.05 | 0.2625 | m2
0.050mm Thick Rcc Part—4 | 1 | 79.98 |  | 0.05 | 3.999 | m2
0.050mm Thick Rcc Part-4 | 1 | 79.98 |  | 0.05 | 3.999 | m2
0.050mm Thick Rcc Part-4 | 1 | 6.7 |  | 0.05 | 0.335 | m2
Offset | 2 | 1.75 |  | 0.05 | 0.175 | m2
0.050mm Thick Rcc Part-5 (4.4+1.2 +3.82 +18.40=27.82) | 1 | 27.8 |  | 0.05 | 1.39 | m2
0.050mm Thick Rcc Part-5 (4.4+1.2 +3.82+18.40=27.82) | 1 | 27.8 |  | 0.05 | 1.39 | m2
0.050mm Thick Rcc Part-5 (4.4+1.2+3.82 +18.40=27.82) | 1 | 6.2 |  | 0.05 | 0.31 | m2
0.050mm Thick Rcc Part-6 | 2 | 3.82 |  | 0.05 | 0.382 | m2
0.050mm Thick Rcc Part-7 | 2 | 0.8 |  | 0.05 | 0.08 | m2
All Drain inner side (38.6+1.155+2.5+38.6+2.5+2.5+2.5+6.65+1.1+12.3+1. 25+3.82+3.65+0.3+17.38+17.380=150.935) | 1 | 150.94 |  | 0.05 | 7.547 | m2
All Drain outer side (38.6+0.3+ 1.155+3.1+38.6+0.3+3.1+6.65+1.1+12.3+0. 3+1.25+3.82 +0.3+3.65+0.3+17.38+0.3+17.380+0.3= 1 51.188) | 1 | 151.19 |  | 0.05 | 7.5595 | m2
1st Electric panel room Column(0.23x4=0.92) | 4 | 0.92 |  | 3.37 | 12.4016 | m2
Floor Drain side | 2 | 5.8 |  | 0.45 | 5.22 | m2
Lintel beam long side(0.23+0.15+0.15=0.53) | 4 | 4.95 |  | 0.53 | 10.494 | m2
Lintel beam short side | 4 | 3.65 |  | 0.53 | 7.738 | m2
2nd Electric panel room Column | 8 | 0.92 |  | 3.37 | 24.8032 | m2
Floor Drain side | 2 | 9.3 |  | 0.45 | 8.37 | m2
Lintel beam long side | 4 | 8.65 |  | 0.53 | 18.338 | m2
Lintel beam short side | 4 | 3.6 |  | 0.53 | 7.632 | m2
PCC |  |  |  |  | 0 | m2
1st Electric panel room bottom drain | 2 | 5.8 |  | 0.1 | 1.16 | m2
| 2 | 1.1 |  | 0.1 | 0.22 | m2
2 nd Electric panel room bottom drain | 2 | 9.3 |  | 0.1 | 1.86 | m2
| 2 | 1.1 |  | 0.1 | 0.22 | m2
Total Shuttering Work for M/C Foundation |  |  |  |  | 139.8158 | m2
RCC work for Cooling Tower
Cooling Tower Near W-Bridge Raft | 1 | 5 | 5 | 0.3 | 7.5 | m3
Wall | 2 | 4 | 0.2 | 3 | 4.8 | m3
Wall | 2 | 4.4 | 0.2 | 3 | 5.28 | m3
internal column | 4 | 0.3 | 0.3 | 3 | 1.08 | m3
Cooling Tower Near W-Bridge Pump Foundation | 2 | 1.2 | 0.6 | 0.5 | 0.72 | m3
Total RCC work for Cooling Tower |  |  |  |  | 19.38 | m3
Shuttering work for Cooling Tower
Pcc
Cooling Tower Near W-Bridge(5.2x4=20.80) | 1 | 20.8 |  | 0.1 | 2.08 | m2
Cooling Tower Near W-Bridge Pump Foundation | 2 | 3.3 |  | 0.1 | 0.66 | m2
| 2 | 1.75 |  | 0.1 | 0.35 | m2
RCC |  |  |  |  | 0 | m2
Cooling Tower Near W-Bridge Raft(5.0x4=20) | 1 | 20 |  | 0.3 | 6 | m2
Outer side Wall (4.40x4=17.60/ | 1 | 17.6 |  | 3 | 52.8 | m2
inner side Wall(4.0x4= 16.0) | 1 | 16 |  | 3 | 48 | m2
internal column(0.3x4= 1.20) | 4 | 1.2 |  | 3 | 14.4 | m2
Cooling Tower Near W-Bridge Pump Foundation | 4 | 1.2 |  | 0.5 | 2.4 | m2
Cooling Tower Near W-Bridge Pump Foundation | 4 | 0.6 |  | 0.5 | 1.2 | m2
Total Shuttering work for Cooling Tower |  |  |  |  | 127.89 | m2
Flooring Flotter Finish Work
0.05 mm Thick
0.05mm Thick Rcc Part-1 | 1 | 19.2 | 5.6 |  | 107.52 | m2
(-) Deduct Pocket | -2 | 2.9 | 0.15 |  | -0.87 | m2
(-) Deduct Pocket | -39 | 0.15 | 0.15 |  | -0.8775 | m2
(-) Deduct Pocket | -12 | 0.2 | 0.2 |  | -0.48 | m2
0.05mm Thick Rcc Part-2 (circle-3.14x5x5=78.S0) | 1 | 1 | 78.5 |  | 78.5 | m2
(-) Deduct Pocket | -80 | 0.15 | 0.15 |  | -1.8 | m2
(-) Deduct Pocket | -20 | 0.2 | 0.2 |  | -0.8 | m2
0.050mm Thick Rcc Part—3 | 1 | 5 | 5.25 |  | 26.25 | m2
0.050mm Thick Rcc Part-4 | 1 | 79.98 | 6.7 |  | 535.866 | m2
Offset | 1 | 1.75 | 1.1 |  | 1.925 | m2
(-) Deduct Pocket | -82 | 0.15 | 0.15 |  | -1.845 | m2
(-) Deduct Pocket | -14 | 0.2 | 0.2 |  | -0.56 | m2
0.050mm Thick Rcc Part-5 (4.4+1.2 +3.82+18.40=27.82) | 1 | 27.8 | 6.2 |  | 172.36 | m2
) Deduct Pocket | -24 | 0.15 | 0.15 |  | -0.54 | m2
(-) Deduct Pocket | -20 | 0.2 | 0.2 |  | -0.8 | m2
0.050mm Thick Rcc Part-6 | 1 | 3.82 | 0.8 |  | 3.056 | m2
(-) Deduct for to duct | -2 | 1.2 | 0.5 |  | -1.2 | m2
(-) Deduct for to Chamber | -2 | 1.95 | 1.4 |  | -5.46 | m2
(-) Deduct for All Drain (3.1+1.155+38.6+38.6+2.5+6.650+1.1+12.30+1.25+1. 25+3.820+3.650+17.38+17.380=147.48) | -1 | 147.48 | 0.3 |  | -44.244 | m2
(-) Deduct for to duct | -2 | 0.65 | 0.65 |  | -0.845 | m2
Total Shuttering work for Cooling Tower |  |  |  |  | 865.1555 | m2
Brick work Upto 3 Mtr GL
1st Electric panel room Long Wall | 1 | 4.95 | 0.23 | 3.37 | 3.8367 | m3
1st Electric panel room Long Wall | 1 | 4.95 | 0.23 | 3.52 | 4.0075 | m3
Short Wall | 2 | 3.65 | 0.23 | 3.37 | 5.6582 | m3
Column | -4 | 0.23 | 0.23 | 3.37 | -0.71309 | m3
DeductionDoor | -1 | 1 | 0.23 | 2.1 | -0.483 | m3
DeductionWindowl | -1 | 2 | 0.23 | 1 | -0.46 | m3
DeductionWindow2 | -1 | 1 | 0.23 | 1 | -0.23 | m3
2ndElectricpanelroomLongWall | 1 | 8.68 | 0.23 | 3.37 | 6.7279 | m3
2ndElectric panel roomLongWall | 1 | 8.65 | 0.23 | 3.52 | 7.003 | m3
ShortWall | 2 | 3.6 | 0.23 | 3.37 | 5.5807 | m3
DeductionDoor | -2 | 1 | 0.23 | 2.1 | -0.966 | m3
DeductionWindow1 | -2 | 1.8 | 0.23 | 1 | -0.828 | m3
DeductionWindow2 | -1 | 0.9 | 0.23 | 1 | -0.207 | m3
Column | -8 | 0.23 | 0.23 | 3.37 | -1.4262 | m3
Total brick Work 0--3 Mtr |  |  |  |  | 27.5008 | m3
Brick work Above 3 Mtr GL
1st Electric panel room Long Wall | 1 | 4.95 | 0.23 | 0.37 | 0.42125 | m3
1st Electric panel room Long Wall | 1 | 4.95 | 0.23 | 0.52 | 0.59202 | m3
Shon Wall | 2 | 3.65 | 0.23 | 0.37 | 0.62123 | m3
Column | -4 | 0.23 | 0.23 | 0.37 | -0.078292 | m3
2nd Electric panel room Long Wall | 1 | 8.68 | 0.23 | 0.37 | 0.73867 | m3
2nd Electric panel room Long Wall | 1 | 8.65 | 0.23 | 0.52 | 1.0345 | m3
Short Wall | 2 | 3.6 | 0.23 | 0.37 | 0.61272 | m3
Column | -8 | 0.23 | 0.23 | 0.37 | -0.15658 | m3
Total brick Work 3--6 Mtr |  |  |  |  | 3.7855 | m3
0
Plaster work Upto 3 Mtr GL
1st Electric panel room Long Wall Outer side | 1 | 4.95 |  | 3.37 | 16.6815 | m2
Top Portion | 1 | 4.95 |  | 0.23 | 1.1385 | m2
1st Electric panel room Long Wall Outer side | 1 | 4.95 |  | 3.52 | 17.424 | m2
Top Portion | 1 | 4.95 |  | 0.23 | 1.1385 | m2
Short Wall Outer side | 2 | 3.65 |  | 3.37 | 24.601 | m2
Top Portion | 2 | 3.65 |  | 0.23 | 1.679 | m2
1st Electric panel room Long Wall Inner side | 1 | 4.49 |  | 3.37 | 15.1313 | m2
1st Electric panel room Long Wall Outer side | 1 | 4.49 |  | 3.52 | 15.8048 | m2
Short Wall Outer side | 2 | 3.19 |  | 3.37 | 21.5006 | m2
DeductionDoor | -1 | 1 |  | 2.1 | -2.1 | m2
Deduction Window1 | -1 | 2 |  | 1 | -2 | m2
Deduction Window2 | -1 | 1 |  | 1 | -1 | m2
2nd Electric panel room Long Wall Outer side | 1 | 8.68 |  | 3.37 | 29.2516 | m2
TopPortion | 1 | 8.68 |  | 0.23 | 1.9964 | m2
2nd Electric panel room Long Wall Outer side | 1 | 8.65 |  | 3.52 | 30.448 | m2
TopPortion | 1 | 8.65 |  | 0.23 | 1.9895 | m2
ShortWall Outer side | 2 | 3.6 |  | 3.37 | 24.264 | m2
TopPortion | 2 | 3.6 |  | 0.23 | 1.656 | m2
2nd Electric panel room Long Wall Inner side | 1 | 8.68 |  | 3.37 | 29.2516 | m2
2nd Electric panel room Long Wall Inner side | 1 | 8.65 |  | 3.52 | 30.448 | m2
Short Wall Inner side | 2 | 3.6 |  | 3.37 | 24.264 | m2
DeductionDoor | -2 | 1 |  | 2.1 | -4.2 | m2
DeductionWindowl | -2 | 1.8 |  | 1 | -3.6 | m2
Deduction Window2 | -1 | 0.9 |  | 1 | -0.9 | m2
Total Plaster Work 0--3 Mtr |  |  |  |  | 274.8683 | m2
Plaster work Above 3 Mtr GL
1st Electric panel room Long Wall Outer side | 1 | 4.95 |  | 0.37 | 1.8315 | m2
Top Portion | 1 | 4.95 |  | 0.23 | 1.1385 | m2
1st Electric panel room Long Wall Outer side | 1 | 4.95 |  | 0.52 | 2.574 | m2
Top Portion | 1 | 4.95 |  | 0.23 | 1.1385 | m2
Short Wall Outer side | 2 | 3.65 |  | 0.37 | 2.701 | m2
Top Portion | 2 | 3.65 |  | 0.23 | 1.679 | m2
1st Electric panel room Long Wall Inner side | 1 | 4.49 |  | 0.37 | 1.6613 | m2
1st Electric panel room Long Wall Outer side | 1 | 4.49 |  | 0.52 | 2.3348 | m2
Short Wall Outer side | 2 | 3.19 |  | 0.37 | 2.3606 | m2
2nd Electric panel room Long Wall Outer side | 1 | 8.68 |  | 0.37 | 3.2116 | m2
Top Portion | 1 | 8.68 |  | 0.23 | 1.9964 | m2
2nd Electric panel room Long Wall Outer side | 1 | 8.65 |  | 0.52 | 4.498 | m2
Top Portion | 1 | 8.65 |  | 0.23 | 1.9895 | m2
Short Wall Outer side | 2 | 3.6 |  | 0.37 | 2.664 | m2
Top Portion | 2 | 3.6 |  | 0.23 | 1.656 | m2
2nd Electri anel room Long Wall Inner side | 1 | 8.68 |  | 0.37 | 3.2116 | m2
2nd Electric panel room Long Wall Inner side | 1 | 8.65 |  | 0.52 | 4.498 | m2
Short Wall Inner side | 2 | 3.6 |  | 0.37 | 2.664 | m2
Total Plaster work Above 3 Mtr GL |  |  |  |  | 43.8083 | m2
Providing 7 Fixing Water bar
Cooling Tower near W-Bridge Raft (4.20x4=16.80 m) | 1 | 16.8 |  |  | 16.8 | RM
Cooling tower wall 1st Lift-1.20 m | 1 | 16.8 |  |  | 16.8 | RM
Cooling tower wall 2nd Lift-1.20 m | 1 | 16.8 |  |  | 16.8 | RM
Cooling tower wall 3rd Lift-1.20 m | 1 | 16.8 |  |  | 16.8 | RM
Total Providing 7 Fixing Water bar |  |  |  |  | 67.2 | RM
Labour Supply
PIPE MILL-03 Shiltting M/C Foundation |  |  | Skilled | Unskilled
Work-Dismentaling RCC/Rod Cutting/Excavation/Dressing/PCC/Steel Binding/shuttring/RCC Casting
2023-05-13 |  |  | 0 | 2 |  | /8Hrs
2023-05-14 |  |  | 2 | 0 |  | /8Hrs
2023-05-15 |  |  | 1 | 6 |  | /8Hrs
2023-05-16 |  |  | 0 | 5.5 |  | /8Hrs
2023-05-17 |  |  | 1.625 | 1.625 |  | /8Hrs
2023-05-18 |  |  | 0 | 3.5 |  | /8Hrs
2023-05-19 |  |  | 0 | 4 |  | /8Hrs
2023-05-20 |  |  | 0 | 2 |  | /8Hrs
2023-05-21 |  |  | 0 | 2 |  | /8Hrs
2023-05-22 |  |  | 0 | 0 |  | /8Hrs
2023-05-23 |  |  | 0 | 3 |  | /8Hrs
2023-05-24 |  |  | 0 | 3 |  | /8Hrs
2023-05-25 |  |  | 0 | 3 |  | /8Hrs
2023-05-26 |  |  | 0 | 2 |  | /8Hrs
2023-05-27 |  |  | 1 | 2 |  | /8Hrs
2023-05-28 |  |  | 1 | 2 |  | /8Hrs
2023-05-29 |  |  | 0 | 2 |  | /8Hrs
2023-05-30 |  |  | 2 | 0 |  | /8Hrs
2023-05-31 |  |  | 2 | 2 |  | /8Hrs
2023-06-01 |  |  | 1 | 2 |  | /8Hrs
2023-06-02 |  |  | 1 | 1 |  | /8Hrs
Total |  |  | 12.625 | 48.625 |  | /8Hrs

## RA 6
To Nakoda Pipe Impex Povt Ltd | [11 empty] | Date of Finalizing-13th september 2023
Work order No: SNIPIPL/WO/2022-23/041 | [11 empty] | Block:- pipe Mill
Bill No RA6
Sl No | Item no | Description | Block | Rate |  | Unit | Upto last bill |  | This Bill |  | Total
|  |  |  | old | New |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Pipe Mill | 160 |  | m3 | 72.6 | 11616 |  |  | 72.6 | 11616
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Pipe Mill | 85 |  | m3 | 19.536 | 1660.56 |  |  | 19.536 | 1660.56
3 | 2 (a) | Watering & Consolidation | Pipe Mill | 60 |  | m3 | 1107.236 | 66434.16 |  |  | 1107.236 | 66434.16
| B | Plain & reinforced Cement Concrete
PCC
4 | 6 | 0--3 Mtr | Pipe Mill | 2100 |  | m3 | 223.2825 | 468893.25 |  | 0 | 223.2825 | 468893.25
RCC
5 | 7 | 0--3 Mtr | Pipe Mill | 2600 | 2750 | m3 | 776.2523 | 2018255.9826 | 0.93 | 2557.5 | 777.1823 | 2020673.9826
6 | 13 | RCC Work for Cooling tower | Pipe Mill | 3350 |  | m3 | 36.06 | 120801 |  | 0 | 36.06 | 120801
| 11 | {Shrikomp} Grouting work | Pipe Mill | 4100 |  | m3 | 7.2 | 29520 |  | 0 | 7.2 | 29520
| E | Formwork (Shuttering)
7 |  | 0--3 Mtr | Pipe Mill | 400 |  | m2 | 461.4858 | 184594.32 | 1.95 | 780 | 463.4358 | 185374.32
8 | 21 | Shuttering Work for Cooling Tower | Pipe Mill | 550 |  | m2 | 245.49 | 135019.5 |  | 0 | 245.49 | 135019.5
Soling Hardcore & Others
9 | 33 | Providing and fixing of PVC water bar 230 | Pipe Mill | 220 |  | M | 118.2 | 26004 |  | 0 | 118.2 | 26004
10 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Pipe Mill | 130 |  | m2 | 2413.1855 | 313714.115 |  | 0 | 2413.1855 | 313714.115
11 |  | Pocket Fixing work | Pipe Mill | 500 |  | Nos | 291 | 145500 |  |  | 291 | 145500
12 | 53(a) | Skilled Labour Supply-8 Hrs | Pipe Mill | 500 |  | Rate | 15.625 | 7812.5 | 12 | 6000 | 27.625 | 13812.5
13 | 53(b) | Un-Skilled Labour Supply-8 Hrs | Pipe Mill | 330 |  | Rate | 49.625 | 16376.25 | 15 | 4950 | 64.625 | 21326.25
16 | 36 | RCC Dismantling | Pipe Mill | 3000 |  | m3 | 5.6 | 16800 |  | 0 | 5.6 | 16800
| 42 | Pressure grouting | Pipe Mill | 620 |  | m2 | 92.4 | 57288 |  | 0 | 92.4 | 57288
| C | REINFORCEMENT WORK
14 | 16 | 0--3 Mtrs | Pipe Mill | 7000 |  | MT | 61.383 | 429681 |  | 0 | 61.383 | 429681
15 |  | TMT Work for Cooling tower | Pipe Mill | 6600 |  | MT | 5.827 | 38458.2 |  | 0 | 5.827 | 38458.2
Mason Works
17 | 25 | Brickwork 0--3 Mtr | Pipe Mill | 3100 |  | m3 | 23.7153 | 73517.43 |  | 0 | 23.7153 | 73517.43
18 | 27 | Brickwork 3--6 Mtr | Pipe Mill | 3410 |  | m3 | 3.7855 | 12908.7153 |  | 0 | 3.7855 | 12908.7153
Plastering & Finishing Items
19 | 28 | Plaster 0--3 Mtr | Pipe Mill | 160 |  | m2 | 231.06 | 36969.6 |  | 0 | 231.06 | 36969.6
20 | 29 | Plaster 3--6 Mtr | Pipe Mill | 176 |  | m2 | 43.8083 | 7710.2608 |  | 0 | 43.8083 | 7710.2608
| * | Total | [5 empty] | 4219534.8437 |  | 14287.5 |  | 4233682.8437
14287.5

## RA 6 Measurement
SHREE NAKODA PIPE IMPEX PVT LTD
DETAIL OF MEASURMENT & CALCULATION OF QUANTITY PIPE MILL-3
AG INFRATECH-AUG-2023
DESCRIPTION | Struc. | Grid | NOS | LENGTH (M) | WIDTH (M) | H/D | QTY | REMARK
1.RCC Work
Pipe Mill-03 Near cooling Tower pump foundation |  |  | 1 | 2.2 | 1.7 | 0.25 | 0.935
Total Qty. for RCC Work | [6 empty] | 0.935 | Cum
2. Shuttring Work
Pipe Mill-03 Near cooling Tower pump foundation |  |  | 2 | 2.2 |  | 0.25 | 1.1
Pipe Mill-03 Near cooling Tower pump foundation |  |  | 2 | 1.7 |  | 0.25 | 0.85
Total Qty. For Shuttring Work | [6 empty] | 1.95 | Sqm
PIPE MILL-03 Shiltting M/C Foundation |  |  |  |  | Skilled Labour | Unskilled Labour
Work-pipe mill-03 to GI Mill-01 Rail track Moorum filling & Blast Speredding
Date-13/08/2023 |  |  |  |  | 1 | 4
Date-14/08/2023 |  |  |  |  | 1 | 3
Work-W-Bright Rcc Wall Deshmentling & Wastage Material Cleaning Work |  |  |  |  | 0 | 0
Date-28/08/2023 |  |  |  |  | 3 | 2
Date-29/08/2023 |  |  |  |  | 2 | 2
Work-Labour Quarter Room Rcc Wall Deshmentling work & Door & Window Fitting & Wastage Material Cleaning/Finishing Work |  |  |  |  | 0 | 0
Date-29/08/2023 |  |  |  |  | 3 | 2
Date-30/08/2023 |  |  |  |  | 2 | 2
|  |  |  | total | 12 | 15