## RA 1
Bill Name:- Pipe Mill
Bill No | RA1 | [15 empty] | 2023-02-10
SHREE NAKODA PIPE IMPEX Ltd TILDA Summary of ( PSB ) RA-03
S.no | DESCRIPTION | Unit | AGI QTY. | NAKODA QTY. | ARCHCONS CREATION QTY. | Rate | AGI Amount | NAKODA Amount | ARCHCONS CREATION Amount | Archon's Quantity | Rate | AGI Amount | Nakoda Amount | Archons Amount | DIFFERENCE Amount |  | Ref
[15 empty] | WITH ARCHCONS | WITH NAKODA
[15 empty] | 0 | 0 | RA1 Pipe mill
1 | Excavation Work | m3 | 72.6 | 72.6 | 72.6 | 160 | 11616 | 11616 | 11616 |  | 160 | 11616 | 11616 |  | 0 | 0 | RA1 Pipe mill
2 | Watering & Compaction Work | m3 | 1087.7 | 1087.7 | 1087.7 | 60 | 65262 | 65262 | 65262 |  | 60 | 65262 | 65262 |  | 0 | 0 | RA1 Pipe mill
3 | PCC Work | m3 | 217.54 | 217.54 | 217.54 | 2100 | 456834 | 456834 | 456834 |  | 2100 | 456834 | 456834 |  | 0 | 0 | RA1 Pipe mill
4 | RCC Work (Cooling Tower) | m3 | 6 | 6 | 6 | 2600 | 15600 | 15600 | 15600 |  | 3350 | 20100 | 20100 |  | 0 | 0 | RA1 Pipe mill
5 | Shuttering Work ( Cooling Tower) | m2 | 5.4 | 5.4 | 5.4 | 400 | 2160 | 2160 | 2160 |  | 550 | 2970 | 2970 |  | 0 | 0 | RA1 Pipe mill
6 | Steel Work | MT | 1.44 | 1.44 | 1.44 | 7000 | 10080 | 10080 | 10080 |  | 7000 | 10080 | 10080 |  | 0 | 0 | RA1 Pipe mill
[9 empty] | 0 | [7 empty] | RA1 Pipe mill
[7 empty] | 561552 | 561552 | 561552 |  |  | 566862 | 566862 |  | 0 | 0

## RA 2
Bill Name:- Pipe Mill
Bill No RA 2 | [16 empty] | 2023-03-27
SHREE NAKODA PIPE IMPEX Ltd TILDA Summary of (Cooling Tower ) RA1
S.no | DESCRIPTION | Unit | AGI QTY. | NAKODA QTY. | ARCHCONS QTY. | Rate | AGI Amount | NAKODA Amount | ARCHCONS Amount | WITH ARCHCONS | Rate | AGI Amount | NAKODA Amount | ARCHCONS Amount | DIFF Amount |  | Ref
[15 empty] | WITH Nakoda | WITH Archons
1 | EARTH EXCAVATION WORK | m3 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | RA2
2 | BACK FILLING WORK | m3 | 19.536 | 19.536 | 19.53 | 85 | 1660.56 | 1660.56 | 1660.05 | 19.536 | 85 | 1660.56 | 1660.56 | 1660.56 | 0 | 0 | RA2
3 | WATERING & CONSOLIDATION WORK | m3 | 19.536 | 19.536 | 19.53 | 60 | 1172.16 | 1172.16 | 1171.8 | 19.536 | 60 | 1172.16 | 1172.16 | 1172.16 | 0 | 0 | RA2
4 | PCC WORK | m3 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | RA2
5 | RCC WORK COOLING TOWER | m3 | 16.68 | 16.68 | 16.68 | 2600 | 43368 | 43368 | 43368 | 16.68 | 3350 | 55878 | 55878 | 55878 | 0 | 0 | RA2
6 | SHUTTERING WORK COOLING TOWER | m2 | 112.2 | 112.2 | 112.2 | 400 | 44880 | 44880 | 44880 | 112.2 | 550 | 61710 | 61710 | 61710 | 0 | 0 | RA2
7 | RCC WORK | m3 | 212.25 | 212.25 | 212.25 | 2600 | 551850 | 551850 | 551850 | 212.25 | 2600 | 551850 | 551850 | 551850 | 0 | 0 | RA2
8 | PROVIDING & FIXING WATER BAR | Mtr | 51 | 51 | 51 | 220 | 11220 | 11220 | 11220 | 51 | 220 | 11220 | 11220 | 11220 | 0 | 0 | RA2
9 | REINFORCEMENT WORK | MT | 16.92 | 16.92 | 16.921 | 7000 | 118440 | 118440 | 118447 | 16.921 | 7000 | 118440 | 118440 | 118447 | 0 | -0.001 | RA2
10 | FLOORING FLOTER FINISH WORK | SQM | 1061.25 | 1061.25 | 1061.25 | 130 | 137962.5 | 137962.5 | 137962.5 | 1061.25 | 130 | 137962.5 | 137962.5 | 137962.5 | 0 | 0 | RA2
* | Total | [5 empty] | 910553.22 | 910553.22 | 910559.35 |  |  | 939893.22 | 939893.22 | 939900.22 | 0 | -6.13
Abhishek Acharya | [9 empty] | Mukesh Lilhare | [6 empty] | Mahesh Wandre
Billing Engineer | [9 empty] | AGI | [6 empty] | Manager {Civil}
SNPIPL | [16 empty] | SNPIPL

## RA 3
Bill Name:- Pipe Mill | [16 empty] | Working Month- April 2023
Bill No RA 3 | [16 empty] | Bill Month- May 2023
SHREE NAKODA PIPE IMPEX Ltd TILDA Summary of (Cooling Tower ) RA1
S.no | DESCRIPTION | Unit | AGI QTY. | NAKODA QTY. | ARCHCONS QTY. | Rate | AGI Amount | NAKODA Amount | ARCHCONS Amount | WITH ARCHCONS | Rate | AGI Amount | NAKODA Amount | ARCHCONS Amount | DIFF Amount |  | Ref
[15 empty] | WITH Nakoda | WITH Archons
1 | EARTH EXCAVATION WORK | m3 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | RA3
2 | BACK FILLING WORK | m3 | 6.26 | [6 empty] | 6.25 | 85 | 532.1 | 0 | 531.25 | 532.1 | 0.01 | RA3
3 | WATERING & CONSOLIDATION WORK | m3 | [8 empty] | 60 | 0 | 0 | 0 | 0 | 0 | RA3
4 | PCC WORK | m3 | [8 empty] | 2100 | 0 | 0 | 0 | 0 | 0 | RA3
5 | RCC WORK COOLING TOWER | m3 | [8 empty] | 3350 | 0 | 0 | 0 | 0 | 0 | RA3
6 | SHUTTERING WORK | m2 | 323.24 | 321.67 | [5 empty] | 323.34 | 400 | 129296 | 128668 | 129336 | 628 | -0.1 | RA3
7 | RCC WORK | m3 | 503.09 | 476.88 | [5 empty] | 503 | 2600 | 1308034 | 1239888 | 1307800 | 68146 | 0.09 | RA3
8 | PROVIDING & FIXING WATER BAR | Mtr | [8 empty] | 220 | 0 | 0 | 0 | 0 | 0 | RA3
9 | REINFORCEMENT WORK | MT | 46.55 | 46.55 | [5 empty] | 46.55 | 7000 | 325850 | 325850 | 325850 | 0 | 0 | RA3
10 | FLOORING FLOTER FINISH WORK | SQM | 486.78 | 486.78 | [5 empty] | 486.78 | 130 | 63281.4 | 63281.4 | 63281.4 | 0 | 0 | RA3
11 | Pocket Fixing | Nos | 291 | 291 | [5 empty] | 291 | 500 | 145500 | 145500 | 145500 | 0 | 0
* | Total | [5 empty] | 0 | 0 | 0 |  |  | 1972493.5 | 1903187.4 | 1972298.65 | 69306.1 | 8.8818e-15
Abhishek Acharya | [9 empty] | Mukesh Lilhare | [6 empty] | Mahesh Wandre
Billing Engineer | [9 empty] | AGI | [6 empty] | Manager {Civil}
SNPIPL | [16 empty] | SNPIPL

## RA-4
Comparision Chart
Bill Name:- Pipe Mill | [11 empty] | 2023-05-01
Bill No RA 4
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity | Rate | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 | 5.7425 | 5.7425 | 5.74 | 2100 | 12059.25 | 12059.25 | 12054 | 0 | 5.25 | RA 4
2 | Shuttering upto +/- 3meter from GL | m3 | 139.8158 | 139.8158 | 131.18 | 400 | 55926.32 | 55926.32 | 52472 | 0 | 3454.32 | RA 4
3 | Shuttering Cooling Tower | m2 | 127.89 | 127.89 | 127.89 | 550 | 70339.5 | 70339.5 | 70339.5 | 0 | 0 | RA 4
4 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 4
5 | RCC upto +/- 3.00 meter from GL. | m3 | 81.1223 | 81.1223 |  | 2600 | 210917.9826 | 210917.9826 | 0 | 0 | 210917.9826 | RA 4
6 | RCC Cooling Tower | m3 | 19.38 | 19.38 | 19.38 | 3350 | 64923 | 64923 | 64923 | 0 | 0 | RA 4
7 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 4
8 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | MT | 0.47 | 0.47 |  | 7000 | 3290 | 3290 | 0 | 0 | 3290 | RA 4
9 | Reinforcement of steel Cooling Tower | MT | 1.83 | 1.83 |  | 6600 | 12078 | 12078 | 0 | 0 | 12078 | RA 4
10 | Brick Work 0--3 Mtr | m3 | 23.7153 | 23.7153 | 27.5 | 3100 | 73517.43 | 73517.43 | 85250 | 0 | -11732.57 | RA 4
11 | Brick Work 3--6 Mtr | m3 | 3.7855 | 3.7855 | 3.79 | 3410 | 12908.7153 | 12908.7153 | 12923.9 | 0 | -15.1847 | RA 4
12 | Plaster 0--3 Mtr | m2 | 231.06 | 231.06 |  | 160 | 36969.6 | 36969.6 | 0 | 0 | 36969.6 | RA 4
13 | Plaster 3--6 Mtr | m2 | 43.8083 | 43.8083 |  | 176 | 7710.2608 | 7710.2608 | 0 | 0 | 7710.2608 | RA 4
14 | Providing and fixing of PVC water bar 230 | RM | 67.2 | 67.2 | 67.2 | 220 | 14784 | 14784 | 14784 | 0 | 0 | RA 4
15 | Trimix flooring with vaccum dewatering including finishing power trowel | m2 | 865.1555 | 865.1555 | 865.16 | 130 | 112470.215 | 112470.215 | 112470.8 | 0 | -0.585 | RA 4
16 | Skilled Labour Supply-8 Hrs | Rate | 12.625 | 12.625 |  | 500 | 6312.5 | 6312.5 | 0 | 0 | 6312.5 | RA 4
17 | Un-Skilled Labour Supply-8 Hrs | Rate | 48.625 | 48.625 |  | 330 | 16046.25 | 16046.25 | 0 | 0 | 16046.25 | RA 4
18 | RCC Dismantling | m3 | 5.6 | 5.6 | 5.6 | 3000 | 16800 | 16800 | 16800 | 0 | 0 | RA 4
19 | RCC M/S Foundation Grouting work {BY Archon's} | Cum |  |  | 53.62 | 620 | 0 | 0 | 33244.4 | 0 | -33244.4 | RA 5
20 | Plaster Work +3 {BY Archon's} | Sqm |  |  | 43.81 | 242 | 0 | 0 | 10602.02 | 0 | -10602.02 | RA 6
21 | Plaster Work +/-3 {By Archon's} |  |  |  | 274.87 | 220 | 0 | 0 | 60471.4 | 0 | -60471.4 | RA 7
[7 empty] | 727053.0237 | 727053.0237 | 546335.02 | 0 | 180718.0037
Abhishek Acharya |  |  |  |  | Mukesh Lilhare | [6 empty] | Mahesh Wandre
Billing Engineer |  |  |  |  | Site Incharge | [6 empty] | Site Incharge
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd

## RA-5
Comparision Chart
Bill Name:- Pipe Mill | [11 empty] | 2023-07-01
Bill No RA 5
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity | Rate | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 |  |  |  | 2100 | 0 | 0 | 0 | 0 | 0 | RA 5
2 | Shuttering upto +/- 3meter from GL | m3 |  |  |  | 400 | 0 | 0 | 0 | 0 | 0 | RA 5
3 | Shuttering Cooling Tower | m2 |  |  |  | 550 | 0 | 0 | 0 | 0 | 0 | RA 5
4 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 5
5 | RCC upto +/- 3.00 meter from GL. | m3 |  |  |  | 2600 | 0 | 0 | 0 | 0 | 0 | RA 5
6 | RCC Cooling Tower | m3 |  |  |  | 3350 | 0 | 0 | 0 | 0 | 0 | RA 5
7 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 5
8 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | MT |  |  |  | 7000 | 0 | 0 | 0 | 0 | 0 | RA 5
9 | Reinforcement of steel Cooling Tower | MT |  |  |  | 6600 | 0 | 0 | 0 | 0 | 0 | RA 5
10 | Brick Work 0--3 Mtr | m3 |  |  |  | 3100 | 0 | 0 | 0 | 0 | 0 | RA 5
11 | Brick Work 3--6 Mtr | m3 |  |  |  | 3410 | 0 | 0 | 0 | 0 | 0 | RA 5
12 | Plaster 0--3 Mtr | m2 |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | RA 5
13 | Plaster 3--6 Mtr | m2 |  |  |  | 176 | 0 | 0 | 0 | 0 | 0 | RA 5
14 | Providing and fixing of PVC water bar 230 | RM |  |  |  | 220 | 0 | 0 | 0 | 0 | 0 | RA 5
15 | Trimix flooring with vaccum dewatering including finishing power trowel | m2 |  |  |  | 130 | 0 | 0 | 0 | 0 | 0 | RA 5
16 | Skilled Labour Supply-8 Hrs | Rate |  | 3 |  | 500 | 0 | 1500 | 0 | -1500 | 0 | RA 5
16 | Skilled Labour Supply-8 Hrs {Rate Claimed by AGI} | Rate | 4 |  | 4 | 550 | 2200 | 0 | 2200 | 2200 | 0 | RA 5
17 | Un-Skilled Labour Supply-8 Hrs | Rate |  | 1 |  | 330 | 0 | 330 | 0 | -330 | 0 | RA 5
18 | RCC Dismantling | m3 |  |  |  | 3000 | 0 | 0 | 0 | 0 | 0 | RA 5
18 | {Shrikomp} Grouting Work | m3 | 7.775 | 7.2 | 7.77 | 4100 | 31877.5 | 29520 | 31857 | 2357.5 | 20.5 | RA 5
18 | Pressure Grouting | m3 | 92.4 | 92.4 | 92.4 | 620 | 57288 | 57288 | 57288 | 0 | 0 | RA 5
[7 empty] | 91365.5 | 88638 |  | 2727.5 | 20.5
Abhishek Acharya |  |  |  |  | Mukesh Lilhare | [6 empty] | Mahesh Wandre
Billing Engineer |  |  |  |  | Site Incharge | [6 empty] | A.P.M
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd

## RA 6
Comparision Chart
Bill Name:- Pipe Mill | [11 empty] | 2023-08-01
Bill No RA 5
| Item |  | AGI Quantity | Nakoda Quantity | Archons Quantity | Rate | AGI Amount | Nakoda Amount | Archons Amount | Difference Amount |  | Ref
[10 empty] | With Nakoda | With Archons
1 | PCC upto 0.00 to +/- 3.00 meter from GL | m3 |  |  |  | 2100 | 0 | 0 | 0 | 0 | 0 | RA 6
2 | Shuttering upto +/- 3meter from GL | m3 | 1.95 | 1.95 |  | 400 | 780 | 780 | 0 | 0 | 780 | RA 6
3 | Shuttering Cooling Tower | m2 |  |  |  | 550 | 0 | 0 | 0 | 0 | 0 | RA 6
4 | Shuttering upto +/- 3.00 to +/- 6.0 meter from GL | m2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 6
5 | RCC upto +/- 3.00 meter from GL. | m3 | 0.94 | 0.93 |  | 2750 | 2585 | 2557.5 | 0 | 27.5 | 2585 | RA 6
6 | RCC Cooling Tower | m3 |  |  |  | 3350 | 0 | 0 | 0 | 0 | 0 | RA 6
7 | RCC upto +/- 3.00 to +/- 6.00 meter from GL | m3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | RA 6
8 | Reinforcement of steel upto +/- 0.0 to +/- 3.0 meter from ground level. | MT |  |  |  | 7000 | 0 | 0 | 0 | 0 | 0 | RA 6
9 | Reinforcement of steel Cooling Tower | MT |  |  |  | 6600 | 0 | 0 | 0 | 0 | 0 | RA 6
10 | Brick Work 0--3 Mtr | m3 |  |  |  | 3100 | 0 | 0 | 0 | 0 | 0 | RA 6
11 | Brick Work 3--6 Mtr | m3 |  |  |  | 3410 | 0 | 0 | 0 | 0 | 0 | RA 6
12 | Plaster 0--3 Mtr | m2 |  |  |  | 160 | 0 | 0 | 0 | 0 | 0 | RA 6
13 | Plaster 3--6 Mtr | m2 |  |  |  | 176 | 0 | 0 | 0 | 0 | 0 | RA 6
14 | Providing and fixing of PVC water bar 230 | RM |  |  |  | 220 | 0 | 0 | 0 | 0 | 0 | RA 6
15 | Trimix flooring with vaccum dewatering including finishing power trowel | m2 |  |  |  | 130 | 0 | 0 | 0 | 0 | 0 | RA 6
16 | Skilled Labour Supply-8 Hrs | Rate | 12 | 12 |  | 500 | 6000 | 6000 | 0 | 0 | 6000 | RA 6
16 | Skilled Labour Supply-8 Hrs {Rate Claimed by AGI} | Rate |  |  |  | 550 | 0 | 0 | 0 | 0 | 0 | RA 6
17 | Un-Skilled Labour Supply-8 Hrs | Rate | 15 | 15 |  | 330 | 4950 | 4950 | 0 | 0 | 4950 | RA 6
18 | RCC Dismantling | m3 |  |  |  | 3000 | 0 | 0 | 0 | 0 | 0 | RA 6
18 | {Shrikomp} Grouting Work | m3 |  |  |  | 4100 | 0 | 0 | 0 | 0 | 0 | RA 6
18 | Pressure Grouting | m3 |  |  |  | 620 | 0 | 0 | 0 | 0 | 0 | RA 6
[7 empty] | 14315 | 14287.5 |  | 27.5 | 14315
Abhishek Acharya |  |  |  |  | Mukesh Lilhare | [6 empty] | Mahesh Wandre
Billing Engineer |  |  |  |  | Site Incharge | [6 empty] | A.P.M
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | AGI | [6 empty] | Nakoda Pipe Impex Pvt Ltd