## Abstract
To,
The Plant Head | [7 empty] | Subject- Regarding for work details of Bill Measurement
Shree Nakoda Pipe Impex Pvt. Ltd. | [7 empty] | Bill No RA 7
Tilda Industrial Estate (C.G) | [7 empty] | Date July 2023
Sl No |  | DESCRIPTION | Block | Unit | Rate | As per WO |  | Upto Previous Bill |  | This Bill |  | Total Till Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 | 1 | FABRICATIONS | GI 2 | MT | 5700 |  |  | 276.1986 | 1574332.2505 | 55.7766 | 317926.791 | 331.9753 | 1892259.0415
2 | 9 | PAINTING | GI 2 | MT | 1400 |  |  | 214.5149 | 300320.8824 | 28.4053 | 39767.4605 | 242.9202 | 340088.3429
3 | 1 | ERECTION | GI 2 | MT | 3800 |  |  | 256.77 | 975726 | 48.1785 | 183078.2329 | 304.9485 | 1158804.2329
4 | 14 | DISMANTLING | GI 2 | MT | 4200 |  |  | 76.15 | 319830 |  |  | 76.15 | 319830
5 |  | Loading and unloading | GI 2 | MT | 150 |  |  | 2098.16 | 314724 |  | 0 | 2098.16 | 314724
6 | 4/5 | Pipe Work | GI 2 | Inch | 75 |  |  | 10901.7467 | 817631 |  |  | 10901.7467 | 817631
| * | Total | GI 2 | [5 empty] | 4302564.1329 |  | 540772.4845 |  | 4843336.6174
`
Abhisek Acharya | [6 empty] | Siraj Ahmed Ansari | [5 empty] | Bheeshma Verma
Billing engineer | [6 empty] | Arsh Engineering | [5 empty] | Manager {G.I}
Nakoda Pipe Impex Pvt Ltd | [12 empty] | Nakoda Pipe Impex Pvt Ltd

## ABstract Brk Up
To,
The Plant Head
Shree Nakoda Pipe Impex Pvt. Ltd.
Tilda Industrial Estate (C.G)
Subaject- Regarding for work details of RA-7 JULY MANTH 2023 ( G.I. 2 )
Dear Sir,
details of following sheets and their wieght
S.No | DESCRIPTION | 9Mtr Purlin Gi Shed | 9Mtr Tie Beam | G I 9 Mtr Latic | TOTAL IN KGS | TOTAL IN TON | RATE | AMOUNT
1 | FABRICATIONS | 39546.3068 |  | 16230.3232 | 55776.63 | 55.7766 | 5700 | 317926.791
2 | PAINTING | 19773.1534 | 8632.1756 | 0.00 | 28405.329 | 28.4053 | 1400 | 39767.4605
3 | ERECTION | 39546.3068 | 8632.1756 | 0.00 | 48178.4824 | 48.1785 | 3800 | 183078.2329
4 | LOADING & UN LOADING |  |  |  | 0 | 0 | 150 | 0
5 | PIPE WORK
[6 empty] | TOTAL AMOUNT |  | 540772.4845
thanking you
warm regards
FOR
ARSH ENGINEERING SERVICES
(SIRAJ AHMED ANSARI)

## Purlin
SHEE NAKODA GI 9MTS PURLIN ESTIMATE FOR ONE
S.No. |  | DESCRIPTION | DETAIL | NO. | NO. | L | B | H/D | STD.WT. | QUANTITY
1 | Purlin | PURLIN ANGLE | ISA 50X50X6 | 1 | 2 | 8.972 | XX | XX | 4.5 | 80.748
2 | Purlin | PURLIN ANGLE | ISA 50X50X6 | 1 | 1 | 8.327 | XX | XX | 4.5 | 37.4715
3 | Purlin | INCLINED BRACING | 12MM TMT | 3 | 22 | 0.49 | XX | XX | 0.88 | 28.4592
4 | Purlin | PURLIN END PLATE | 8MM TH FLAT | 1 | 2 | 0.33 | 0.065 | 0.008 | 7850 | 2.6941
5 | Purlin | PURLIN STIFFNER PLATE | 8MM TH FLAT | 2 | 2 | 0.07 | 0.04 | 0.008 | 7850 | 0.70336
[9 empty] | TOTAL | 150.0762
6 |  | JOINT ANGLE | ISA 50X50X6 | 1 | 3 | 0.15 | XX | XX | 4.5 | 2.025
[9 empty] | TOTAL SUM | 152.1012
[8 empty] | TOTAL | STES 130 | 19773.1534
|  | WORK DONE | WIEGHT(KGS)
|  | FABRICATION | 39546.3068
|  | PAINTING | 19773.1534
|  | ERECTION | 39546.3068

## Tie Beam
SHREE NAKODA GI SHED 9 MTS TIE BEAM ESTIMATE
S. NO | Structure | DETAILS | ITEMS | Element No | Item No | L | W | H/D | ST. W.T. IN KG/M | QUANTITY IN KG
1 | Tie Beam | TOP GIRDER | ISMB 150 | 1 | 1 | 8.68 | XX | XX | 15 | 130.2
2 | Tie Beam | BOTT. ANGLE | ISA 65X65X6 | 1 | 2 | 8.68 | XX | XX | 5.8 | 100.688
3 | Tie Beam | HALF CUT BRACKET | ISMB 200 | 2 | 2 | 0.3 | XX | XX | 24.2 | 29.04
4 | Tie Beam | INCLINED BRACING | ISA 50X50X6 | 2 | 16 | 0.6 | XX | XX | 4.5 | 86.4
5 | Tie Beam | GUSSET PLATE | 8MM PL | 1 | 2 | 0.129 | 0.094 | 0.008 | 7850 | 1.523
6 | Tie Beam | GUSSET PLATE | 8MM PL | 1 | 10 | 0.187 | 0.107 | 0.008 | 7850 | 12.5657
7 | Tie Beam | GUSSET PLATE | 8MM PL | 1 | 12 | 0.125 | 0.168 | 0.008 | 7850 | 15.8256
8 | Tie Beam | TOP TIE ANGLE | ISA 50X50X6 | 1 | 9 | 1.045 | XX | XX | 4.5 | 42.3225
9 | Tie Beam | JOINT ANGLE | ISA 65X65X6 | 1 | 2 | 0.15 | XX | XX | 5.8 | 1.74
[9 empty] | TOTAL | 420.3048
TOTAL 20 SETS | [9 empty] | 8406.0956
1 |  | JOINT PLATE | 12MM PL | 4 | 16 | 0.5 | 0.075 | 0.012 | 7850 | 226.08
[9 empty] | G. TOTAL | 8632.1756
64
|  | WORK DONE | WIEGHT(KGS)
|  | FABRICATION | 0
|  | PAINTING | 8632.1756
|  | ERECTION | 8632.1756

## Latic Beam
SHREE NAKODA G.I. SHED 9 MTS LATIC ESTIMATE
S. NO | Structure | DETAILS | ITEMS | NO | NO | L | W | H/D | ST.WT.IN KG/M | QUANTITY IN KG
1 | Latic Beam | BOTT. CHANNEL | ISMC 150 | 1 | 1 | 8.68 | XX | XX | 16.8 | 145.824
2 | Latic Beam | TOP CHANNEL | ISMC 150 | 1 | 1 | 8.68 | XX | XX | 16.8 | 145.824
3 | Latic Beam | TOP EXTRA CHANNEL | ISMC 150 | 1 | 2 | 0.5 | XX | XX | 16.8 | 16.8
4 | Latic Beam | BRACKET TOP PLATE | 12MM PL | 1 | 4 | 0.3 | 0.25 | 0.012 | 7850 | 28.26
5 | Latic Beam | HALF CUT BRACKET | ISMB 200 | 1 | 4 | 0.3 | XX | XX | 24.2 | 29.04
6 | Latic Beam | VERTICAL BRACING | ISA 75X75X6 | 2 | 7 | 1.241 | XX | XX | 6.8 | 118.1432
7 | Latic Beam | INCLINED BRACING | ISA 75X75X6 | 2 | 6 | 1.72 | XX | XX | 6.8 | 140.352
[9 empty] | TOTAL | 624.2432
TOTAL 26 SETS | [9 empty] | 16230.3232
|  | WORK DONE | WIEGHT(KGS)
|  | FABRICATION | 16230.3232
|  | PAINTING | 0.00
|  | ERECTION | 0.00