## GI
To Nakoda pipe Impex Pvt Ltd | [14 empty] | Sheet:- Estimate (Mechanical)
Khamariya | [14 empty] | Block :- GI2
Chattissgarh | [14 empty] | Dated:- 14th june 2023
Sl No | Description of work | Structure | Nos | Element | Item | Size | L | B | H | U. Weigh | Total | Nos | Total | Grand Total | Unit | Remarks
1 | Fabrication | Truss | 13 | Bottom Channel | ISMC | 150 | 12.153 |  |  | 16.8 | 204.1704 | 2 | 408.3408 | 5308.4304 | KG | Truss is not as per drawing in site
2 | Fabrication | Truss | 13 | Bottom Channel | ISMC | 150 | 12.95 |  |  | 16.8 | 217.56 | 2 | 435.12 | 5656.56 | KG | Some Technical modfications have been done by H.O.D
3 | Fabrication | Truss | 13 | Top Channel | ISMC | 150 | 12.95 |  |  | 16.8 | 217.56 | 2 | 435.12 | 5656.56 | KG
4 | Fabrication | Truss | 13 | Bottom base Plate | MS Plate | 12 | 0.3 | 0.35 | 0.012 | 7850 | 9.891 | 2 | 19.782 | 257.166 | KG
5 | Fabrication | Truss | 13 | Top Base Plate | MS Plate | 12 | 0.45 | 0.5 | 0.012 | 7850 | 21.195 | 2 | 42.39 | 551.07 | KG
6 | Fabrication | Truss | 13 | Stiffener | MS Plate | 12 | 0.45 | 0.213 | 0.012 | 7850 | 9.0291 | 4 | 36.1163 | 469.5116 | KG
7 | Fabrication | Truss | 13 | Vertical bracing | Angle | 60*60*6 | 1.18 |  |  | 5.42 | 6.3956 | 24 | 153.4944 | 1995.4272 | KG
8 | Fabrication | Truss | 13 | Inclined Bracing | Angle | 75*75*6 | 1.44 |  |  | 6.8 | 9.792 | 8 | 78.336 | 1018.368 | KG
9 | Fabrication | Truss | 13 | Inclined Bracing | Angle | 60*60*6 | 1.451 |  |  | 5.42 | 7.8644 | 22 | 173.0172 | 2249.2241 | KG
10 | Fabrication | Truss | 13 | Inclined Bracing | Angle | 60*60*6 | 1.342 |  |  | 5.42 | 7.2736 | 4 | 29.0946 | 378.2293 | KG
11 | Fabrication | Truss | 13 | Centre Joint Plate | MS Plate | 12 | 1.732 | 0.4 | 0.012 | 7850 | 65.2618 | 2 | 130.5235 | 1696.8058 | KG
12 | Fabrication | Truss | 13 | Monitor top Cannel | ISMC | 150 | 1.831 |  |  | 16.8 | 30.7608 | 2 | 61.5216 | 799.7808 | KG
13 | Fabrication | Truss | 13 | Inclined Bracing | Angle | 60*60*6 | 0.889 |  |  | 5.42 | 4.8184 | 4 | 19.2735 | 250.5558 | KG
14 | Fabrication | Truss | 13 | Inclined Bracing | Angle | 60*60*6 | 0.685 |  |  | 5.42 | 3.7127 | 4 | 14.8508 | 193.0604 | KG
15 | Fabrication | Truss | 13 | Purlin Plate | MS Plate | 8 | 0.09 | 0.33 | 0.008 | 7850 | 1.8652 | 24 | 44.7638 | 581.9299 | KG
16 | Fabrication | Truss | 13 | Purlin Plate | MS Plate | 8 | 0.05 | 0.025 | 0.008 | 7850 | 0.0785 | 96 | 7.536 | 97.968 | KG
17 | Fabrication | Truss | 13 | Truss Centre Support Angle | Angle | 75*75*6 | 7.142 |  |  | 6.8 | 48.5656 | 2 | 97.1312 | 1262.7056 | KG
[13 empty] | 2186.4118 | 28423.3529 | KG
1 | Fabrication | Column | 26 | Base Plate | MS Plate | 25 | 1.15 | 0.55 | 0.025 | 7850 | 124.1281 | 1 | 124.1281 | 3227.3312 | KG
2 | Fabrication | Column | 26 | Long stiffener plate | MS Plate | 12 | 1.15 | 0.3 | 0.012 | 7850 | 32.499 | 2 | 64.998 | 1689.948 | KG
3 | Fabrication | Column | 26 | Short Stiffener Plate | MS Plate | 12 | 0.113 | 0.25 | 0.012 | 7850 | 2.6612 | 6 | 15.9669 | 415.1394 | KG
4 | Fabrication | Column | 26 | Crane Leg | ISMB | 300 | 6.385 |  |  | 46 | 293.71 | 1 | 293.71 | 7636.46 | KG
5 | Fabrication | Column | 26 | Roof Leg | ISMB | 300 | 10.716 |  |  | 46 | 492.936 | 1 | 492.936 | 12816.336 | KG
6 | Fabrication | Column | 26 | Horzontal Bracing | Angle | 60*60*6 | 1.01 |  |  | 5.42 | 5.4742 | 12 | 65.6904 | 1707.9504 | KG
7 | Fabrication | Column | 26 | Inclined Bracing | Angle | 60*60*6 | 1.364 |  |  | 5.42 | 7.3929 | 10 | 73.9288 | 1922.1488 | KG
8 | Fabrication | Column | 26 | Half Cut Bracket | ISMB | 200 | 0.3 |  |  | 24.2 | 7.26 | 8 | 58.08 | 1510.08 | KG
9 | Fabrication | Column | 26 | Tie Beam | ISMB | 200 | 0.892 |  |  | 24.2 | 21.5864 | 1 | 21.5864 | 561.2464 | KG
10 | Fabrication | Column | 26 | Short Stiffener Plate | MS Plate | 12 | 0.146 | 0.2 | 0.012 | 7850 | 2.7506 | 1 | 2.7506 | 71.5166 | KG
11 | Fabrication | Column | 26 | Roof Leg | MS Plate | 12 | 0.2 | 0.3 | 0.012 | 7850 | 5.652 | 1 | 5.652 | 146.952 | KG
12 | Fabrication | Column | 26 | Cleat | Angle | 60*60*6 | 0.25 |  |  | 5.42 | 1.355 | 2 | 2.71 | 70.46 | KG
13 | Fabrication | Column | 26 | Gantry Stiffener Plate | MS Plate | 12 | 1.17 | 0.3 | 0.012 | 7850 | 33.0642 | 2 | 66.1284 | 1719.3384 | KG
14 | Fabrication | Column | 26 | Gantry short Stiffener Plate | MS Plate | 12 | 0.098 | 0.3 | 0.012 | 7850 | 2.7695 | 2 | 5.539 | 144.013 | KG
15 | Fabrication | Column | 26 | Gantry Base Plate | MS Plate | 16 | 0.43 | 0.52 | 0.016 | 7850 | 28.0842 | 1 | 28.0842 | 730.1882 | KG
16 | Fabrication | Column | 26 | Gantry tie plate | MS Plate | 12 | 0.786 | 0.3 | 0.012 | 7850 | 22.2124 | 2 | 44.4247 | 1155.0427 | KG
17 | Fabrication | Column | 26 | Roof Leg | ISMB | 300 | 5.331 |  |  | 46 | 245.226 | 1 | 245.226 | 6375.876 | KG
18 | Fabrication | Column | 26 | Horizontal Bracing | Angle | 60*60*6 | 0.57 |  |  | 5.42 | 3.0894 | 6 | 18.5364 | 481.9464 | KG
19 | Fabrication | Column | 26 | Inclined Bracing | Angle | 60*60*6 | 0.817 |  |  | 5.42 | 4.4281 | 8 | 35.4251 | 921.0531 | KG
20 | Fabrication | Column | 26 | bracket stiffener Plate | MS Plate | 12 | 0.909 | 0.462 | 0.012 | 7850 | 39.56 | 2 | 79.1201 | 2057.1223 | KG
21 | Fabrication | Column | 26 | Bracket top Plate | MS Plate | 12 | 0.3 | 0.35 | 0.012 | 7850 | 9.891 | 1 | 9.891 | 257.166 | KG
22 | Fabrication | Column | 26 | Stiffener plate | MS Plate | 12 | 0.65 | 0.15 | 0.012 | 7850 | 9.1845 | 2 | 18.369 | 477.594 | KG
24 | Fabrication | Column | 26 | Short Stiffener Plate | MS Plate | 12 | 0.88 | 0.15 | 0.012 | 7850 | 12.4344 | 2 | 24.8688 | 646.5888 | KG
25 | Fabrication | Column | 26 | Column Top Plate | MS Plate | 12 | 0.5 | 0.65 | 0.012 | 7850 | 30.615 | 1 | 30.615 | 795.99 | KG
[13 empty] | 1828.3649 | 47537.4877 | KG
Louver 1
20 | Fabrication | Louver | 130 | Gusset | MS Plate | 8 | 0.157 | 0.152 | 0.008 | 7850 | 1.4987 | 2 | 2.9973 | 389.6514 | KG
21 | Fabrication | Louver | 130 | Gusset | MS Plate | 8 | 0.32 | 0.195 | 0.008 | 7850 | 3.9187 | 3 | 11.7562 | 1528.3008 | KG
22 | Fabrication | Louver | 130 | Louver Man Angle | Angle | 50*50*6 | 2.443 |  |  | 4.5 | 10.9935 | 2 | 21.987 | 2858.31 | KG
23 | Fabrication | Louver | 130 | Horizontal Bracing | Angle | 50*50*6 | 0.797 |  |  | 4.5 | 3.5865 | 2 | 7.173 | 932.49 | KG
24 | Fabrication | Louver | 130 | Inclned Bracing | Angle | 50*50*6 | 0.828 |  |  | 4.5 | 3.726 | 2 | 7.452 | 968.76 | KG
25 | Fabrication | Louver | 130 | Horizontal Bracing | Angle | 50*50*6 | 0.448 |  |  | 4.5 | 2.016 | 2 | 4.032 | 524.16 | KG
26 | Fabrication | Louver | 130 | Gusset | MS Plate | 8 | 0.333 | 0.294 | 0.008 | 7850 | 6.1482 | 1 | 6.1482 | 799.2719 | KG
27 | Fabrication | Louver | 130 | Gusset | MS Plate | 8 | 0.15 | 0.101 | 0.008 | 7850 | 0.95142 | 1 | 0.95142 | 123.6846 | KG
[13 empty] | 62.4971 | 8124.6287 | KG
1 | Fabrication | Crane Gantry | 26 | Gantry Bottom Base | Ms Plate | 16 | 0.308 | 0.43 | 0.016 | 7850 | 16.6345 | 2 | 33.2689 | 864.9921 | KG
2 | Fabrication | Crane Gantry | 26 | Top Channel | ISMC | 300 | 8.972 |  |  | 36.3 | 325.6836 | 1 | 325.6836 | 8467.7736 | KG
3 | Fabrication | Crane Gantry | 26 | Girder | ISMB | 600 | 8.972 |  |  | 122.6 | 1099.9672 | 1 | 1099.9672 | 28599.1472 | KG
4 | Fabrication | Crane Gantry | 26 | End Plate | MS Plate | 12 | 0.608 | 0.43 | 0.012 | 7850 | 24.6276 | 2 | 49.2553 | 1280.6377 | KG
5 | Fabrication | Crane Gantry | 26 | Vertical bracing | Angle | 75*75*6 | 0.4 |  |  | 6.8 | 2.72 | 4 | 10.88 | 282.88 | KG
5A | Fabrication | Crane Gantry | 26 | Web Stiffener plate | MS Plate | 12 | 0.3 | 0.21 | 0.012 | 7850 | 5.9346 | 2 | 11.8692 | 308.5992 | KG
5B | Fabrication | Crane Gantry | 26 | Web Stiffener plate | MS Plate | 12 | 0.6 | 0.1 | 0.012 | 7850 | 5.652 | 2 | 11.304 | 293.904 | KG
6 | Fabrication | Crane Gantry | 26 | Web Stiffener plate | MS Plate | 10 | 0.6 | 0.1 | 0.01 | 7850 | 4.71 | 22 | 103.62 | 2694.12 | KG
7 | Fabrication | Crane Gantry | 26 | Bottom Channel | ISMC | 150 | 8.68 |  |  | 16.8 | 145.824 | 2 | 291.648 | 7582.848 | KG
8 | Fabrication | Crane Gantry | 26 | Inclined Bracing | Angle | 75*75*6 | 0.718 |  |  | 6.8 | 4.8824 | 24 | 117.1776 | 3046.6176 | KG
9 | Fabrication | Crane Gantry | 26 | Gusset | MS Plate | 8 | 0.2 | 0.1 | 0.008 | 7850 | 1.256 | 2 | 2.512 | 65.312 | KG
10 | Fabrication | Crane Gantry | 26 | Gusset | MS Plate | 8 | 0.235 | 0.1 | 0.008 | 7850 | 1.4758 | 6 | 8.8548 | 230.2248 | KG
11 | Fabrication | Crane Gantry | 26 | Gusset | MS Plate | 8 | 0.3 | 0.275 | 0.008 | 7850 | 5.181 | 7 | 36.267 | 942.942 | KG
12 | Fabrication | Crane Gantry | 26 | Half Cut Bracket | ISMB | 200 | 0.3 |  |  | 25.4 | 7.62 | 2 | 15.24 | 396.24 | KG
13 | Fabrication | Crane Gantry | 26 | Bracket Top Plate | MS Plate | 12 | 0.3 | 0.25 | 0.012 | 7850 | 7.065 | 2 | 14.13 | 367.38 | KG
14 | Fabrication | Crane Gantry | 26 | Inclined Bracing | Angle | 75*75*6 | 0.849 |  |  | 6.8 | 5.7732 | 4 | 23.0928 | 600.4128 | KG
15 | Fabrication | Crane Gantry | 26 | Top and Bottom horizontal Bracing | Angle | 50*50*6 | 0..94 |  |  | 4.5 | 4.5 | 18 | 81 | 2106 | KG
16 | Fabrication | Crane Gantry | 26 | Top and Bottom Inclined Bracing | Angle | 50*50*6 | 1.47 |  |  | 4.5 | 6.615 | 16 | 105.84 | 2751.84 | KG |  | Diagonal Size Issue not same as mentioned in drawing (8.58) Mtrs According to Dwg, Site Measurement is 8.68
[11 empty] | 0 |  | 2341.6104 | 60881.871
1 | Fabrication | Gable Beam | 2 | Bottom Channel | ISMC | 150 | 25.04 |  |  | 16.8 | 420.672 | 2 | 841.344 | 1682.688
2 | Fabrication | Gable Beam | 2 | Bottom extra Channel | ISMC | 150 | 5 |  |  | 16.8 | 84 | 4 | 336 | 672
3 | Fabrication | Gable Beam | 2 | Top Channel | ISMC | 150 | 25.04 |  |  | 16.8 | 420.672 | 2 | 841.344 | 1682.688
4 | Fabrication | Gable Beam | 2 | Top extra Channel | ISMC | 150 | 5 |  |  | 16.8 | 84 | 4 | 336 | 672
5 | Fabrication | Gable Beam | 2 | Vertrical bracing | ISA | 60*60*6 | 0.98 |  |  | 5.42 | 5.3116 | 16 | 84.9856 | 169.9712
6 | Fabrication | Gable Beam | 2 | Inclined Bracng | ISA | 60*60*6 | 1.278 |  |  | 5.42 | 6.9268 | 16 | 110.8282 | 221.6563
7 | Fabrication | Gable Beam | 2 | Vertical bracing | ISA | 60*60*6 | 0.98 |  |  | 5.42 | 5.3116 | 30 | 159.348 | 318.696
8 | Fabrication | Gable Beam | 2 | Inclined Bracing | ISA | 60*60*6 | 1.337 |  |  | 5.42 | 7.2465 | 28 | 202.9031 | 405.8062
9 | Fabrication | Gable Beam | 2 | Base Plate | MS Plate | 12 | 0.4 | 0.65 | 0.1 | 7850 | 204.1 | 2 | 408.2 | 816.4
10 | Fabrication | Gable Beam | 2 | Horizontal bracing | ISA | 50*50*6 | 0.62 |  |  | 4.5 | 2.79 | 57 | 159.03 | 318.06
11 | Fabrication | Gable Beam | 2 | Inclined Bracing | ISA | 50*50*6 | 0.91 |  |  | 4.5 | 4.095 | 55 | 225.225 | 450.45
[11 empty] | 0 |  | 3705.2079 | 7410.4158
1 | Fabrication | Tie Beam (9 Mtrs) | 52 | Top Girder | ISMB | 150 | 8.58 |  |  | 14.9 | 127.842 | 1 | 127.842 | 6647.784 |  | RA 4 52 PC Claimed
2 | Fabrication | Tie Beam (9 Mtrs) | 52 | bottom Girder | ISA | 60*60*6 | 8.58 |  |  | 5.42 | 46.5036 | 2 | 93.0072 | 4836.3744 |  | Erection Claim 20PC RSA7
3 | Fabrication | Tie Beam (9 Mtrs) | 52 | half Cut Angle | ISMB | 200 | 0.3 |  |  | 24.2 | 7.26 | 4 | 29.04 | 1510.08 |  | Erection Claim 18PC RSA8
4 | Fabrication | Tie Beam (9 Mtrs) | 52 | Inclined Bracing | ISA | 50*50*6 | 0.592 |  |  | 4.5 | 2.664 | 32 | 85.248 | 4432.896 |  | Erection Claim 13 PC RA 6
5 | Fabrication | Tie Beam (9 Mtrs) | 52 | Gusset | MS Plate | 8 | 0.129 | 0.094 | 0.008 | 7850 | 0.76151 | 2 | 1.523 | 79.1973
6 | Fabrication | Tie Beam (9 Mtrs) | 52 | Gusset | MS Plate | 8 | 0.187 | 0.107 | 0.008 | 7850 | 1.2566 | 20 | 25.1313 | 1306.8278
7 | Fabrication | Tie Beam (9 Mtrs) | 52 | Gusset | MS Plate | 8 | 0.168 | 0.125 | 0.008 | 7850 | 1.3188 | 12 | 15.8256 | 822.9312
8 | Fabrication | Tie Beam (9 Mtrs) | 52 | Top Tie angle | ISA | 50*50*6 | 1.045 |  |  | 4.5 | 4.7025 | 9 | 42.3225 | 2200.77
[11 empty] | 0 |  | 419.9396 | 21836.8607
1 | Fabrication | Bracings | 2 | Bracing For Support | ISMC | 100 | 4.7768 |  |  | 9.6 | 45.8573 | 4 | 183.4291 | 366.8582
2 | Fabrication | Bracings | 2 | Bracing For Support | ISMC | 100 | 8.8278 |  |  | 9.6 | 84.7469 | 4 | 338.9875 | 677.975
3 | Fabrication | Bracings | 2 | Bracing For Support | ISMC | 100 | 25.04 |  |  | 9.6 | 240.384 | 6 | 1442.304 | 2884.608
4 | Fabrication | Bracings | 2 | Bracing For Support | ISMC | 101 | 11.3997 |  |  | 9.6 | 109.4371 | 1 | 109.4371 | 218.8742
5 | Fabrication | Bracings | 2 | Bracing For Support | ISMB | 200 | 7.366 |  |  | 24.2 | 178.2572 | 2 | 356.5144 | 713.0288
6 | Fabrication | Bracings | 2 | Bracing For Support | ISMB | 200 | 8.04 |  |  | 24.2 | 194.568 | 1 | 194.568 | 389.136
[11 empty] | 0 |  | 2625.2402 | 5250.4803 | KG
1 | Fabrication | Purlin | 520 | Purlin Angle | ISA | 50*50*6 | 8.972 |  |  | 4.5 | 40.374 | 2 | 80.748 | 41988.96 |  | RA 4 200 Pc
2 | Fabrication | Purlin | 520 | Purlin Angle | ISA | 50*50*6 | 8.327 |  |  | 4.5 | 37.4715 | 1 | 37.4715 | 19485.18 |  | RA 6 150 Pc
3 | Fabrication | Purlin | 520 | Inclined Bracing | TMT | 12 | 0.49 |  |  | 0.888 | 0.43512 | 66 | 28.7179 | 14933.3184 |  | RA 7 130
4 | Fabrication | Purlin | 520 | Purlin End Plate | Ms Plate | 8 | 0.33 | 0.07 | 0.008 | 7850 | 1.4507 | 2 | 2.9014 | 1508.7072 |  | RA 8 36 PC
5 | Fabrication | Purlin | 520 | Purlin Stiffner Plate | Ms Plate | 8 | 0.07 | 0.04 | 0.008 | 7850 | 0.17584 | 4 | 0.70336 | 365.7472
[11 empty] | 0 |  | 150.5421 | 78281.9128 | KG
Latic Beam 26 PC settled in GI RA 07
[16 empty] | SHREE NAKODA D. I. DALA ESTIMATE | Extra Work From Drawing
18
19
20
21
22
23
24
25
26
27
28
29 | [15 empty] | 14352
30
113
114
115

## GI Abstract
Block GI 2
Estimated Value Mechanical
Sl No | Block | Description | Truss | Column & Louver | Crane Gantry & latic | Gable Beam | Latic beam | Bracing | Purlin | Total | Rate | Amount
1 | GI 2 | Fabrication | 28.4234 | 55.6621 | 60.8819 | 7.4104 | 21.8369 | 5.2505 | 78.2819 | 257.747 | 5700 | 1469157.9568
2 | GI 2 | Erection | 28.4234 | 55.6621 | 60.8819 | 7.4104 | 21.8369 | 5.2505 | 78.2819 | 257.747 | 3800 | 979438.6378
3 | GI 2 | Painting | 28.4234 | 55.6621 | 60.8819 | 7.4104 | 21.8369 | 5.2505 | 78.2819 | 257.747 | 1400 | 360845.8139
4 | GI 2 | Dismantling
5 | GI 2 | Loading & Unloading
6 | GI 2 | Sheeting
7 | GI 2 | Pipe Work
2809442.4086
GI-2
[10 empty] | Jan | RA 1 | 36.623
[10 empty] | Feb | RA 2 | 15.86
[10 empty] | Mar | RA 3 | 31.37
[10 empty] | Apr | RA 4 | 52.64
[10 empty] | May | RA 5
[10 empty] | Jun | RA 6 | 22.863
[10 empty] | Jul | RA 7 | 36.223
195.579

## Comaparision
Sl No | Item | Block | As per Dwg |  |  | As Per Site |  |  | Difference
|  |  | Quantity | Nos | Total | Quantity | Nos | Total | Quantity | Nos | Total
1 | Truss | GI-2 | 2186.4118 | 13 | 28423.3529 | 2413.4596 | 13 | 31374.9742 | 227.0478 | 0 | 0
2 | Column | GI-2 | 1828.3649 | 26 | 47537.4877 | 1831.18 | 26 | 47610.68 | 2.8151 | 0 | 0
3 | Louver | GI-2 | 62.4971 | 130 | 8124.6287 | 62.5 | 130 | 8125 | 0.002856 | 0 | 0
4 | Crane Gantry | GI-2 | 2341.6104 | 26 | 60881.871 |  | 26 | 0 | -2341.6104 | 0 | 0
5 | Gable Beam | GI-2 | 3705.2079 | 1 | 3705.2079 |  | 1 | 0 | -3705.2079 | 0 | 0
6 | Latic Tie beam | GI-2 | 419.9396 | 52 | 21836.8607 | 421.7448 | 52 | 21930.7284 | 1.8051 | 0 | 0
7 | Bracing | GI-2 | 2625.2402 | 2 | 5250.4803 |  | 2 | 0 | -2625.2402 | 0 | 0
8 | Purlin | GI-2 | 150.5421 | 520 | 78281.9128 | 152.4246 | 479 | 73011.3738 | 1.8824 | -41 | -77.18
* | Total |  |  |  | 254041.8021 |  |  | 182052.7564 |  |  | -77.18

## Ferro
To Nakoda pipe Impex Pvt Ltd | [14 empty] | Sheet:- Estimate (Mechanical)
Khamariya | [14 empty] | Block :- Ferro
Chattissgarh | [14 empty] | Dated:- 14th june 2023
Sl No | Description of work | Structure | Nos | Item | Size | Length | Width | Depth | Unit Weight | Total | Nos | Total weight | Unit | Grand Total | Unit
1 | Fabrication | Column A1/A6 | 2 | MS Plate | 25 | 0.75 | 0.6 | 0.025 | 7850 | 88.3125 | 1 | 88.3125 | KG | 176.625 | KG
2 | Fabrication | Column A1/A6 | 2 | MS Plate | 12 | 0.75 | 0.4 | 0.012 | 7850 | 28.26 | 2 | 56.52 | KG | 113.04 | KG
3 | Fabrication | Column A1/A6 | 2 | MS Plate | 25 | 0.75 | 0.138 | 0.025 | 7850 | 20.3119 | 2 | 40.6238 | KG | 81.2475 | KG
4 | Fabrication | Column A1/A6 | 2 | MS Plate | 12 | 0.2 | 0.138 | 0.012 | 7850 | 2.5999 | 12 | 31.199 | KG | 62.3981 | KG
5 | Fabrication | Column A1/A6 | 2 | ISMB | 300 | 28.458 |  |  | 46 | 1309.068 | 2 | 2618.136 | KG | 5236.272 | KG
6 | Fabrication | Column A1/A6 | 2 | ISA | 65*65*6 | 105.675 |  |  | 5.93 | 626.6527 | 1 | 626.6527 | KG | 1253.3055 | KG
7 | Fabrication | Column A1/A6 | 2 | MS Plate | 12 | 0.32 | 0.579 | 0.012 | 7850 | 17.4534 | 1 | 17.4534 | KG | 34.9068 | KG
8 | Fabrication | Column A1/A6 | 2 | MS Plate | 12 | 0.23 | 0.42 | 0.012 | 7850 | 9.0997 | 1 | 9.0997 | KG | 18.1994 | KG
9 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.1 | 0.36 | 0.01 | 7850 | 2.826 | 2 | 5.652 | KG | 11.304 | KG
10 | Fabrication | Column A1/A6 | 2 | MS Plate | 16 | 0.59 | 0.635 | 0.016 | 7850 | 47.056 | 3 | 141.1681 | KG | 282.3362 | KG
11 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.59 | 0.785 | 0.01 | 7850 | 36.3573 | 1 | 36.3573 | KG | 72.7146 | KG
12 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.2 | 0.3 | 0.01 | 7850 | 4.71 | 7 | 32.97 | KG | 65.94 | KG
13 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.2 | 0.3 | 0.01 | 7850 | 4.71 | 7 | 32.97 | KG | 65.94 | KG
14 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.25 | 0.4 | 0.01 | 7850 | 7.85 | 1 | 7.85 | KG | 15.7 | KG
15 | Fabrication | Column A1/A6 | 2 | MS Plate | 10 | 0.25 | 0.4 | 0.01 | 7850 | 7.85 | 1 | 7.85 | KG | 15.7 | KG
16 | Fabrication | Column A1/A6 | 2 | ISMB | 200 | 0.25 |  |  | 24.2 | 6.05 | 7 | 42.35 | KG | 84.7 | KG
17 | Fabrication | Column A1/A6 | 2 | ISMB | 300 | 0.35 |  |  | 46 | 16.1 | 1 | 16.1 | KG | 32.2 | KG
[12 empty] | 3811.2645 | KG | 7622.5291 | KG | 4006.1295 | 194.865
1 | Fabrication | Column A2/A3 | 2 | Ms Plate | 25 | 0.4 | 0.75 | 0.025 | 7850 | 58.875 | 1 | 58.875 | KG | 117.75 | KG
2 | Fabrication | Column A2/A3 | 2 | Ms Plate | 12 | 0.4 | 0.75 | 0.012 | 7850 | 28.26 | 2 | 56.52 | KG | 113.04 | KG
3 | Fabrication | Column A2/A3 | 2 | Ms Plate | 25 | 0.138 | 0.75 | 0.025 | 7850 | 20.3119 | 2 | 40.6238 | KG | 81.2475 | KG
4 | Fabrication | Column A2/A3 | 2 | Ms Plate | 12 | 0.138 | 0.2 | 0.012 | 7850 | 2.5999 | 12 | 31.199 | KG | 62.3981 | KG
5 | Fabrication | Column A2/A3 | 2 | ISMB | 300 | 28.458 |  |  | 46 | 1309.068 | 2 | 2618.136 | KG | 5236.272 | KG
6 | Fabrication | Column A2/A3 | 2 | ISA | 65*65*6 | 105.675 |  |  | 5.93 | 626.6527 | 1 | 626.6527 | KG | 1253.3055 | KG
7 | Fabrication | Column A2/A3 | 2 | Ms Plate | 12 | 0.32 | 0.579 | 0.012 | 7850 | 17.4534 | 1 | 17.4534 | KG | 34.9068 | KG
8 | Fabrication | Column A2/A3 | 2 | Ms Plate | 12 | 0.23 | 0.42 | 0.012 | 7850 | 9.0997 | 1 | 9.0997 | KG | 18.1994 | KG
9 | Fabrication | Column A2/A3 | 2 | Ms Plate | 10 | 0.1 | 0.36 | 0.01 | 7850 | 2.826 | 2 | 5.652 | KG | 11.304 | KG
10 | Fabrication | Column A2/A3 | 2 | Ms Plate | 16 | 0.59 | 0.585 | 0.016 | 7850 | 43.3508 | 4 | 173.4034 | KG | 346.8067 | KG
11 | Fabrication | Column A2/A3 | 2 | Ms Plate | 16 | 0.59 | 0.635 | 0.016 | 7850 | 47.056 | 2 | 94.1121 | KG | 188.2242 | KG
12 | Fabrication | Column A2/A3 | 2 | Ms Plate | 10 | 0.2 | 0.3 | 0.01 | 7850 | 4.71 | 9 | 42.39 | KG | 84.78 | KG
13 | Fabrication | Column A2/A3 | 2 | Ms Plate | 10 | 0.2 | 0.3 | 0.01 | 7850 | 4.71 | 9 | 42.39 | KG | 84.78 | KG
14 | Fabrication | Column A2/A3 | 2 | Ms Plate | 10 | 0.25 | 0.4 | 0.01 | 7850 | 7.85 | 3 | 23.55 | KG | 47.1 | KG
15 | Fabrication | Column A2/A3 | 2 | Ms Plate | 10 | 0.25 | 0.4 | 0.01 | 7850 | 7.85 | 3 | 23.55 | KG | 47.1 | KG
16 | Fabrication | Column A2/A3 | 2 | ISMB | 200 | 0.25 |  |  | 24.2 | 6.05 | 9 | 54.45 | KG | 108.9 | KG
17 | Fabrication | Column A2/A3 | 2 | ISMB | 300 | 0.35 |  |  | 46 | 16.1 | 3 | 48.3 | KG | 96.6 | KG
18 | Fabrication | Column A2/A3 | 2 | Ms Plate | 16 | 0.59 | 0.835 | 0.016 | 7850 | 61.8768 | 2 | 123.7537 | KG | 247.5074 | KG
[12 empty] | 4090.1108 | KG | 8180.2215 | KG
Louver 1
20 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
21 | Fabrication | [8 empty] | 0 | 3 | 0 | KG | 0 | KG
22 | Fabrication | [9 empty] | 2 | 2 | KG | 0 | KG
23 | Fabrication | [9 empty] | 2 | 2 | KG | 0 | KG
24 | Fabrication | [9 empty] | 2 | 2 | KG | 0 | KG
25 | Fabrication | [9 empty] | 2 | 2 | KG | 0 | KG
26 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0 | KG
27 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0 | KG
[12 empty] | 8 | KG | 0 | KG
1 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
2 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0 | KG
3 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0 | KG
4 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
5 | Fabrication | [8 empty] | 0 | 4 | 0 | KG | 0 | KG
5A | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
5B | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
6 | Fabrication | [8 empty] | 0 | 22 | 0 | KG | 0 | KG
7 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
8 | Fabrication | [8 empty] | 0 | 24 | 0 | KG | 0 | KG
9 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
10 | Fabrication | [8 empty] | 0 | 6 | 0 | KG | 0 | KG
11 | Fabrication | [8 empty] | 0 | 7 | 0 | KG | 0 | KG
12 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
13 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
14 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0 | KG
15 | Fabrication | [8 empty] | 0 | 18 | 0 | KG | 0 | KG
16 | Fabrication | [8 empty] | 0 | 16 | 0 | KG | 0 | KG
[10 empty] | 0 |  | 0 | KG | 0
1 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
2 | Fabrication | [8 empty] | 0 | 4 | 0 | KG | 0
3 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
4 | Fabrication | [8 empty] | 0 | 4 | 0 |  | 0
5 | Fabrication | [8 empty] | 0 | 16 | 0 | KG | 0
6 | Fabrication | [8 empty] | 0 | 16 | 0 | KG | 0
7 | Fabrication | [8 empty] | 0 | 30 | 0 | KG | 0
8 | Fabrication | [8 empty] | 0 | 28 | 0 | KG | 0
9 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
10 | Fabrication | [8 empty] | 0 | 57 | 0 | KG | 0
11 | Fabrication | [8 empty] | 0 | 55 | 0 | KG | 0
[10 empty] | 0 |  | 0 | KG | 0
1 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0
2 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
3 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
4 | Fabrication | [8 empty] | 0 | 32 | 0 | KG | 0
5 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
6 | Fabrication | [8 empty] | 0 | 20 | 0 | KG | 0
7 | Fabrication | [8 empty] | 0 | 12 | 0 | KG | 0
8 | Fabrication | [8 empty] | 0 | 9 | 0 | KG | 0
[10 empty] | 0 |  | 0 | KG | 0
1 | Fabrication | [8 empty] | 0 | 4 | 0 | KG | 0
2 | Fabrication | [8 empty] | 0 | 4 | 0 | KG | 0
3 | Fabrication | [8 empty] | 0 | 6 | 0 | KG | 0
4 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0
5 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
6 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0
[10 empty] | 0 |  | 0 | KG | 0 | KG
1 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
2 | Fabrication | [8 empty] | 0 | 1 | 0 | KG | 0
3 | Fabrication | [8 empty] | 0 | 66 | 0 | KG | 0
4 | Fabrication | [8 empty] | 0 | 2 | 0 | KG | 0
5 | Fabrication | [8 empty] | 0 | 4 | 0 | KG | 0
[10 empty] | 0 |  | 0 | KG | 0 | KG

## Ferro Abstract
11949.6

## Payment Follow up
To | [15 empty] | Vendor:-Siraj Fabrications
Nakoda Pipe Impex Pvt Ltd | [15 empty] | Bill Follow Up sheet
Sl no | Block | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | Total | Estimated Value | Remaining balance
1 | GI-2 | 2023-01-01: 1417028.25; 2023-02-01: 451256.5; 2023-03-01: 510016.4; 2023-04-01: 563702.7329; 2023-05-01: 402959.73; 2023-06-01: 957586.25 | 4302549.8629 | 2786919.647 | -1515630.2159
2 | GI-2
3 | GI-2
4 | GI-2
5 | GI-2
Note:-
In The Estimated Value the following has not been considered
1) | Loading & unloading
2) | Dismantling
3) | Sheeting works