## RA 2
Bill Name:- Chimney
Bill No:- RA 2 (July 2023)
SHREE NAKODA PIPE IMPEX Ltd TILDA Summary of ( PSB ) RA-03
S.no | DESCRIPTION | Unit | AQUAPLAST QTY. | NAKODA QTY. | ARCHCONS QTY. | Rate | AQUAPLAST Amount | NAKODA Amount | ARCHCONS Amount | DIFFERENCE Amount |  | Ref
[10 empty] | WITH ARCHCONS | WITH NAKODA
Civil Work
1 | Completion Percentage | N/A | 15% | 12% |  | 4400000 | 660000 | 528000 | 0 | 660000 | 132000 | RA2
[7 empty] | 660000 | 528000 | 0 | 660000 | 132000 | RA2
Note: | The Deduction of the amount is due to the deduction percentage of mobilization advance
Percentage of civil work completion is valid as per the claimed bill
The difference amount should be calculated upto 880000 given to aquaplast as mobilisation advance
Abhishek Acharya |  |  |  |  | Mahesh Wandre | [6 empty] | Sudhakar Rao
Billing Engineer |  |  |  |  | Assistant Project manager | [6 empty] | Generel manager {Power plant}
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | Nakoda Pipe Impex Pvt Ltd | [6 empty] | Nakoda Pipe Impex Pvt Ltd

## RA 3
Bill Name:- Chimney
Bill No:- RA 3 (August 2023)
SHREE NAKODA PIPE IMPEX Ltd TILDA Summary of ( PSB ) RA-03
S.no | DESCRIPTION | Unit | AQUAPLAST QTY. | NAKODA QTY. | ARCHCONS QTY. | Rate | AQUAPLAST Amount | NAKODA Amount | ARCHCONS Amount | DIFFERENCE Amount |  | Ref
[10 empty] | WITH ARCHCONS | WITH NAKODA
Civil Work
1 | Completion Percentage | N/A | 12.5% | 10% |  | 4400000 | 550000 | 440000 | 0 | 550000 | 110000 | RA2
[7 empty] | 550000 | 440000 | 0 | 550000 | 110000 | RA2
Note: | The Deduction of the amount is due to the deduction percentage of mobilization advance
Percentage of civil work completion is valid as per the claimed bill
The difference amount shoul be calculated upto 880000 given to aquaplast as mobilisation advance
Abhishek Acharya |  |  |  |  | Mahesh Wandre | [6 empty] | Sudhakar Rao
Billing Engineer |  |  |  |  | Assistant Project manager | [6 empty] | Generel manager {Power plant}
Nakoda Pipe Impex Pvt Ltd |  |  |  |  | Nakoda Pipe Impex Pvt Ltd | [6 empty] | Nakoda Pipe Impex Pvt Ltd