## RA -1
To | [10 empty] | RA 1
Nakoda Pipe Impex Pvt Ltd | [10 empty] | 2023-06-01
Sl No | Item No | Description | UOM | Rate | Block | Upto Prev Bill |  | This Bill |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthworks
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all (0-3)Mtr | m3 | 180 | TG Building | 0 | 0 | 4104.84 | 738871.2 | 4104.84 | 738871.2
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all (3-6)Mtr | m3 | 220 | TG Building | 0 | 0 | 1900.5409 | 418119.0024 | 1900.5409 | 418119.0024
3 |  | Soil Dressing | m3 | 25 | TG Building | 0 | 0 | 601.01 | 15025.25 | 601.01 | 15025.25
4 |  | Hard rock Excavation 3-6 Mtrs | m3 | 1150 | TG Building | 0 | 0 | 834.9 | 960135 | 834.9 | 960135
5 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 |  | TG Building | 0 | 0 |  | 0 | 0 | 0
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2599 | TG Building | 0 | 0 | 35.771 | 92968.829 | 35.771 | 92968.829
7 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 3190 | TG Building | 0 | 0 | 0.642 | 2047.98 | 0.642 | 2047.98
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3604.7 | TG Building | 0 | 0 | 105.33 | 379683.051 | 105.33 | 379683.051
9 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 580 | TG Building | 0 | 0 | 4.812 | 2790.96 | 4.812 | 2790.96
10 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M-+/-6mtrs. | M2 | 655.4 | TG Building | 0 | 0 | 174.653 | 114467.5762 | 174.653 | 114467.5762
11 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | TG Building | 0 | 0 | 0.024 | 216 | 0.024 | 216
12 | 40 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete(3-6Mtr) | Nos | 10170 | TG Building | 0 |  | 7.884 | 80180.28 | 7.884 | 80180.28
[7 empty] | 0 |  | 2804505.1286 |  | 2804505.1286

## RA 2
To | [10 empty] | RA 2
Nakoda Pipe Impex Pvt Ltd | [10 empty] | 2023-07-01
Block: TG Building
Sl No | Item No | Description | UOM | Rate | Block | Upto Prev Bill |  | This Bill |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthworks
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all (0-3)Mtr | m3 | 180 | TG Building | 4104.84 | 738871.2 |  | 0 | 4104.84 | 738871.2
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 500 Mtr including all (3-6)Mtr | m3 | 220 | TG Building | 1900.5409 | 418119.0024 |  | 0 | 1900.5409 | 418119.0024
3 |  | Soil Dressing | m3 | 25 | TG Building | 601.01 | 15025.25 |  | 0 | 601.01 | 15025.25
4 |  | Hard rock Excavation 3-6 Mtrs | m3 | 1150 | TG Building | 834.9 | 960135 |  | 0 | 834.9 | 960135
5 |  | Sand Bedding | m3 | 1180 | TG Building |  |  | 47.96 | 56592.8
6 |  | Backfilling | m3 | 80 | TG Building |  |  | 1829.12 | 146329.6 | 1829.12 | 146329.6
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | TG Building | 0 | 0 |  | 0 | 0 | 0
8 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2599 | TG Building | 35.771 | 92968.829 | 10.291 | 26746.309 | 46.062 | 119715.138
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 3190 | TG Building | 0.642 | 2047.98 | 11.768 | 37539.92 | 12.41 | 39587.9
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3604.7 | TG Building | 105.33 | 379683.051 | 312.8168 | 1127610.719 | 418.1468 | 1507293.77
11 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 580 | TG Building | 4.812 | 2790.96 | 88.486 | 51321.88 | 93.298 | 54112.84
12 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M-+/-6mtrs. | M2 | 655.4 | TG Building | 174.653 | 114467.5762 | 400.885 | 262740.029 | 575.538 | 377207.6052
13 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | TG Building | 0.024 | 216 | 6.211 | 55899 | 6.235 | 56115
14 | 40 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete(3-6Mtr) | Nos | 10170 | TG Building | 7.884 | 80180.28 | 24.5 | 249165 | 32.384 | 329345.28
[7 empty] | 2804505.1286 |  | 2013945.257 |  | 4761857.5856
2013945.257

## RA 2 measurement
To | [11 empty] | RA 2
Nakoda Pipe Impex Pvt Ltd | [11 empty] | TG Building
Sl No | Description | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed in
|  |  |  | From | To
1 | Reinforced Cement Concrete
1.1 | RCC 3--6 Mtrs | F1 |  | 91 | 91.5 | 3 | 2.6 | 0.5 | 1 | 3.9 | Cum | RA 2
1.2 | RCC 3--6 Mtrs | F2 |  | 91 | 91.6 | 3.4 | 3 | 0.6 | 1 | 6.12 | Cum | RA 2
1.3 | RCC 3--6 Mtrs | F3 |  | 91 | 91.4 | 1.8 | 1.8 | 0.4 | 7 | 9.072 | Cum | RA 2
1.4 | RCC 3--6 Mtrs | F4 |  | 91 | 91.5 | 2.5 | 2.5 | 0.5 | 1 | 3.125 | Cum | RA 2
1.5 | RCC 3--6 Mtrs | F5 |  | 91 | 91.6 | 3.3 | 3.5 | 0.6 | 1 | 6.93 | Cum | RA 2
1.6 | RCC 3--6 Mtrs | F6 |  | 91 | 91.7 | 3.7 | 3.4 | 0.7 | 4 | 35.224 | Cum | RA 2
1.7 | RCC 3--6 Mtrs | F7 |  | 91 | 91.75 | 4.1 | 3.6 | 0.75 | 2 | 22.14 | Cum | RA 2
1.8 | RCC 3--6 Mtrs | F9 |  | 91 | 91.75 | 5.15 | 3.8 | 0.75 | 1 | 14.6775 | Cum | RA 2
1.9 | RCC 3--6 Mtrs | F10 |  | 91 | 91.95 | 5.45 | 2.6 | 0.95 | 1 | 13.4615 | Cum | RA 2
1.1 | RCC 3--6 Mtrs | F12 | N/A |  |  | 3 | 1.7 | 0.5 | 2 | 5.1 | Cum | RA 2
1.11 | RCC 3--6 Mtrs | C1 |  | 91.6 | 93.54 | 0.8 | 0.4 | 1.94 | 3 | 1.8624 | Cum | RA 2
1.12 | RCC 3--6 Mtrs | C2 |  | 91.7 | 93.54 | 0.8 | 0.5 | 1.84 | 5 | 3.68 | Cum | RA 2
1.13 | RCC 3--6 Mtrs | C2A |  | 91.7 | 93.54 | 0.8 | 0.5 | 1.84 |  | 0.736 | Cum | RA 2
1.14 | RCC 3--6 Mtrs | C3 |  | 91.9 | 93.54 | 1 | 0.5 | 1.64 | 2 | 1.64 | Cum | RA 2
1.15 | RCC 3--6 Mtrs | C3A |  | 91.75 | 93.54 | 1 | 0.5 | 1.79 | 2 | 1.79 | Cum | RA 2
1.16 | RCC 3--6 Mtrs | C4 |  | 91.4 | 93.54 | 0.4 | 0.4 | 2.14 | 12 | 4.1088 | Cum | RA 2
1.17 | RCC 3--6 Mtrs | C5 |  | 91.5 | 93.54 | 0.4 | 0.4 | 2.04 | 4 | 1.3056 | Cum | RA 2
1.18 | RCC 3--6 Mtrs | [10 empty] | RA 2
1.19 | RCC 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 | 12.5 | 7 | 0.5 | 1 | 43.75 | Cum | RA 2
1.2 | RCC 3--6 Mtrs | TG raft |  | 93.54 | 95.04 | 12.5 | 7 | 1.5 | 1 | 131.25 | Cum | RA 2
1 | Total 3 - 6 Mtrs | [8 empty] | 309.8728 | Cum
2.1 | RCC 0--3 MTRS | C1 |  | 93.54 | 99.54 | 0.8 | 0.4 | 6 | 7 | 13.44 | Cum | RA 2
2.2 | RCC 0--3 MTRS |  | (-) Deduction from RA 1 | [6 empty] | 0.642 |  | RA 2
2.3 | RCC 0--3 MTRS | [8 empty] | 12.798 |  | RA 2
2.4 | RCC 0--3 MTRS | C2 |  | 93.54 | 94.656 | 0.8 | 0.5 | 1.116 | 5 | 2.232 | Cum | RA 2 {5 Nos upto 1.116 Mtr Hieght}
2.5 | RCC 0--3 MTRS | C2A |  | 93.54 | 94.656 | 0.8 | 0.5 | 1.116 | 5 | 2.232 | Cum | RA 2 {5 Nos upto 1.116 Mtr Hieght}
2.6 | RCC 0--3 MTRS | C3 |  | 93.54 | 94.656 | 1 | 0.5 | 1.116 | 2 | 1.116 | Cum | RA 2 {2Nos upto 1.116 Mtr Hieght}
2.7 | RCC 0--3 MTRS | C3A |  | 93.54 | 94.656 | 1 | 0.5 | 1.116 | 2 | 1.116 | Cum | RA 2 {2Nos upto 1.116 Mtr Hieght}
2.8 | RCC 0--3 MTRS | C4 |  | 93.54 | 94.656 | 0.4 | 0.4 | 1.116 | 11 | 1.9642 | Cum | RA 2 {11 Nos upto 1.116 Mtr Hieght}
2.9 | RCC 0--3 MTRS | C5 |  | 93.54 | 94.656 | 0.4 | 0.4 | 1.116 | 3 | 0.53568 | Cum | RA 2 {3 Nos upto 1.116 Mtr Hieght}
2 | RCC 0--3 MTRS | [8 empty] | 21.9938 | Cum
3 | Shuttering
3.1 | Shuttering 3--6 Mtrs | F1 |  | 91 | 91.5 | 3 |  | 0.5 | 2 | 3 | Sqm | RA 2
3.2 | Shuttering 3--6 Mtrs | F2 |  | 91 | 91.6 | 3.4 |  | 0.6 | 2 | 4.08 | Sqm | RA 2
3.3 | Shuttering 3--6 Mtrs | F3 |  | 91 | 91.4 | 1.8 |  | 0.4 | 14 | 10.08 | Sqm | RA 2
3.4 | Shuttering 3--6 Mtrs | F4 |  | 91 | 91.5 | 2.5 |  | 0.5 | 2 | 2.5 | Sqm | RA 2
3.5 | Shuttering 3--6 Mtrs | F5 |  | 91 | 91.6 | 3.3 |  | 0.6 | 2 | 3.96 | Sqm | RA 2
3.6 | Shuttering 3--6 Mtrs | F6 |  | 91 | 91.7 | 3.7 |  | 0.7 | 8 | 20.72 | Sqm | RA 2
3.7 | Shuttering 3--6 Mtrs | F7 |  | 91 | 91.75 | 4.1 |  | 0.75 | 4 | 12.3 | Sqm | RA 2
3.8 | Shuttering 3--6 Mtrs | F9 |  | 91 | 91.75 | 5.15 |  | 0.75 | 2 | 7.725 | Sqm | RA 2
3.9 | Shuttering 3--6 Mtrs | F10 |  | 91 | 91.95 | 5.45 |  | 0.95 | 2 | 10.355 | Sqm | RA 2
3.1 | Shuttering 3--6 Mtrs | F12 | N/A |  |  | 3 |  | 0.5 | 4 | 6 | Sqm
3.11 | Shuttering 3--6 Mtrs | C1 |  | 91.6 | 93.54 | 0.8 |  | 1.94 | 6 | 9.312 | Sqm | RA 2
3.12 | Shuttering 3--6 Mtrs | C2 |  | 91.7 | 93.54 | 0.8 |  | 1.84 | 10 | 14.72 | Sqm | RA 2
3.13 | Shuttering 3--6 Mtrs | C2A |  | 91.7 | 93.54 | 0.8 |  | 1.84 | 10 | 14.72 | Sqm | RA 2
3.14 | Shuttering 3--6 Mtrs | C3 |  | 91.9 | 93.54 | 1 |  | 1.64 | 4 | 6.56 | Sqm | RA 2
3.15 | Shuttering 3--6 Mtrs | C3A |  | 91.75 | 93.54 | 1 |  | 1.79 | 4 | 7.16 | Sqm | RA 2
3.16 | Shuttering 3--6 Mtrs | C4 |  | 91.4 | 93.54 | 0.4 |  | 2.14 | 24 | 20.544 | Sqm | RA 2
3.17 | Shuttering 3--6 Mtrs | C5 |  | 91.5 | 93.54 | 0.4 |  | 2.04 | 8 | 6.528 | Sqm | RA 2
3.18 | Shuttering 3--6 Mtrs
3.19 | Shuttering 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 | 12.5 |  | 2 | 2 | 50 | Sqm | RA 2
3.2 | Shuttering 3--6 Mtrs
3.21 | Shuttering 3--6 Mtrs | F1 |  | 91 | 91.5 |  | 2.6 | 0.5 | 2 | 2.6 | Sqm | RA 2
3.22 | Shuttering 3--6 Mtrs | F2 |  | 91 | 91.6 |  | 3 | 0.6 | 2 | 3.6 | Sqm | RA 2
3.23 | Shuttering 3--6 Mtrs | F3 |  | 91 | 91.4 |  | 1.8 | 0.4 | 14 | 10.08 | Sqm | RA 2
3.24 | Shuttering 3--6 Mtrs | F4 |  | 91 | 91.5 |  | 2.5 | 0.5 | 2 | 2.5 | Sqm | RA 2
3.25 | Shuttering 3--6 Mtrs | F5 |  | 91 | 91.6 |  | 3.5 | 0.6 | 2 | 4.2 | Sqm | RA 2
3.26 | Shuttering 3--6 Mtrs | F6 |  | 91 | 91.7 |  | 3.4 | 0.7 | 8 | 19.04 | Sqm | RA 2
3.27 | Shuttering 3--6 Mtrs | F7 |  | 91 | 91.75 |  | 3.6 | 0.75 | 4 | 10.8 | Sqm | RA 2
3.28 | Shuttering 3--6 Mtrs | F9 |  | 91 | 91.75 |  | 3.8 | 0.75 | 2 | 5.7 | Sqm | RA 2
3.29 | Shuttering 3--6 Mtrs | F10 |  | 91 | 91.95 |  | 2.6 | 0.95 | 2 | 4.94 | Sqm | RA 2
3.3 | Shuttering 3--6 Mtrs | F12 | N/A |  |  |  | 1.7 | 0.5 | 4 | 3.4 | Sqm
3.31 | Shuttering 3--6 Mtrs | C1 |  | 91.6 | 93.54 |  | 0.4 | 1.94 | 6 | 4.656 | Sqm | RA 2
3.32 | Shuttering 3--6 Mtrs | C2 |  | 91.7 | 93.54 |  | 0.5 | 1.84 | 10 | 9.2 | Sqm | RA 2
3.33 | Shuttering 3--6 Mtrs | C2A |  | 91.7 | 93.54 |  | 0.5 | 1.84 | 10 | 9.2 | Sqm | RA 2
3.34 | Shuttering 3--6 Mtrs | C3 |  | 91.9 | 93.54 |  | 0.5 | 1.64 | 4 | 3.28 | Sqm | RA 2
3.35 | Shuttering 3--6 Mtrs | C3A |  | 91.75 | 93.54 |  | 0.5 | 1.79 | 4 | 3.58 | Sqm | RA 2
3.36 | Shuttering 3--6 Mtrs | C4 |  | 91.4 | 93.54 |  | 0.4 | 2.14 | 24 | 20.544 | Sqm | RA 2
3.37 | Shuttering 3--6 Mtrs | C5 |  | 91.5 | 93.54 |  | 0.4 | 2.04 | 8 | 6.528 | Sqm | RA 2
3.38 | Shuttering 3--6 Mtrs
3.39 | Shuttering 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 |  | 7 | 2 | 2 | 43.75 | Sqm | RA 2
4 | Total 3 - 6 Mtrs | [8 empty] | 377.862 | Sqm | RA 2
4.1 | Shuttering 0--3 MTRS | C1 |  | 93.54 | 99.54 | 0.8 |  | 5.7134 | 14 | 63.99 | Sqm | RA 2
4.2 | Shuttering 0--3 MTRS | C2 |  | 93.54 | 94.656 | 0.8 |  | 1.116 | 10 | 8.928 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.3 | Shuttering 0--3 MTRS | C2A |  | 93.54 | 94.656 | 0.8 |  | 1.116 | 10 | 8.928 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.4 | Shuttering 0--3 MTRS | C3 |  | 93.54 | 94.656 | 1 |  | 1.116 | 4 | 4.464 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.5 | Shuttering 0--3 MTRS | C3A |  | 93.54 | 94.656 | 1 |  | 1.116 | 4 | 4.464 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.6 | Shuttering 0--3 MTRS | C4 |  | 93.54 | 94.656 | 0.4 |  | 1.116 | 22 | 9.8208 | Sqm | RA 2 {11 Nos upto 1.116 Mtr Hieght}
4.7 | Shuttering 0--3 MTRS | C5 |  | 93.54 | 94.656 | 0.4 |  | 1.116 | 6 | 2.6784 | Sqm | RA 2 {3 Nos upto 1.116 Mtr Hieght}
4.9 | Shuttering 0--3 MTRS | C1 |  | 93.54 | 99.54 |  | 0.4 | 5.7134 | 14 | 31.995 | Sqm | RA 2
4.1 | Shuttering 0--3 MTRS | C2 |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 10 | 5.58 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.11 | Shuttering 0--3 MTRS | C2A |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 10 | 5.58 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.12 | Shuttering 0--3 MTRS | C3 |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 4 | 2.232 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.13 | Shuttering 0--3 MTRS | C3A |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 4 | 2.232 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.14 | Shuttering 0--3 MTRS | C4 |  | 93.54 | 94.656 |  | 0.4 | 1.116 | 22 | 9.8208 | Sqm | RA 2 {11 Nos upto 1.116 Mtr Hieght}
4.15 | Shuttering 0--3 MTRS | C5 |  | 93.54 | 94.656 |  | 0.4 | 1.116 | 6 | 2.6784 | Sqm | RA 2 {3 Nos upto 1.116 Mtr Hieght}
| Shuttering 0--3 MTRS | [8 empty] | 163.3914 | Sqm | RA 2

## RA 2 Measurement New
To | [11 empty] | RA 2
Nakoda Pipe Impex Pvt Ltd | [11 empty] | TG Building
Sl No | Description | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed in
|  |  |  | From | To
1 | Reinforced Cement Concrete
1.1 | RCC 3--6 Mtrs | F1 |  | 91 | 91.5 | 3 | 2.6 | 0.5 | 1 | 3.9 | Cum | RA 2
1.2 | RCC 3--6 Mtrs | F2 |  | 91 | 91.6 | 3.4 | 3 | 0.6 | 1 | 6.12 | Cum | RA 2
1.3 | RCC 3--6 Mtrs | F3 |  | 91 | 91.4 | 1.8 | 1.8 | 0.4 | 7 | 9.072 | Cum | RA 2
1.4 | RCC 3--6 Mtrs | F4 |  | 91 | 91.5 | 2.5 | 2.5 | 0.5 | 1 | 3.125 | Cum | RA 2
1.5 | RCC 3--6 Mtrs | F5 |  | 91 | 91.6 | 3.3 | 3.5 | 0.6 | 1 | 6.93 | Cum | RA 2
1.6 | RCC 3--6 Mtrs | F6 |  | 91 | 91.7 | 3.7 | 3.4 | 0.7 | 4 | 35.224 | Cum | RA 2
1.7 | RCC 3--6 Mtrs | F7 |  | 91 | 91.75 | 4.1 | 3.6 | 0.75 | 2 | 22.14 | Cum | RA 2
1.8 | RCC 3--6 Mtrs | F9 |  | 91 | 91.75 | 5.15 | 3.8 | 0.75 | 1 | 14.6775 | Cum | RA 2
1.9 | RCC 3--6 Mtrs | F10 |  | 91 | 91.95 | 5.45 | 2.6 | 0.95 | 1 | 13.4615 | Cum | RA 2
1.1 | RCC 3--6 Mtrs | F12 | N/A |  |  | 3 | 1.7 | 0.5 | 2 | 5.1 | Cum | RA 2
1.11 | RCC 3--6 Mtrs | C1 |  | 91.6 | 93.54 | 0.8 | 0.4 | 1.94 | 3 | 1.8624 | Cum | RA 2
1.12 | RCC 3--6 Mtrs | C2 |  | 91.7 | 93.54 | 0.8 | 0.5 | 1.84 | 5 | 3.68 | Cum | RA 2
1.13 | RCC 3--6 Mtrs | C2A |  | 91.7 | 93.54 | 0.8 | 0.5 | 1.84 |  | 0.736 | Cum | RA 2
1.14 | RCC 3--6 Mtrs | C3 |  | 91.9 | 93.54 | 1 | 0.5 | 1.64 | 2 | 1.64 | Cum | RA 2
1.15 | RCC 3--6 Mtrs | C3A |  | 91.75 | 93.54 | 1 | 0.5 | 1.79 | 2 | 1.79 | Cum | RA 2
1.16 | RCC 3--6 Mtrs | C4 |  | 91.4 | 93.54 | 0.4 | 0.4 | 2.14 | 12 | 4.1088 | Cum | RA 2
1.17 | RCC 3--6 Mtrs | C5 |  | 91.5 | 93.54 | 0.4 | 0.4 | 2.04 | 4 | 1.3056 | Cum | RA 2
1.18 | RCC 3--6 Mtrs | [10 empty] | RA 2
1.19 | RCC 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 | 12.5 | 7 | 0.5 | 1 | 43.75 | Cum | RA 2
1.2 | RCC 3--6 Mtrs | TG raft |  | 93.54 | 95.04 | 12.5 | 7 | 1.5 | 1 | 131.25 | Cum | RA 2
1 | Total 3 - 6 Mtrs | [8 empty] | 309.8728 | Cum
2.1 | RCC 0--3 MTRS | C1 |  | 93.54 | 99.54 | 0.8 | 0.4 | 6 | 7 | 13.44 | Cum | RA 2
2.2 | RCC 0--3 MTRS |  | (-) Deduction from RA 1 | [6 empty] | 0.642 |  | RA 2
2.3 | RCC 0--3 MTRS | [8 empty] | 12.798 |  | RA 2
2.4 | RCC 0--3 MTRS | C2 |  | 93.54 | 94.656 | 0.8 | 0.5 | 1.116 | 5 | 2.232 | Cum | RA 2 {5 Nos upto 1.116 Mtr Hieght}
2.5 | RCC 0--3 MTRS | C2A |  | 93.54 | 94.656 | 0.8 | 0.5 | 1.116 | 5 | 2.232 | Cum | RA 2 {5 Nos upto 1.116 Mtr Hieght}
2.6 | RCC 0--3 MTRS | C3 |  | 93.54 | 94.656 | 1 | 0.5 | 1.116 | 2 | 1.116 | Cum | RA 2 {2Nos upto 1.116 Mtr Hieght}
2.7 | RCC 0--3 MTRS | C3A |  | 93.54 | 94.656 | 1 | 0.5 | 1.116 | 2 | 1.116 | Cum | RA 2 {2Nos upto 1.116 Mtr Hieght}
2.8 | RCC 0--3 MTRS | C4 |  | 93.54 | 94.656 | 0.4 | 0.4 | 1.116 | 11 | 1.9642 | Cum | RA 2 {11 Nos upto 1.116 Mtr Hieght}
2.9 | RCC 0--3 MTRS | C5 |  | 93.54 | 94.656 | 0.4 | 0.4 | 1.116 | 3 | 0.53568 | Cum | RA 2 {3 Nos upto 1.116 Mtr Hieght}
2 | RCC 0--3 MTRS | [8 empty] | 21.9938 | Cum
3 | Shuttering
3.1 | Shuttering 3--6 Mtrs | F1 |  | 91 | 91.5 | 3 |  | 0.5 | 2 | 3 | Sqm | RA 2
3.2 | Shuttering 3--6 Mtrs | F2 |  | 91 | 91.6 | 3.4 |  | 0.6 | 2 | 4.08 | Sqm | RA 2
3.3 | Shuttering 3--6 Mtrs | F3 |  | 91 | 91.4 | 1.8 |  | 0.4 | 14 | 10.08 | Sqm | RA 2
3.4 | Shuttering 3--6 Mtrs | F4 |  | 91 | 91.5 | 2.5 |  | 0.5 | 2 | 2.5 | Sqm | RA 2
3.5 | Shuttering 3--6 Mtrs | F5 |  | 91 | 91.6 | 3.3 |  | 0.6 | 2 | 3.96 | Sqm | RA 2
3.6 | Shuttering 3--6 Mtrs | F6 |  | 91 | 91.7 | 3.7 |  | 0.7 | 8 | 20.72 | Sqm | RA 2
3.7 | Shuttering 3--6 Mtrs | F7 |  | 91 | 91.75 | 4.1 |  | 0.75 | 4 | 12.3 | Sqm | RA 2
3.8 | Shuttering 3--6 Mtrs | F9 |  | 91 | 91.75 | 5.15 |  | 0.75 | 2 | 7.725 | Sqm | RA 2
3.9 | Shuttering 3--6 Mtrs | F10 |  | 91 | 91.95 | 5.45 |  | 0.95 | 2 | 10.355 | Sqm | RA 2
3.1 | Shuttering 3--6 Mtrs | F12 | N/A |  |  | 3 |  | 0.5 | 4 | 6 | Sqm
3.11 | Shuttering 3--6 Mtrs | C1 |  | 91.6 | 93.54 | 0.8 |  | 1.94 | 6 | 9.312 | Sqm | RA 2
3.12 | Shuttering 3--6 Mtrs | C2 |  | 91.7 | 93.54 | 0.8 |  | 1.84 | 10 | 14.72 | Sqm | RA 2
3.13 | Shuttering 3--6 Mtrs | C2A |  | 91.7 | 93.54 | 0.8 |  | 1.84 | 10 | 14.72 | Sqm | RA 2
3.14 | Shuttering 3--6 Mtrs | C3 |  | 91.9 | 93.54 | 1 |  | 1.64 | 4 | 6.56 | Sqm | RA 2
3.15 | Shuttering 3--6 Mtrs | C3A |  | 91.75 | 93.54 | 1 |  | 1.79 | 4 | 7.16 | Sqm | RA 2
3.16 | Shuttering 3--6 Mtrs | C4 |  | 91.4 | 93.54 | 0.4 |  | 2.14 | 24 | 20.544 | Sqm | RA 2
3.17 | Shuttering 3--6 Mtrs | C5 |  | 91.5 | 93.54 | 0.4 |  | 2.04 | 8 | 6.528 | Sqm | RA 2
3.18 | Shuttering 3--6 Mtrs
3.19 | Shuttering 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 | 12.5 |  | 2 | 2 | 50 | Sqm | RA 2
3.2 | Shuttering 3--6 Mtrs
3.21 | Shuttering 3--6 Mtrs | F1 |  | 91 | 91.5 |  | 2.6 | 0.5 | 2 | 2.6 | Sqm | RA 2
3.22 | Shuttering 3--6 Mtrs | F2 |  | 91 | 91.6 |  | 3 | 0.6 | 2 | 3.6 | Sqm | RA 2
3.23 | Shuttering 3--6 Mtrs | F3 |  | 91 | 91.4 |  | 1.8 | 0.4 | 14 | 10.08 | Sqm | RA 2
3.24 | Shuttering 3--6 Mtrs | F4 |  | 91 | 91.5 |  | 2.5 | 0.5 | 2 | 2.5 | Sqm | RA 2
3.25 | Shuttering 3--6 Mtrs | F5 |  | 91 | 91.6 |  | 3.5 | 0.6 | 2 | 4.2 | Sqm | RA 2
3.26 | Shuttering 3--6 Mtrs | F6 |  | 91 | 91.7 |  | 3.4 | 0.7 | 8 | 19.04 | Sqm | RA 2
3.27 | Shuttering 3--6 Mtrs | F7 |  | 91 | 91.75 |  | 3.6 | 0.75 | 4 | 10.8 | Sqm | RA 2
3.28 | Shuttering 3--6 Mtrs | F9 |  | 91 | 91.75 |  | 3.8 | 0.75 | 2 | 5.7 | Sqm | RA 2
3.29 | Shuttering 3--6 Mtrs | F10 |  | 91 | 91.95 |  | 2.6 | 0.95 | 2 | 4.94 | Sqm | RA 2
3.3 | Shuttering 3--6 Mtrs | F12 | N/A |  |  |  | 1.7 | 0.5 | 4 | 3.4 | Sqm
3.31 | Shuttering 3--6 Mtrs | C1 |  | 91.6 | 93.54 |  | 0.4 | 1.94 | 6 | 4.656 | Sqm | RA 2
3.32 | Shuttering 3--6 Mtrs | C2 |  | 91.7 | 93.54 |  | 0.5 | 1.84 | 10 | 9.2 | Sqm | RA 2
3.33 | Shuttering 3--6 Mtrs | C2A |  | 91.7 | 93.54 |  | 0.5 | 1.84 | 10 | 9.2 | Sqm | RA 2
3.34 | Shuttering 3--6 Mtrs | C3 |  | 91.9 | 93.54 |  | 0.5 | 1.64 | 4 | 3.28 | Sqm | RA 2
3.35 | Shuttering 3--6 Mtrs | C3A |  | 91.75 | 93.54 |  | 0.5 | 1.79 | 4 | 3.58 | Sqm | RA 2
3.36 | Shuttering 3--6 Mtrs | C4 |  | 91.4 | 93.54 |  | 0.4 | 2.14 | 24 | 20.544 | Sqm | RA 2
3.37 | Shuttering 3--6 Mtrs | C5 |  | 91.5 | 93.54 |  | 0.4 | 2.04 | 8 | 6.528 | Sqm | RA 2
3.38 | Shuttering 3--6 Mtrs
3.39 | Shuttering 3--6 Mtrs | TG Raft |  | 93.04 | 93.54 |  | 7 | 2 | 2 | 43.75 | Sqm | RA 2
4 | Total 3 - 6 Mtrs | [8 empty] | 377.862 | Sqm | RA 2
4.1 | Shuttering 0--3 MTRS | C1 |  | 93.54 | 99.54 | 0.8 |  | 5.7134 | 14 | 63.99 | Sqm | RA 2
4.2 | Shuttering 0--3 MTRS | C2 |  | 93.54 | 94.656 | 0.8 |  | 1.116 | 10 | 8.928 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.3 | Shuttering 0--3 MTRS | C2A |  | 93.54 | 94.656 | 0.8 |  | 1.116 | 10 | 8.928 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.4 | Shuttering 0--3 MTRS | C3 |  | 93.54 | 94.656 | 1 |  | 1.116 | 4 | 4.464 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.5 | Shuttering 0--3 MTRS | C3A |  | 93.54 | 94.656 | 1 |  | 1.116 | 4 | 4.464 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.6 | Shuttering 0--3 MTRS | C4 |  | 93.54 | 94.656 | 0.4 |  | 1.116 | 22 | 9.8208 | Sqm | RA 2 {11 Nos upto 1.116 Mtr Hieght}
4.7 | Shuttering 0--3 MTRS | C5 |  | 93.54 | 94.656 | 0.4 |  | 1.116 | 6 | 2.6784 | Sqm | RA 2 {3 Nos upto 1.116 Mtr Hieght}
4.9 | Shuttering 0--3 MTRS | C1 |  | 93.54 | 99.54 |  | 0.4 | 5.7134 | 14 | 31.995 | Sqm | RA 2
4.1 | Shuttering 0--3 MTRS | C2 |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 10 | 5.58 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.11 | Shuttering 0--3 MTRS | C2A |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 10 | 5.58 | Sqm | RA 2 {5 Nos upto 1.116 Mtr Hieght}
4.12 | Shuttering 0--3 MTRS | C3 |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 4 | 2.232 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.13 | Shuttering 0--3 MTRS | C3A |  | 93.54 | 94.656 |  | 0.5 | 1.116 | 4 | 2.232 | Sqm | RA 2 {2Nos upto 1.116 Mtr Hieght}
4.14 | Shuttering 0--3 MTRS | C4 |  | 93.54 | 94.656 |  | 0.4 | 1.116 | 22 | 9.8208 | Sqm | RA 2 {11 Nos upto 1.116 Mtr Hieght}
4.15 | Shuttering 0--3 MTRS | C5 |  | 93.54 | 94.656 |  | 0.4 | 1.116 | 6 | 2.6784 | Sqm | RA 2 {3 Nos upto 1.116 Mtr Hieght}
| Shuttering 0--3 MTRS | [8 empty] | 163.3914 | Sqm | RA 2
3.1 | Shuttering PCC | F1 |  | 91 | 91.5 | 3 |  | 0.1 | 2 | 0.6 | Sqm | RA 2
3.2 | Shuttering PCC | F2 |  | 91 | 91.6 | 3.4 |  | 0.1 | 2 | 0.68 | Sqm | RA 2
3.3 | Shuttering PCC | F3 |  | 91 | 91.4 | 1.8 |  | 0.1 | 14 | 2.52 | Sqm | RA 2
3.4 | Shuttering PCC | F4 |  | 91 | 91.5 | 2.5 |  | 0.1 | 2 | 0.5 | Sqm | RA 2
3.5 | Shuttering PCC | F5 |  | 91 | 91.6 | 3.3 |  | 0.1 | 2 | 0.66 | Sqm | RA 2
3.6 | Shuttering PCC | F6 |  | 91 | 91.7 | 3.7 |  | 0.1 | 8 | 2.96 | Sqm | RA 2
3.7 | Shuttering PCC | F7 |  | 91 | 91.75 | 4.1 |  | 0.1 | 4 | 1.64 | Sqm | RA 2
3.8 | Shuttering PCC | F9 |  | 91 | 91.75 | 5.15 |  | 0.1 | 2 | 1.03 | Sqm | RA 2
3.9 | Shuttering PCC | F10 |  | 91 | 91.95 | 5.45 |  | 0.1 | 2 | 1.09 | Sqm | RA 2
3.1 | Shuttering PCC | F12 | N/A |  |  | 3 |  | 0.1 | 4 | 1.2 | Sqm
3.1 | Shuttering PCC | F1 |  | 91 | 91.5 | 3 |  | 0.1 | 2 | 0.6 | Sqm | RA 2
3.2 | Shuttering PCC | F2 |  | 91 | 91.6 | 3.4 |  | 0.1 | 2 | 0.68 | Sqm | RA 2
3.3 | Shuttering PCC | F3 |  | 91 | 91.4 | 1.8 |  | 0.1 | 14 | 2.52 | Sqm | RA 2
3.4 | Shuttering PCC | F4 |  | 91 | 91.5 | 2.5 |  | 0.1 | 2 | 0.5 | Sqm | RA 2
3.5 | Shuttering PCC | F5 |  | 91 | 91.6 | 3.3 |  | 0.1 | 2 | 0.66 | Sqm | RA 2
3.6 | Shuttering PCC | F6 |  | 91 | 91.7 | 3.7 |  | 0.1 | 8 | 2.96 | Sqm | RA 2
3.7 | Shuttering PCC | F7 |  | 91 | 91.75 | 4.1 |  | 0.1 | 4 | 1.64 | Sqm | RA 2
3.8 | Shuttering PCC | F9 |  | 91 | 91.75 | 5.15 |  | 0.1 | 2 | 1.03 | Sqm | RA 2
3.9 | Shuttering PCC | F10 |  | 91 | 91.95 | 5.45 |  | 0.1 | 2 | 1.09 | Sqm | RA 2
3.1 | Shuttering PCC | F12 | N/A |  |  | 3 |  | 0.1 | 4 | 1.2 | Sqm
| Shuttering PCC | [8 empty] | 25.76 | Sqm | RA 2