## RA 1
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev bill | This Bill | Total
Excavation
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 |  | ACC
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 |  | ACC
3 |  | Soil Dressing | m2 |  | ACC
4 |  | Hard Rock breaking 0-3 | m3 |  | ACC
5 |  | Hard Rock breaking 3-6 | m3 |  | ACC
6 |  | Hard Rock breaking 6-9 | m3 |  | ACC
7 |  | Backfilling | m3 |  | ACC
8 |  | Sand Filling | m3 |  | ACC
9 |  | Aggregate filling | m3 |  | ACC
10 |  | Rock Soling | m3 |  | ACC
Concrete
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 |  | ACC
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 |  | ACC
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 |  | ACC
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 |  | ACC
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 |  | ACC
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 |  | ACC
Shuttering
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 |  | ACC
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 |  | ACC
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 |  | ACC
Re- In forcements
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT |  | ACC
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT |  | ACC
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT |  | ACC
21 |  | Fabrication & Fixing of insert Plates |  |  | ACC
|  | JigS & Fixture | MT |  | ACC
|  | Fixing of Foundation bolts 32 mm Dia & Above |  |  | ACC

## RA 1 Measurement
A C C
S.no. | Description | Reduced Level |  | Stucture | Mkd | No | L | B | H | Qty | Unit | Remark |  | 3.07
|  | From | To
Excavtion 0--3Mtr
|  |  |  | Foundation |  | 1 | 26.17 | 60 | 1.8 | 2826.36 | cum | JMR Not Rcved
|  |  |  | Foundation |  | 2 | 5.8 | 5.8 | 1.2 | 80.736 | cum | JMR Not Rcved
|  |  |  | Foundation | F2&F3 | 1 | 10 | 7.6 | 1.2 | 91.2 | cum | JMR Not Rcved
|  |  |  | Foundation | F2 | 1 | 7 | 6.8 | 1.2 | 57.12 | cum | JMR Not Rcved
|  |  |  | Foundation | F4 | 5 | 7.2 | 7.2 | 1.2 | 311.04 | cum | JMR Not Rcved
|  |  |  | Foundation | F5 | 4 | 7.6 | 7.6 | 1.2 | 277.248 | cum | JMR Not Rcved
[9 empty] | TOTAL | 3643.704 | cum
Excavtion 3--6Mtr
|  |  |  | Foundation |  | 2 | 3.8 | 3.8 | 2.2 | 63.536 | cum | JMR Not Rcved
|  |  |  | Foundation | F2&F3 | 1 | 8 | 5.6 | 2.2 | 98.56 | cum | JMR Not Rcved
|  |  |  | Foundation | F2 | 1 | 5 | 4.8 | 2.2 | 52.8 | cum | JMR Not Rcved
|  |  |  | Foundation | F4 | 5 | 5.25 | 5.2 | 2.2 | 300.3 | cum | JMR Not Rcved
|  |  |  | Foundation | F5 | 4 | 5.6 | 5.6 | 2.2 | 275.968 | cum | JMR Not Rcved
[10 empty] | 0 |  | JMR Not Rcved
[9 empty] | TOTAL | 791.164 | cum
DRESING 3-6MTR
|  |  |  | Foundation | F1 | 2 | 2.6 | 2.6 |  | 13.52 | Sqm | JMR Not Rcved
|  |  |  | Foundation | F2 | 2 | 3.8 | 3.6 |  | 27.36 | Sqm | JMR Not Rcved
|  |  |  | Foundation | F3 | 1 | 4.4 | 3.8 |  | 16.72 | Sqm | JMR Not Rcved
|  |  |  | Foundation | F4 | 5 | 4 | 4 |  | 80 | Sqm | JMR Not Rcved
|  |  |  | Foundation | F5 | 4 | 4.4 | 4.4 |  | 77.44 | Sqm | JMR Not Rcved
[9 empty] | TOTAL | 215.04 | Sqm
Dressing 0 --3MTR
| BEAM | [8 empty] | 0 |  | JMR Not Rcved
| PB1 A |  |  | Foundation |  | 1 | 46.81 | 0.65 |  | 30.4265 |  | JMR Not Rcved
| PB1 B |  |  | Foundation |  | 1 | 36.81 | 0.65 |  | 23.9265 |  | JMR Not Rcved
| PB1 1' |  |  | Foundation |  | 1 | 6.45 | 0.65 |  | 4.1925 |  | JMR Not Rcved
| PB1 1" |  |  | Foundation |  | 1 | 12.45 | 0.65 |  | 8.0925 |  | JMR Not Rcved
| B1 |  |  | Foundation |  | 1 | 3 | 0.65 |  | 1.95 |  | JMR Not Rcved
| PB2 (4,3,2) |  |  | Foundation |  | 3 | 12.97 | 0.65 |  | 25.2915 |  | JMR Not Rcved
| B" |  |  | Foundation |  | 1 | 3 | 0.65 |  | 1.95 |  | JMR Not Rcved
[9 empty] | TOTAL | 95.8295 |  |  |  | 1
SAND filling 3--6 Mtr
| F1 |  |  | Foundation |  | 2 | 2.4 | 2.4 | 0.1 | 1.152 | Cum | JMR Not Rcved
| F2 |  |  | Foundation |  | 2 | 3.6 | 3.4 | 0.1 | 2.448 | Cum | JMR Not Rcved
| F3 |  |  | Foundation |  | 1 | 4.2 | 3.6 | 0.1 | 1.512 | Cum | JMR Not Rcved
| F4 |  |  | Foundation |  | 5 | 3.8 | 3.8 | 0.1 | 7.22 | Cum | JMR Not Rcved
| F5 |  |  | Foundation |  | 4 | 4.2 | 4.2 | 0.1 | 7.056 | Cum | JMR Not Rcved
[9 empty] | TOTAL | 19.388 | Cum
PCC3-6MTR
|  |  |  | Footing | F1 | 2 | 2.2 | 2.2 | 0.1 | 0.968 | Cum
|  |  |  | Footing | F2 | 2 | 3.4 | 3.2 | 0.1 | 2.176 | Cum
|  |  |  | Footing | F3 | 1 | 4 | 3.4 | 0.1 | 1.36 | Cum
|  |  |  | Footing | F4 | 5 | 3.6 | 3.6 | 0.1 | 6.48 | Cum
|  |  |  | Footing | F5 | 4 | 4 | 4 | 0.1 | 6.4 | Cum
[9 empty] | TOTAL | 17.384 | Cum
P C C 0 --3MTR
BEAM
| PB1 A |  |  |  |  | 1 | 43.2994 | 0.55 | 0.1 | 2.3815 | Cum
| PB1 B |  |  |  |  | 1 | 34.11 | 0.55 | 0.1 | 1.8761 | Cum
| PB1 B'-B" |  |  |  |  | 1 | 5.775 | 0.55 | 0.1 | 0.31763 | Cum
| PB1 1" A'-B" |  |  |  |  | 1 | 10.875 | 0.55 | 0.1 | 0.59813 | Cum
| B1 1"-1' |  |  |  |  | 1 | 2.55 | 0.55 | 0.1 | 0.14025 |  |  |  |  | 10.0894 |  | -5.303
| PB2 (A4-B4,A3-B3,A2-B2) |  |  |  |  | 3 | 12.07 | 0.55 | 0.1 | 1.9916 | Cum
| PB 2 1'-1" |  |  |  |  | 1 | 2.325 | 0.55 | 0.1 | 0.12787 | Cum
[9 empty] | TOTAL | 7.4329 | Cum |  |  |  | 10.0894
RCC (3-6MTR)
|  | 91.2 | 91.55 | RAFT | F1 | 2 | 1.8 | 1.8 | 0.35 | 2.268 | Cum |  |  |  |  | from | to
|  | 91.55 | 91.95 | PEDISTAL | F1 | 2 | 0.85 | 0.85 | 0.4 | 0.578 | Cum |  |  |  | 0--3\ | 96.303 | 93.303
|  | 91.2 | 91.65 | RAFT | F2 | 2 | 3 | 2.8 | 0.45 | 7.56 | Cum |  |  |  | 3--6/ | 93.303 | 90.303
|  | 91.65 | 92.15 | PEDISTAL | F2 | 2 | 1.2 | 1.2 | 0.5 | 1.44 | Cum |  |  |  | 6--9/ | 90.303 | 87.303
|  | 91.2 | 91.65 | RAFT | F3 | 1 | 3 | 3.6 | 0.45 | 4.86 | Cum
|  | 91.65 | 92.15 | PEDISTAL | F3 | 1 | 1.3 | 1.3 | 0.5 | 0.845 | Cum
|  | 91.2 | 91.65 | RAFT | F4 | 5 | 3.2 | 3.2 | 0.45 | 23.04 | Cum
|  | 91.65 | 92.15 | PEDISTAL | F4 | 5 | 1.3 | 1.3 | 0.5 | 4.225 | Cum
|  | 91.2 | 91.725 | RAFT | F5 | 4 | 3.6 | 3.6 | 0.525 | 27.216 | Cum |  |  |  | Pcc Bottom | 91.1
|  | 91.725 | 92.325 | PEDISTAL | F5 | 4 | 1.3 | 1.3 | 0.6 | 4.056 | Cum |  |  |  | PCC top | 91.2
|  | 92.15 | 93.303 | COL | C1/F4 | 5 | 0.9 | 0.9 | 1.153 | 4.6697 | Cum |  | 1.153 | 0 | RCC Top (Footing) | 91.725
|  | 92.325 | 93.303 | COL | C1/F5 | 4 | 0.9 | 0.9 | 0.978 | 3.1687 | Cum |  | 0.978 | 0 | RCC Top (Pedastal) | 92.325
|  | 92.15 | 93.303 | COL | C2/F2 | 2 | 0.45 | 0.45 | 1.15 | 0.46575 | Cum |  | 1.153 | -0.003 | Column Bottom F1
|  | 91.95 | 93.303 | COL | C3 | 2 | 0.45 | 0.45 | 1.15 | 0.46575 | Cum |  | 1.353 | -0.203
[9 empty] | TOTAL | 84.8579 | Cum
0-3mtr
| col C1 0.00 | 93.303 | 94.4 |  |  | 10 | 0.9 | 0.9 | 1.097 | 8.8857 | Cum
| C2 | 93.303 | 94.4 |  |  | 2 | 0.45 | 0.45 | 1.097 | 0.44429 | Cum |  |  |  | 2.85
| C3 | 93.303 | 94.4 |  |  | 2 | 0.45 | 0.45 | 1.097 | 0.44429 | Cum |  |  |  | 1.5
| P BEAM | [8 empty] | 0 | Cum |  |  |  | 1.153
| PB1 A |  |  |  |  | 1 | 43.2994 | 0.35 | 0.6 | 9.0929 | Cum |  |  |  | 1.153
| PB1 B |  |  |  |  | 1 | 34.11 | 0.35 | 0.6 | 7.1631 | Cum
| PB1 1' |  |  |  |  | 1 | 5.775 | 0.35 | 0.6 | 1.2127 | Cum |  |  |  |  | 94.4
| PB1 1" |  |  |  |  | 1 | 12.45 | 0.35 | 0.6 | 2.6145 | Cum |  |  |  |  | 94.4
| B1 |  |  |  |  | 1 | 2.55 | 0.35 | 0.6 | 0.5355 | Cum |  |  |  |  | 94.4
| PB2 (4,3,2) |  |  |  |  | 3 | 12.07 | 0.35 | 0.6 | 7.6041 | Cum |  |  | 1.153
| B" |  |  |  |  | 1 | 2.325 | 0.35 | 0.6 | 0.48825 | Cum
0
[9 empty] | TOTAL | 38.4853 | Cum
| SHUTTERING |  |  | M2
3-6MTR
| RAFT F1 | 91.2 | 91.55 |  |  | 4 | 1.8 |  | 0.35 | 2.52 | Sqm
| PEDISTAL | 91.55 | 91.95 |  |  | 4 | 0.85 |  | 0.4 | 1.36 | Sqm
| F2 | 91.2 | 91.65 |  |  | 4 | 3 |  | 0.45 | 5.4 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 4 | 1.2 |  | 0.5 | 2.4 | Sqm
| F3 | 91.2 | 91.65 |  |  | 2 | 3 |  | 0.45 | 2.7 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 2 | 1.3 |  | 0.5 | 1.3 | Sqm
| F4 | 91.2 | 91.65 |  |  | 10 | 3.2 |  | 0.45 | 14.4 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 10 | 1.3 |  | 0.5 | 6.5 | Sqm
| F5 | 91.2 | 91.725 |  |  | 8 | 3.6 |  | 0.525 | 15.12 | Sqm
| PEDISTAL | 91.725 | 92.325 |  |  | 8 | 1.3 |  | 0.6 | 6.24 | Sqm
| (COL-C1)/F4 | 92.15 | 93.303 |  |  | 10 | 0.9 |  | 1.153 | 10.377 | Sqm
| (COL C1)/F5 | 92.325 | 93.303 |  |  | 8 | 0.9 |  | 0.978 | 7.0416 | Sqm
| C2/F2 | 92.15 | 93.303 |  |  | 4 | 0.45 |  | 1.15 | 2.07 | Sqm
| C3 | 91.95 | 93.303 |  |  | 4 | 0.45 |  | 1.15 | 2.07 | Sqm
Sqm
| RAFT F1 | 91.2 | 91.55 |  |  | 4 |  | 1.8 | 0.35 | 2.52 | Sqm
| PEDISTAL | 91.55 | 91.95 |  |  | 4 |  | 0.85 | 0.4 | 1.36 | Sqm
| F2 | 91.2 | 91.65 |  |  | 4 |  | 2.8 | 0.45 | 5.04 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 4 |  | 1.2 | 0.5 | 2.4 | Sqm
| F3 | 91.2 | 91.65 |  |  | 2 |  | 3.6 | 0.45 | 3.24 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 2 |  | 1.3 | 0.5 | 1.3 | Sqm
| F4 | 91.2 | 91.65 |  |  | 10 |  | 3.2 | 0.45 | 14.4 | Sqm
| PEDISTAL | 91.65 | 92.15 |  |  | 10 |  | 1.3 | 0.5 | 6.5 | Sqm
| F5 | 91.2 | 91.725 |  |  | 8 |  | 3.6 | 0.525 | 15.12 | Sqm
| PEDISTAL | 91.725 | 92.325 |  |  | 8 |  | 1.3 | 0.6 | 6.24 | Sqm
| (COL-C1)/F4 | 92.15 | 93.303 |  |  | 10 |  | 0.9 | 1.153 | 10.377 | Sqm
| (COL C1)/F5 | 92.325 | 93.303 |  |  | 8 |  | 0.9 | 0.978 | 7.0416 | Sqm
| C2/F2 | 92.15 | 93.303 |  |  | 4 |  | 0.45 | 1.15 | 2.07 | Sqm
| C3 | 91.95 | 93.303 |  |  | 4 |  | 0.45 | 1.15 | 2.07 | Sqm
Sqm
Sqm
Sqm
[9 empty] | TOTAL | 159.1772 | Sqm
| SHUTTERING |  |  | M2
| 0-3mtr | [9 empty] | Sqm
| col C1 0.00 | 93.303 | 94.4 |  |  | 20 | 0.9 |  | 1.097 | 19.746 | Sqm
| C2 | 93.303 | 94.4 |  |  | 4 | 0.45 |  | 1.097 | 1.9746 | Sqm
| C3 | 93.303 | 94.4 |  |  | 4 | 0.45 |  | 1.097 | 1.9746 | Sqm
Sqm
| col C1 0.00 | 93.303 | 94.4 |  |  | 20 |  | 0.9 | 1.097 | 19.746 | Sqm
| C2 | 93.303 | 94.4 |  |  | 4 |  | 0.45 | 1.097 | 1.9746 | Sqm
| C3 | 93.303 | 94.4 |  |  | 4 |  | 0.45 | 1.097 | 1.9746 | Sqm
| P BEAM | [8 empty] | 0 | Sqm
| PB1 A |  |  | Side Shuttering |  | 2 | 43.2994 |  | 0.6 | 51.9593 | Sqm
| PB1 B |  |  | Side Shuttering |  | 2 | 34.11 |  | 0.6 | 40.932 | Sqm
| PB1 1' |  |  | Side Shuttering |  | 2 | 5.775 |  | 0.6 | 6.93 | Sqm
| PB1 1" |  |  | Side Shuttering |  | 2 | 12.45 |  | 0.6 | 14.94 | Sqm
| B1 |  |  | Side Shuttering |  | 2 | 2.55 |  | 0.6 | 3.06 | Sqm
| PB2 (4,3,2) |  |  | Side Shuttering |  | 6 | 12.07 |  | 0.6 | 43.452 | Sqm
| B" |  |  | Side Shuttering |  | 2 | 2.325 |  | 0.6 | 2.79 | Sqm
Side Shuttering
[9 empty] | TOTAL | 211.4537
| BACK FILLING |  |  | M3 |  |  | TOTAL EXCAVATION |  |  | 1608.508
[6 empty] | RCC |  |  |  | 123.3432
[9 empty] | TOTAL | 1485.1648

## Sheet2
BAR BENDING SCHEDULE A C C
S.No | Description | Dia in MM | NO OF RAFT | No of member | No. of Bar | Cutting Length | [5 empty] | DIAWISE LENGTH
|  |  | RAFT | [6 empty] | TOTAL QUNT (M)
1 | F1 3--6MTR | [6 empty] | lap | TOTAL |  | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
Footings- | Bottom | 12MM | 2 | 2 | 12 | 1.7 | 0.4 |  | 2.1 | 48 |  |  | 48
| top | 10MM | 2 | 2 | 12 | 1.7 | 0.4 |  | 2.1 | 100.8 |  | 100.8
| chair | 12MM | 2 | 1 | 5 | 0.7 | 1.4 |  | 2.1 | 21 |  |  | 21
| PEDISTAL | 12MM | 2 | 1 | 16 | 0.65 | 0.4 |  | 1.05 | 33.6 |  |  | 33.6
| RING | 8MM | 2 | 1 | 6 | 3.08 | 0.1 |  | 3.18 | 38.16 | 38.16
[9 empty] | 0 | 0
| F2 | 16MM | 2 | 1 | 21 | 2.7 | 0.6 |  | 3.3 | 138.6 |  |  |  | 138.6
|  | 16MM | 2 | 1 | 20 | 2.9 | 0.6 |  | 3.5 | 140 |  |  |  | 140
| TOP | 10MM | 2 | 1 | 21 | 2.7 | 0.6 |  | 3.3 | 138.6 |  | 138.6
|  | 10MM | 2 | 1 | 20 | 2.9 | 0.6 |  | 3.5 | 140 |  | 140
| chair | 12MM | 2 | 1 | 8 | 0.7 | 1.5 |  | 2.2 | 35.2 |  |  | 35.2
| PEDISTAL | 12MM | 2 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 50 |  |  | 50
| RING | 8MM | 2 | 1 | 6 | 4.5 | 0.1 |  | 4.6 | 55.2 | 55.2
| F3 | 16MM | 1 | 1 | 29 | 2.9 | 0.6 |  | 3.5 | 101.5 |  |  |  | 101.5
|  | 16MM | 1 | 1 | 24 | 3.5 | 0.6 |  | 4.1 | 98.4 |  |  |  | 98.4
| TOP | 10MM | 1 | 1 | 29 | 2.9 | 0.6 |  | 3.5 | 101.5 |  | 101.5
|  | 10MM | 1 | 1 | 24 | 3.5 | 0.6 |  | 4.1 | 98.4 |  | 98.4
| chair | 12MM | 1 | 1 | 9 | 0.7 | 1.5 |  | 2.2 | 19.8 |  |  | 19.8
| PEDISTAL | 12MM | 1 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 25 |  |  | 25
| RING | 8MM | 1 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 29.88 | 29.88
| F4 | 16MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 |  |  |  | 499.5
|  | 16MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 |  |  |  | 499.5
| TOP | 10MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 | 499.5
|  | 10MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 | 499.5
| chair | 12MM | 5 | 1 | 10 | 0.7 | 1.5 |  | 2.2 | 110 |  |  | 110
| PEDISTAL | 12MM | 5 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 125 |  |  | 125
| RING | 8MM | 5 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 149.4 | 149.4
| F5 | 20MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  |  |  |  | 410
|  | 20MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  |  |  |  | 410
| TOP | 10MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  | 410
|  | 10MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  | 410
| chair | 12MM | 4 | 1 | 12 | 0.7 | 1.5 |  | 2.2 | 105.6 |  |  | 105.6
| PEDISTAL | 12MM | 4 | 1 | 20 | 1.075 | 0.4 |  | 1.475 | 118 |  |  | 118
| RING | 8MM | 4 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 119.52 | 119.52
[9 empty] | 0 | 0
| COL C1 | 25MM | 5 | 1 | 16 | 2.425 | 0.4 |  | 2.825 | 226 | [5 empty] | 226
|  |  | 5 | 1 | 16 | 2.425 | 0.4 |  | 2.825 | 226 | [5 empty] | 226
| RING | 8MM | 5 | 2 | 13 | 3.28 | 0.1 |  | 3.38 | 439.4 | 439.4
|  |  | 5 | 2 | 13 | 3.28 | 0.1 |  | 3.38 | 439.4 | 439.4
|  |  | 10 | 2 | 13 | 2.52 | 0.1 |  | 2.62 | 681.2 |  | 681.2
|  |  | 10 | 2 | 13 | 0.98 |  |  | 0.98 | 254.8 |  | 254.8
| C2 | 25mm | 2 | 1 | 8 | 2.4 | 0.4 |  | 2.8 | 44.8 | [5 empty] | 44.8
|  | 8mm | 2 | 2 | 13 | 1.48 | 0.1 |  | 1.58 | 82.16 | 82.16
|  | 8mm | 2 | 2 | 13 | 0.89 | 0.1 |  | 0.99 | 51.48 | 51.48
| C3 | 25mm | 2 | 1 | 4 | 2.4 | 0.4 |  | 2.8 | 22.4 | [5 empty] | 22.4
|  | 20mm | 2 | 1 | 4 | 2.4 | 0.4 |  | 2.8 | 22.4 |  |  |  |  | 22.4
|  | 8mm | 2 | 2 | 13 | 1.48 | 0.1 |  | 1.58 | 82.16 | 82.16
|  | 8mm | 2 | 2 | 13 | 0.89 | 0.1 |  | 0.99 | 51.48 | 51.48
[11 empty] | 2537.24 | 2335.3 | 691.2 | 1477.5 | 842.4 | 519.2
[11 empty] | 0.395 | 0.62 | 0.888 | 1.58 | 2.47 | 3.87
[11 empty] | 1002.2098 | 1447.886 | 613.7856 | 2334.45 | 2080.728 | 2009.304
[11 empty] | TOTAL | 9488.3634
[11 empty] | TOTAL | 9.4884
0--3
| COL C1 | 25MM | 5 | 1 | 16 | 1.2 | 0.4 | 1.225 | 2.825 | 226 | [5 empty] | 226
|  | 25MM | 5 | 1 | 16 | 1.2 | 0.4 | 1.225 | 2.825 | 226 | [5 empty] | 226
| RING | 8MM | 5 | 2 | 7 | 3.28 | 0.1 |  | 3.38 | 236.6 | 236.6
|  | 8MM | 5 | 2 | 7 | 3.28 | 0.1 |  | 3.38 | 236.6 | 236.6
|  | 8MM | 10 | 2 | 7 | 2.52 | 0.1 |  | 2.62 | 366.8 | 366.8
|  | 8MM | 10 | 2 | 7 | 0.98 |  |  | 0.98 | 137.2 | 137.2
| C2 | 25mm | 2 | 1 | 8 | 1.2 | 0.4 | 1.225 | 2.825 | 45.2 | [5 empty] | 45.2
|  | 8mm | 2 | 2 | 7 | 1.48 | 0.1 |  | 1.58 | 44.24 | 44.24
|  | 8mm | 2 | 2 | 7 | 0.89 | 0.1 |  | 0.99 | 27.72 | 27.72
| C3 | 25mm | 2 | 1 | 4 | 1.2 | 0.4 | 1.225 | 2.825 | 22.6 | [5 empty] | 22.6
|  | 20mm | 2 | 1 | 4 | 1.2 | 0.4 | 1 | 2.6 | 20.8 |  |  |  |  | 20.8
|  | 8mm | 2 | 2 | 7 | 1.48 | 0.1 |  | 1.58 | 44.24 | 44.24
|  | 8mm | 2 | 2 | 7 | 0.89 | 0.1 |  | 0.99 | 27.72 | 27.72 | [5 empty] | 148
| P BEAM | [7 empty] | 0 | 0
| PB1 A | 20mm | 1 | 2 | 3 | 47.2 | 0.4 | 5 | 52.6 | 315.6 |  |  |  |  | 315.6
| EXT | 16 | 1 | 2 | 2 | 4 | 0.4 |  | 4.4 | 17.6 |  |  |  | 17.6
|  | 16 | 1 | 3 | 2 | 7 |  |  | 7 | 42 |  |  |  | 42
| RING | 8 | 1 | 1 | 189 | 1.6 | 0.1 |  | 1.7 | 321.3 | 321.3
[9 empty] | 0 | 0
| PB1 A | 20mm | 1 | 2 | 3 | 37.2 | 0.8 | 5 | 43 | 258 |  |  |  |  | 258
| EXT | 16 | 1 | 2 | 2 | 4 | 0.8 |  | 4.8 | 19.2 |  |  |  | 19.2
|  | 16 | 1 | 2 | 2 | 7 |  |  | 7 | 28 |  |  |  | 28
| RING | 8 | 1 | 1 | 148 | 1.6 | 0.1 |  | 1.7 | 251.6 | 251.6
| PB2 | 20 | 4 | 2 | 3 | 13.2 | 0.8 | 1 | 15 | 360 |  |  |  |  | 360 |  | 65
| EXT | 16 | 4 | 1 | 2 | 3.5 | 0.4 |  | 3.9 | 31.2 |  |  |  | 31.2
| RING | 8 | 4 | 1 | 66 | 1.6 | 0.1 |  | 1.7 | 448.8 | 448.8
| PB1 1" | 20 | 1 | 2 | 3 | 12.75 | 0.4 | 1 | 14.15 | 84.9 |  |  |  |  | 84.9
|  | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 64 | 1.6 | 0.1 |  | 1.7 | 108.8 | 108.8
| PB1 1" | 20 | 1 | 2 | 3 | 10.4 | 0.4 | 1 | 11.8 | 70.8 |  |  |  |  | 70.8
| 1---1" | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 58 | 1.6 | 0.1 |  | 1.7 | 98.6 | 98.6
[9 empty] | 0 | 0
| PB1 1" | 20 | 1 | 2 | 3 | 6.7 | 0.4 |  | 7.1 | 42.6 |  |  |  |  | 42.6
| 1 | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 35 | 1.6 | 0.1 |  | 1.7 | 59.5 | 59.5
[11 empty] | 2409.72 | 0 | 0 | 184.8 | 1152.7 | 519.8
[11 empty] | 0.395 | 0.62 | 0.888 | 1.58 | 2.47 | 3.87
[11 empty] | 951.8394 | 0 | 0 | 291.984 | 2847.169 | 2011.626
[11 empty] | TOTAL | 6102.6184
[11 empty] | TOTAL | 6.1026