## RA 1
To
Nakoda Pipe Impex Pvt Ltd | [10 empty] | 2023-09-20
ACC RA 1
Sl No | Item No | Description | UOM | Rate | Block | Upto Prev Bill |  | This Bill Claimed |  | Total Up to Date
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents {0--3Mtr} | m3 | 180 | ACC |  |  |  | 0 | 0 | 0
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents {3--6Mtr} | m3 | 220 | ACC |  |  |  | 0 | 0 | 0
3 |  | Backfilling | m3 | 80 | ACC |  |  |  | 0 | 0 | 0
5 |  | Sand Filling | m3 | 1180 | ACC |  |  |  | 0 | 0 | 0
6 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | ACC |  |  | 7.4329 | 17095.7641 | 7.4329 | 17095.7641
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6Mtr | m3 | 2599 | ACC |  |  | 17.384 | 45181.016 | 17.384 | 45181.016
8 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | ACC |  |  | 38.4853 | 105834.6848 | 38.4853 | 105834.6848
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing {Circular foundation} | m3 | 3107.5 | ACC |  |  | 84.8579 | 263695.831 | 84.8579 | 263695.831
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 | 3465 | ACC |  |  |  | 0 | 0 | 0
11 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | ACC |  |  | 211.4537 | 84581.4627 | 211.4537 | 84581.4627
12 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/-3--6Mtr | m2 | 452 | ACC |  |  | 159.1772 | 71948.0944 | 159.1772 | 71948.0944
13 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | ACC |  |  | 6.1026 | 54923.5656 | 6.1026 | 54923.5656
|  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | ACC |  |  | 9.4884 | 96496.6558 | 9.4884 | 96496.6558
14 |  | Bolt Fixing of anchor and foundation Bolt upto 30 mm Dia | Nos | 450 | ACC |  |  |  | 0 | 0 | 0
|  | Bolt Fixing of anchor and foundation Bolt above 32 mm Dia | MT | 22000 | ACC |  |  |  | 0 | 0 | 0
15 | 40 | Pocket Fixing Work | Nos |  | ACC |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[7 empty] | 0 |  | 739757.0744 |  | 739757.0744

## Measuerment Sheet
A C C
S.no. | Description | Reduced Level |  | Stucture | Mkd | No | L | B | H | Qty | Unit | Remark
|  | From | To
Excavtion 0--3Mtr
|  |  |  | Foundation |  | 1 | 26.17 | 60 | 1.8 | 2826.36 | cum
|  |  |  | Foundation |  | 2 | 5.8 | 5.8 | 1.2 | 80.736 | cum
|  |  |  | Foundation | F2&F3 | 1 | 10 | 7.6 | 1.2 | 91.2 | cum
|  |  |  | Foundation | F2 | 1 | 7 | 6.8 | 1.2 | 57.12 | cum
|  |  |  | Foundation | F4 | 5 | 7.2 | 7.2 | 1.2 | 311.04 | cum
|  |  |  | Foundation | F5 | 4 | 7.6 | 7.6 | 1.2 | 277.248 | cum
[9 empty] | TOTAL | 3643.704 | cum
Excavtion 3--6Mtr
|  |  |  | Foundation |  | 2 | 3.8 | 3.8 | 2.2 | 63.536 | cum
|  |  |  | Foundation | F2&F3 | 1 | 8 | 5.6 | 2.2 | 98.56 | cum
|  |  |  | Foundation | F2 | 1 | 5 | 4.8 | 2.2 | 52.8 | cum
|  |  |  | Foundation | F4 | 5 | 5.25 | 5.2 | 2.2 | 300.3 | cum
|  |  |  | Foundation | F5 | 4 | 5.6 | 5.6 | 2.2 | 275.968 | cum
0
[9 empty] | TOTAL | 791.164 | cum
DRESING 3-6MTR
|  |  |  | Foundation | F1 | 2 | 2.6 | 2.6 |  | 13.52 | Sqm
|  |  |  | Foundation | F2 | 2 | 3.8 | 3.6 |  | 27.36 | Sqm
|  |  |  | Foundation | F3 | 1 | 4.4 | 3.8 |  | 16.72 | Sqm
|  |  |  | Foundation | F4 | 5 | 4 | 4 |  | 80 | Sqm
|  |  |  | Foundation | F5 | 4 | 4.4 | 4.4 |  | 77.44 | Sqm
[9 empty] | TOTAL | 215.04 | Sqm
Dressing 0 --3MTR
| BEAM | [8 empty] | 0
| PB1 A |  |  | Foundation |  | 1 | 46.81 | 0.65 |  | 30.4265
| PB1 B |  |  | Foundation |  | 1 | 36.81 | 0.65 |  | 23.9265
| PB1 1' |  |  | Foundation |  | 1 | 6.45 | 0.65 |  | 4.1925
| PB1 1" |  |  | Foundation |  | 1 | 12.45 | 0.65 |  | 8.0925
| B1 |  |  | Foundation |  | 1 | 3 | 0.65 |  | 1.95
| PB2 (4,3,2) |  |  | Foundation |  | 3 | 12.97 | 0.65 |  | 25.2915
| B" |  |  | Foundation |  | 1 | 3 | 0.65 |  | 1.95
[9 empty] | TOTAL | 95.8295 |  |  |  | 1
SAND filling 3--6 Mtr
| F1 |  |  | Foundation |  | 2 | 2.4 | 2.4 | 0.1 | 1.152 | Cum
| F2 |  |  | Foundation |  | 2 | 3.6 | 3.4 | 0.1 | 2.448 | Cum
| F3 |  |  | Foundation |  | 1 | 4.2 | 3.6 | 0.1 | 1.512 | Cum
| F4 |  |  | Foundation |  | 5 | 3.8 | 3.8 | 0.1 | 7.22 | Cum
| F5 |  |  | Foundation |  | 4 | 4.2 | 4.2 | 0.1 | 7.056 | Cum
[9 empty] | TOTAL | 19.388 | Cum
PCC3-6MTR
|  |  |  | Footing | F1 | 2 | 2.2 | 2.2 | 0.1 | 0.968 | Cum
|  |  |  | Footing | F2 | 2 | 3.4 | 3.2 | 0.1 | 2.176 | Cum
|  |  |  | Footing | F3 | 1 | 4 | 3.4 | 0.1 | 1.36 | Cum
|  |  |  | Footing | F4 | 5 | 3.6 | 3.6 | 0.1 | 6.48 | Cum
|  |  |  | Footing | F5 | 4 | 4 | 4 | 0.1 | 6.4 | Cum
[9 empty] | TOTAL | 17.384 | Cum
P C C 0 --3MTR
BEAM
| PB1 A |  |  |  |  | 1 | 43.2994 | 0.55 | 0.1 | 2.3815 | Cum
| PB1 B |  |  |  |  | 1 | 34.11 | 0.55 | 0.1 | 1.8761 | Cum
| PB1 B'-B" |  |  |  |  | 1 | 5.775 | 0.55 | 0.1 | 0.31763 | Cum
| PB1 1" A'-B" |  |  |  |  | 1 | 10.875 | 0.55 | 0.1 | 0.59813 | Cum
| B1 1"-1' |  |  |  |  | 1 | 2.55 | 0.55 | 0.1 | 0.14025 |  |  |  |  | 10.0894 |  | -5.303
| PB2 (A4-B4,A3-B3,A2-B2) |  |  |  |  | 3 | 12.07 | 0.55 | 0.1 | 1.9916 | Cum
| PB 2 1'-1" |  |  |  |  | 1 | 2.325 | 0.55 | 0.1 | 0.12787 | Cum
[9 empty] | TOTAL | 7.4329 | Cum |  |  |  | 10.0894
RCC (3-6MTR)
|  | 91.2 | 91.55 | RAFT | F1 | 2 | 1.8 | 1.8 | 0.35 | 2.268 | Cum |  |  |  |  | from | to
|  | 91.55 | 91.95 | PEDISTAL | F1 | 2 | 0.85 | 0.85 | 0.4 | 0.578 | Cum |  |  |  | 0--3\ | 96.303 | 93.303
|  | 91.2 | 91.65 | RAFT | F2 | 2 | 3 | 2.8 | 0.45 | 7.56 | Cum |  |  |  | 3--6/ | 93.303 | 90.303
|  | 91.65 | 92.15 | PEDISTAL | F2 | 2 | 1.2 | 1.2 | 0.5 | 1.44 | Cum |  |  |  | 6--9/ | 90.303 | 87.303
|  | 91.2 | 91.65 | RAFT | F3 | 1 | 3 | 3.6 | 0.45 | 4.86 | Cum
|  | 91.65 | 92.15 | PEDISTAL | F3 | 1 | 1.3 | 1.3 | 0.5 | 0.845 | Cum
|  | 91.2 | 91.65 | RAFT | F4 | 5 | 3.2 | 3.2 | 0.45 | 23.04 | Cum
|  | 91.65 | 92.15 | PEDISTAL | F4 | 5 | 1.3 | 1.3 | 0.5 | 4.225 | Cum
|  | 91.2 | 91.725 | RAFT | F5 | 4 | 3.6 | 3.6 | 0.525 | 27.216 | Cum |  |  |  | Pcc Bottom | 91.1
|  | 91.725 | 92.325 | PEDISTAL | F5 | 4 | 1.3 | 1.3 | 0.6 | 4.056 | Cum |  |  |  | PCC top | 91.2
|  | 92.15 | 93.303 | COL | C1/F4 | 5 | 0.9 | 0.9 | 1.153 | 4.6697 | Cum |  | 1.153 | 0 | RCC Top (Footing) | 91.725
|  | 92.325 | 93.303 | COL | C1/F5 | 4 | 0.9 | 0.9 | 0.978 | 3.1687 | Cum |  | 0.978 | 0 | RCC Top (Pedastal) | 92.325
|  | 92.15 | 93.303 | COL | C2/F2 | 2 | 0.45 | 0.45 | 1.15 | 0.46575 | Cum |  | 1.153 | -0.003 | Column Bottom F1
|  | 91.95 | 93.303 | COL | C3 | 2 | 0.45 | 0.45 | 1.15 | 0.46575 | Cum |  | 1.353 | -0.203
[9 empty] | TOTAL | 84.8579 | Cum
0-3mtr
|  | 93.303 | 94.4 | col | C1 | 10 | 0.9 | 0.9 | 1.097 | 8.8857 | Cum
|  | 93.303 | 94.4 | col | C2 | 2 | 0.45 | 0.45 | 1.097 | 0.44429 | Cum |  |  |  | 2.85
|  | 93.303 | 94.4 | col | C3 | 2 | 0.45 | 0.45 | 1.097 | 0.44429 | Cum |  |  |  | 1.5
|  |  |  | P BEAM | [5 empty] | 0 | Cum |  |  |  | 1.153
[5 empty] | PB1 A | 1 | 43.2994 | 0.35 | 0.6 | 9.0929 | Cum |  |  |  | 1.153
[5 empty] | PB1 B | 1 | 34.11 | 0.35 | 0.6 | 7.1631 | Cum
[5 empty] | PB1 1' | 1 | 5.775 | 0.35 | 0.6 | 1.2127 | Cum |  |  |  |  | 94.4
[5 empty] | PB1 1" | 1 | 12.45 | 0.35 | 0.6 | 2.6145 | Cum |  |  |  |  | 94.4
[5 empty] | B1 | 1 | 2.55 | 0.35 | 0.6 | 0.5355 | Cum |  |  |  |  | 94.4
[5 empty] | PB2 (4,3,2) | 3 | 12.07 | 0.35 | 0.6 | 7.6041 | Cum |  |  | 1.153
[5 empty] | B" | 1 | 2.325 | 0.35 | 0.6 | 0.48825 | Cum
0
[9 empty] | TOTAL | 38.4853 | Cum
SHUTTERING 3--6Mtr
|  | 91.2 | 91.55 | RAFT F1 |  | 4 | 1.8 |  | 0.35 | 2.52 | Sqm
|  | 91.55 | 91.95 | PEDISTAL |  | 4 | 0.85 |  | 0.4 | 1.36 | Sqm
|  | 91.2 | 91.65 | F2 |  | 4 | 3 |  | 0.45 | 5.4 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 4 | 1.2 |  | 0.5 | 2.4 | Sqm
|  | 91.2 | 91.65 | F3 |  | 2 | 3 |  | 0.45 | 2.7 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 2 | 1.3 |  | 0.5 | 1.3 | Sqm
|  | 91.2 | 91.65 | F4 |  | 10 | 3.2 |  | 0.45 | 14.4 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 10 | 1.3 |  | 0.5 | 6.5 | Sqm
|  | 91.2 | 91.725 | F5 |  | 8 | 3.6 |  | 0.525 | 15.12 | Sqm
|  | 91.725 | 92.325 | PEDISTAL |  | 8 | 1.3 |  | 0.6 | 6.24 | Sqm
|  | 92.15 | 93.303 | (COL-C1)/F4 |  | 10 | 0.9 |  | 1.153 | 10.377 | Sqm
|  | 92.325 | 93.303 | (COL C1)/F5 |  | 8 | 0.9 |  | 0.978 | 7.0416 | Sqm
|  | 92.15 | 93.303 | C2/F2 |  | 4 | 0.45 |  | 1.15 | 2.07 | Sqm
|  | 91.95 | 93.303 | C3 |  | 4 | 0.45 |  | 1.15 | 2.07 | Sqm
Sqm
|  | 91.2 | 91.55 | RAFT F1 |  | 4 |  | 1.8 | 0.35 | 2.52 | Sqm
|  | 91.55 | 91.95 | PEDISTAL |  | 4 |  | 0.85 | 0.4 | 1.36 | Sqm
|  | 91.2 | 91.65 | F2 |  | 4 |  | 2.8 | 0.45 | 5.04 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 4 |  | 1.2 | 0.5 | 2.4 | Sqm
|  | 91.2 | 91.65 | F3 |  | 2 |  | 3.6 | 0.45 | 3.24 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 2 |  | 1.3 | 0.5 | 1.3 | Sqm
|  | 91.2 | 91.65 | F4 |  | 10 |  | 3.2 | 0.45 | 14.4 | Sqm
|  | 91.65 | 92.15 | PEDISTAL |  | 10 |  | 1.3 | 0.5 | 6.5 | Sqm
|  | 91.2 | 91.725 | F5 |  | 8 |  | 3.6 | 0.525 | 15.12 | Sqm
|  | 91.725 | 92.325 | PEDISTAL |  | 8 |  | 1.3 | 0.6 | 6.24 | Sqm
|  | 92.15 | 93.303 | (COL-C1)/F4 |  | 10 |  | 0.9 | 1.153 | 10.377 | Sqm
|  | 92.325 | 93.303 | (COL C1)/F5 |  | 8 |  | 0.9 | 0.978 | 7.0416 | Sqm
|  | 92.15 | 93.303 | C2/F2 |  | 4 |  | 0.45 | 1.15 | 2.07 | Sqm
|  | 91.95 | 93.303 | C3 |  | 4 |  | 0.45 | 1.15 | 2.07 | Sqm
Sqm
Sqm
Sqm
[9 empty] | TOTAL | 159.1772 | Sqm
| SHUTTERING |  |  | M2
| 0-3mtr | [9 empty] | Sqm
|  | 93.303 | 94.4 |  | col C1 0.00 | 20 | 0.9 |  | 1.097 | 19.746 | Sqm
|  | 93.303 | 94.4 |  | C2 | 4 | 0.45 |  | 1.097 | 1.9746 | Sqm
|  | 93.303 | 94.4 |  | C3 | 4 | 0.45 |  | 1.097 | 1.9746 | Sqm
Sqm
|  | 93.303 | 94.4 |  | col C1 0.00 | 20 |  | 0.9 | 1.097 | 19.746 | Sqm
|  | 93.303 | 94.4 |  | C2 | 4 |  | 0.45 | 1.097 | 1.9746 | Sqm
|  | 93.303 | 94.4 |  | C3 | 4 |  | 0.45 | 1.097 | 1.9746 | Sqm
[5 empty] | P BEAM |  |  |  |  | 0 | Sqm
|  |  |  | Side Shuttering | PB1 A | 2 | 43.2994 |  | 0.6 | 51.9593 | Sqm
|  |  |  | Side Shuttering | PB1 B | 2 | 34.11 |  | 0.6 | 40.932 | Sqm
|  |  |  | Side Shuttering | PB1 1' | 2 | 5.775 |  | 0.6 | 6.93 | Sqm
|  |  |  | Side Shuttering | PB1 1" | 2 | 12.45 |  | 0.6 | 14.94 | Sqm
|  |  |  | Side Shuttering | B1 | 2 | 2.55 |  | 0.6 | 3.06 | Sqm
|  |  |  | Side Shuttering | PB2 (4,3,2) | 6 | 12.07 |  | 0.6 | 43.452 | Sqm
|  |  |  | Side Shuttering | B" | 2 | 2.325 |  | 0.6 | 2.79 | Sqm
Side Shuttering
[9 empty] | TOTAL | 211.4537
| BACK FILLING |  |  | M3 |  |  | TOTAL EXCAVATION |  |  | 1608.508
[6 empty] | RCC |  |  |  | 123.3432
[9 empty] | TOTAL | 1485.1648

## Abstract
TAX INVOICE
ACC
Name :- |  | M -TECH ENGINEERING |  |  | Invoice No. :
Address:- |  | B-11 Madhavrao Sapre Nagar,Birgoan |  |  | Invoice Date :-
|  | Raipur (C. G) |  |  | State :- Chhattisgarh
Mobile No.+ 9630655442 |  |  |  |  | State Code :- 22
E-mail:- mtechengg@yahoo.com |  |  |  |  | GSTIN :22AAZFM9371R1Z2
Details of Buyer
Name :- |  | SHREE NAKODA PIPE IMPEX PVT LTD
Address:- |  | Nakoda House Near Crossing Mowa Vidhan Sabha Road Raipur (C.G)
GSTIN :- |  | 22ABCCS8296A1ZG |  |  |  | State Code :- 22
Sr. No. | Name of Service |  | Unit | Total Quantity | Rate | Taxable Value
1 | EXCAVATION |  | M3 |  |  | 0
| 0-3 |  |  | 3643.704 | 180 | 655866.72
| 3,---6 |  |  | 791.164 | 220 | 174056.08
2 | DRESSING 0-3 |  | M2 | 95.8295 | 90 | 8624.655
| 3,---6 |  |  | 215.04 | 102 | 21934.08
3 | SAND FILING 0--3 |  | M3 |  |  | 0
| 3,---6 |  |  | 19.388 | 1333 | 25844.204
4 | P C C 0-3 |  | M3 | 8.1087 | 2300 | 18649.895
| 3,---6 |  |  | 17.384 | 2599 | 45181.016
5 | RCC 0-3 |  | M3 | 41.6523 | 6500 | 270739.95
| 3,---6 |  | M3 | 87.1445 | 7345 | 640076.3525
6 | SHUTTERING-0--3 |  | M2 | 232.536 | 450 | 104641.2
| 3,---6 |  |  | 188.82 | 509 | 96109.38
7 | BACK FILLING |  | M3 | 1479.7112 | 80 | 118376.896
8 | STEE L0--3 |  | MT | 6.1026 | 10000 | 61026.184
| 3--6 |  |  | 9.4878 | 11300 | 107212.0844
2348338.6969
[5 empty] | Basic Value | 2348338.6969
[5 empty] | Add : CGST | 211351
[5 empty] | Add : SGST | 211351
Add : IGST
Tax Amount (in Words) Twenty Seven Lac Seventy One Thousand Fourt Nine Only. |  |  |  |  | Total Amount | 2771040.6969
Certified that the particulars given above me true and correct
For, M Tech Engineering
Proprietor/Authorized Signatory

## Sheet2
BAR BENDING SCHEDULE A C C
S.No | Description | Dia in MM | NO OF RAFT | No of member | No. of Bar | Cutting Length | [5 empty] | DIAWISE LENGTH
|  |  | RAFT | [6 empty] | TOTAL QUNT
1 | F1 3--6MTR | [6 empty] | lap | TOTAL |  | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm
| Footings- | 12MM | 2 | 2 | 12 | 1.7 | 0.4 |  | 2.1 | 48 |  |  | 48
| top | 10MM | 2 | 2 | 12 | 1.7 | 0.4 |  | 2.1 | 100.8 |  | 100.8
| chair | 12MM | 2 | 1 | 5 | 0.7 | 0.8 | 0.536 | 2.036 | 20.36 |  |  | 20.36
| PEDISTAL | 12MM | 2 | 1 | 16 | 0.65 | 0.4 |  | 1.05 | 33.6 |  |  | 33.6
| RING | 8MM | 2 | 1 | 6 | 3.08 | 0.1 |  | 3.18 | 38.16 | 38.16
F2
|  | 16MM | 2 | 1 | 21 | 2.7 | 0.6 |  | 3.3 | 138.6 |  |  |  | 138.6
|  | 16MM | 2 | 1 | 20 | 2.9 | 0.6 |  | 3.5 | 140 |  |  |  | 140
| TOP | 10MM | 2 | 1 | 21 | 2.7 | 0.6 |  | 3.3 | 138.6 |  | 138.6
|  | 10MM | 2 | 1 | 20 | 2.9 | 0.6 |  | 3.5 | 140 |  | 140
| chair | 12MM | 2 | 1 | 8 | 0.7 | 1.5 |  | 2.2 | 35.2 |  |  | 35.2
| PEDISTAL | 12MM | 2 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 50 |  |  | 50 |  |  |  | 5.2
| RING | 8MM | 2 | 1 | 6 | 4.5 | 0.1 |  | 4.6 | 55.2 | 55.2
| F3 | 16MM | 1 | 1 | 29 | 2.9 | 0.6 |  | 3.5 | 101.5 |  |  |  | 101.5
|  | 16MM | 1 | 1 | 24 | 3.5 | 0.6 |  | 4.1 | 98.4 |  |  |  | 98.4
| TOP | 10MM | 1 | 1 | 29 | 2.9 | 0.6 |  | 3.5 | 101.5 |  | 101.5
|  | 10MM | 1 | 1 | 24 | 3.5 | 0.6 |  | 4.1 | 98.4 |  | 98.4
| chair | 12MM | 1 | 1 | 9 | 0.7 | 1.5 |  | 2.2 | 19.8 |  |  | 19.8
| PEDISTAL | 12MM | 1 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 25 |  |  | 25
| RING | 8MM | 1 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 29.88 | 29.88
| F4 | 16MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 |  |  |  | 499.5
|  | 16MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 |  |  |  | 499.5
| TOP | 10MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 | 499.5
|  | 10MM | 5 | 1 | 27 | 3.1 | 0.6 |  | 3.7 | 499.5 | 499.5
| chair | 12MM | 5 | 1 | 10 | 0.7 | 1.5 |  | 2.2 | 110 |  |  | 110
| PEDISTAL | 12MM | 5 | 1 | 20 | 0.85 | 0.4 |  | 1.25 | 125 |  |  | 125
| RING | 8MM | 5 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 149.4 | 149.4
| F5 | 20MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  |  |  |  | 410
|  | 20MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  |  |  |  | 410
| TOP | 10MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  | 410
|  | 10MM | 4 | 1 | 25 | 3.5 | 0.6 |  | 4.1 | 410 |  | 410
| chair | 12MM | 4 | 1 | 12 | 0.7 | 1.5 |  | 2.2 | 105.6 |  |  | 105.6
| PEDISTAL | 12MM | 4 | 1 | 20 | 1.075 | 0.4 |  | 1.475 | 118 |  |  | 118
| RING | 8MM | 4 | 1 | 6 | 4.88 | 0.1 |  | 4.98 | 119.52 | 119.52
[9 empty] | 0 | 0
| COL C1 | 25MM | 5 | 1 | 16 | 2.425 | 0.4 |  | 2.825 | 226 | [5 empty] | 226
|  |  | 5 | 1 | 16 | 2.425 | 0.4 |  | 2.825 | 226 | [5 empty] | 226
| RING | 8MM | 5 | 2 | 13 | 3.28 | 0.1 |  | 3.38 | 439.4 | 439.4
|  |  | 5 | 2 | 13 | 3.28 | 0.1 |  | 3.38 | 439.4 | 439.4
|  |  | 10 | 2 | 13 | 2.52 | 0.1 |  | 2.62 | 681.2 |  | 681.2
|  |  | 10 | 2 | 13 | 0.98 |  |  | 0.98 | 254.8 |  | 254.8
| C2 | 25mm | 2 | 1 | 8 | 2.4 | 0.4 |  | 2.8 | 44.8 | [5 empty] | 44.8
|  | 8mm | 2 | 2 | 13 | 1.48 | 0.1 |  | 1.58 | 82.16 | 82.16
|  | 8mm | 2 | 2 | 13 | 0.89 | 0.1 |  | 0.99 | 51.48 | 51.48
| C3 | 25mm | 2 | 1 | 4 | 2.4 | 0.4 |  | 2.8 | 22.4 | [5 empty] | 22.4
|  | 20mm | 2 | 1 | 4 | 2.4 | 0.4 |  | 2.8 | 22.4 |  |  |  |  | 22.4
|  | 8mm | 2 | 2 | 13 | 1.48 | 0.1 |  | 1.58 | 82.16 | 82.16
|  | 8mm | 2 | 2 | 13 | 0.89 | 0.1 |  | 0.99 | 51.48 | 51.48
[11 empty] | 2537.24 | 2335.3 | 690.56 | 1477.5 | 842.4 | 519.2
[11 empty] | 0.395 | 0.62 | 0.888 | 1.58 | 2.47 | 3.87
[11 empty] | 1002.2098 | 1447.886 | 613.2173 | 2334.45 | 2080.728 | 2009.304
[11 empty] | TOTAL | 9487.7951
[11 empty] | TOTAL | 9.4878
0--3
| COL C1 | 25MM | 5 | 1 | 16 | 1.2 | 0.4 | 1.225 | 2.825 | 226 | [5 empty] | 226
|  | 25MM | 5 | 1 | 16 | 1.2 | 0.4 | 1.225 | 2.825 | 226 | [5 empty] | 226
| RING | 8MM | 5 | 2 | 7 | 3.28 | 0.1 |  | 3.38 | 236.6 | 236.6
|  | 8MM | 5 | 2 | 7 | 3.28 | 0.1 |  | 3.38 | 236.6 | 236.6
|  | 8MM | 10 | 2 | 7 | 2.52 | 0.1 |  | 2.62 | 366.8 | 366.8
|  | 8MM | 10 | 2 | 7 | 0.98 |  |  | 0.98 | 137.2 | 137.2
| C2 | 25mm | 2 | 1 | 8 | 1.2 | 0.4 | 1.225 | 2.825 | 45.2 | [5 empty] | 45.2
|  | 8mm | 2 | 2 | 7 | 1.48 | 0.1 |  | 1.58 | 44.24 | 44.24
|  | 8mm | 2 | 2 | 7 | 0.89 | 0.1 |  | 0.99 | 27.72 | 27.72
| C3 | 25mm | 2 | 1 | 4 | 1.2 | 0.4 | 1.225 | 2.825 | 22.6 | [5 empty] | 22.6
|  | 20mm | 2 | 1 | 4 | 1.2 | 0.4 | 1 | 2.6 | 20.8 |  |  |  |  | 20.8
|  | 8mm | 2 | 2 | 7 | 1.48 | 0.1 |  | 1.58 | 44.24 | 44.24
|  | 8mm | 2 | 2 | 7 | 0.89 | 0.1 |  | 0.99 | 27.72 | 27.72 | [6 empty] | 148
| P BEAM | [7 empty] | 0 | 0
| PB1 A | 20mm | 1 | 2 | 3 | 47.2 | 0.4 | 5 | 52.6 | 315.6 |  |  |  |  | 315.6
| EXT | 16 | 1 | 2 | 2 | 4 | 0.4 |  | 4.4 | 17.6 |  |  |  | 17.6
|  | 16 | 1 | 3 | 2 | 7 |  |  | 7 | 42 |  |  |  | 42
| RING | 8 | 1 | 1 | 189 | 1.6 | 0.1 |  | 1.7 | 321.3 | 321.3
[9 empty] | 0 | 0
| PB1 A | 20mm | 1 | 2 | 3 | 37.2 | 0.8 | 5 | 43 | 258 |  |  |  |  | 258
| EXT | 16 | 1 | 2 | 2 | 4 | 0.8 |  | 4.8 | 19.2 |  |  |  | 19.2
|  | 16 | 1 | 2 | 2 | 7 |  |  | 7 | 28 |  |  |  | 28
| RING | 8 | 1 | 1 | 148 | 1.6 | 0.1 |  | 1.7 | 251.6 | 251.6
| PB2 | 20 | 4 | 2 | 3 | 13.2 | 0.8 | 1 | 15 | 360 |  |  |  |  | 360 |  |  | 65
| EXT | 16 | 4 | 1 | 2 | 3.5 | 0.4 |  | 3.9 | 31.2 |  |  |  | 31.2
| RING | 8 | 4 | 1 | 66 | 1.6 | 0.1 |  | 1.7 | 448.8 | 448.8
| PB1 1" | 20 | 1 | 2 | 3 | 12.75 | 0.4 | 1 | 14.15 | 84.9 |  |  |  |  | 84.9
|  | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 64 | 1.6 | 0.1 |  | 1.7 | 108.8 | 108.8
| PB1 1" | 20 | 1 | 2 | 3 | 10.4 | 0.4 | 1 | 11.8 | 70.8 |  |  |  |  | 70.8
| 1---1" | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 58 | 1.6 | 0.1 |  | 1.7 | 98.6 | 98.6
[9 empty] | 0 | 0
| PB1 1" | 20 | 1 | 2 | 3 | 6.7 | 0.4 |  | 7.1 | 42.6 |  |  |  |  | 42.6
| 1 | 16 | 1 | 2 | 2 | 3.5 | 0.4 |  | 3.9 | 15.6 |  |  |  | 15.6
|  | 8 | 1 | 1 | 35 | 1.6 | 0.1 |  | 1.7 | 59.5 | 59.5
[11 empty] | 2409.72 | 0 | 0 | 184.8 | 1152.7 | 519.8
[11 empty] | 0.395 | 0.62 | 0.888 | 1.58 | 2.47 | 3.87
[11 empty] | 951.8394 | 0 | 0 | 291.984 | 2847.169 | 2011.626
[11 empty] | TOTAL | 6102.6184
[11 empty] | TOTAL | 6.1026