## Abstract
To
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Estimate
ACC
Sl No | Description | UOM | Rate | Upto Prev Bill |  | Estimated Value
|  |  |  | Quantity | Amount | Quantity | Amount
1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 |  |  | 1180.344 | 212461.92
2 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 |  |  | 236.0688 | 51935.136
3 | Soil Dressing | m2 | 60 |  |  | 393.448 | 23606.88
4 | Hard Rock breaking 0--3 Mtr | m3 | 1050 |  |  | 0
5 | Backfilling | m3 | 80 |  |  | 1136.5581 | 90924.6452
6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 all heights and depths above and below pliths to require materials, tools and plants, labour complete 0 to 3 Mtr | m3 | 2300 |  |  | 5.7779 | 13289.2045
7 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 all heights and depths above and below pliths to require materials, tools and plants, labour complete 3 to 6 Mtr | m3 | 2599 |  |  | 23.6918 | 61574.9882
8 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 |  |  | 175.6062 | 545696.2665
9 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 |  |  | 74.7788 | 205641.7536
10 | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering 0 to +/- 3M. | m2 | 400 |  |  | 402.0261 | 160810.452
11 | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering+/- 3M to +/- 6 Mtr | m2 | 452 |  |  | 64.251 | 29041.452
12 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 |  |  | 20.6776 | 186098.6705
13 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 |  |  | 8.8052 | 89548.945
[5 empty] | 0 |  | 1670630.3135

## Measurement Sheet
To
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Estimate
Boiler
Sl No | Description | Block | Struc. | Grid | RL |  | L | B | H | Nos | Qnty | Unit | Ref
[5 empty] | From | To
Excavation & Backfilling
Excavation
1 | 0--3 Mtr | Boiler | Foundation |  | 91.5 | 94.5 | 26.3 | 13.6 | 3 | 1 | 1073.04 | Cum
| Total | [9 empty] | 1073.04 | Cum
1 | 3--6 Mtr | Boiler | Foundation |  | 90.9 | 91.5 | 26.3 | 13.6 | 0.6 | 1 | 214.608 | Cum
| Total | [9 empty] | 214.608 | Cum
Hard Rock Breaking
Hard Rock breaking
Hard Rock breaking
Hard Rock breaking
Dressing & Levelling
4 | Soil Dressing | Boiler |  |  | 90.9 | 90.9 | 26.3 | 13.6 |  | 1 | 357.68 | Sqm
| Total | [9 empty] | 357.68 | Sqm
Backfilling
5 | Total Excavation | Boiler | [8 empty] | 1287.648
| Deduction of RCC | Boiler | [8 empty] | 26.7906
| Deduction of PCC | Boiler | [8 empty] | 227.6227
| Total Backfilling | [9 empty] | 1033.2346 | m3
Plain & Reinforced Cement Concrete
PCC
6 | 3--6 Mtr | Boiler | Raft | NA | 90.9 | 91 | 24.2 | 8.9 | 0.1 | 1 | 21.538 | Cum
| Total 3--6 Mtr | [9 empty] | 21.538 | Cum
| (0) to (+3) Mtr | Boiler | PB1 |  | 93.9 | 94 | 18.125 | 0.5 | 0.1 | 2 | 1.8125 | Cum
| (0) to (+3) Mtr | Boiler | PB2 | 9--1 | 93.9 | 94 | 2.684 | 0.5 | 0.1 | 6 | 0.8052 | Cum
| (0) to (+3) Mtr | Boiler | PB2 | 7--3 | 93.9 | 94 | 2.425 | 0.5 | 0.1 | 3 | 0.36375 | Cum
| (0) to (+3) Mtr | Boiler | PB3 |  | 93.9 | 94 | 9.413 | 0.5 | 0.1 | 2 | 0.9413 | Cum
| (0) to (+3) Mtr | Boiler | PB4 |  | 93.9 | 94 | 5.049 | 0.5 | 0.1 | 2 | 0.5049 | Cum
| (0) to (+3) Mtr | Boiler | PB5 |  | 93.9 | 94 | 8.25 | 0.5 | 0.1 | 2 | 0.825 | Cum
| Total 0--3 Mtr | [9 empty] | 5.2527 | Cum
RCC
7 | (0) to (-3) Mtr | Boiler | PB1 |  | 94 | 94.55 | 18.125 | 0.3 | 0.55 | 2 | 5.9813 | Cum
| (0) to (-3) Mtr | Boiler | PB2 | 9--1 | 94 | 94.55 | 2.684 | 0.3 | 0.55 | 6 | 2.6572 | Cum
| (0) to (-3) Mtr | Boiler | PB2 | 7--3 | 94 | 94.55 | 2.425 | 0.3 | 0.55 | 3 | 1.2004 | Cum
| (0) to (-3) Mtr | Boiler | PB3 |  | 94 | 94.55 | 9.413 | 0.3 | 0.55 | 2 | 3.1063 | Cum
| (0) to (-3) Mtr | Boiler | PB4 |  | 94 | 94.55 | 5.049 | 0.3 | 0.55 | 2 | 1.6662 | Cum
| (0) to (-3) Mtr | Boiler | PB5 |  | 94 | 94.55 | 8.25 | 0.3 | 0.55 | 2 | 2.7225 | Cum
| (0) to (-3) Mtr | Boiler | C1 |  | 91.75 | 95.25 | 0.95 | 0.95 | 3.5 | 8 | 25.27 | Cum
| (0) to (-3) Mtr | Boiler | C2 |  | 91.75 | 95.25 | 0.75 | 0.75 | 3.5 | 12 | 23.625 | Cum
| (0) to (+3) Mtr | Boiler | C3 |  | 91.6 | 95.25 | 0.4 | 0.4 | 3.65 | 3 | 1.752 | Cum
| Total 0 to +/- 3 Mtr | [9 empty] | 67.9807 | Cum
| (-3) to (-6) Mtr | Boiler | Raft |  | 91 | 91.75 | 24 | 8.7 | 0.75 | 1 | 156.6
| (-3) to (-6) Mtr | Boiler | F 2 |  | 91 | 91.6 | 1.3 | 1.3 | 0.6 | 3 | 3.042
| Total +/- 3 to +/- 6 Mtr | [9 empty] | 159.642 | Cum
Formwork & Shuttering
| (0) to (-3) Mtr | Boiler | PB1 |  | 94 | 94.55 | 18.125 |  | 0.55 | 4 | 39.875 | Sqm
| (0) to (-3) Mtr | Boiler | PB2 | 9--1 | 94 | 94.55 | 2.684 |  | 0.55 | 12 | 17.7144 | Sqm
| (0) to (-3) Mtr | Boiler | PB2 | 7--3 | 94 | 94.55 | 2.425 |  | 0.55 | 6 | 8.0025 | Sqm
| (0) to (-3) Mtr | Boiler | PB3 |  | 94 | 94.55 | 9.413 |  | 0.55 | 4 | 20.7086 | Sqm
| (0) to (-3) Mtr | Boiler | PB4 |  | 94 | 94.55 | 5.049 |  | 0.55 | 4 | 11.1078 | Sqm
| (0) to (-3) Mtr | Boiler | PB5 |  | 94 | 94.55 | 8.25 |  | 0.55 | 4 | 18.15 | Sqm
| (0) to (-3) Mtr | Boiler | C1 |  | 91.75 | 95.25 | 0.95 |  | 3.5 | 16 | 53.2 | Sqm
| (0) to (-3) Mtr | Boiler | C2 |  | 91.75 | 95.25 | 0.75 |  | 3.5 | 24 | 63 | Sqm
| (0) to (+3) Mtr | Boiler | C3 |  | 91.6 | 95.25 | 0.4 |  | 3.65 | 6 | 8.76 | Sqm
Sqm
| (0) to (-3) Mtr | Boiler | C1 |  | 91.75 | 95.25 |  | 0.95 | 3.5 | 16 | 53.2 | Sqm
| (0) to (-3) Mtr | Boiler | C2 |  | 91.75 | 95.25 |  | 0.75 | 3.5 | 24 | 63 | Sqm
| (0) to (+3) Mtr | Boiler | C3 |  | 91.6 | 95.25 |  | 0.4 | 3.65 | 6 | 8.76 | Sqm
| Total 0 to +/- 3 Mtr | [9 empty] | 365.4783 | Sqm
| (-3) to (-6) Mtr | Boiler | Raft |  | 91 | 91.75 | 24 |  | 0.75 | 2 | 36
| (-3) to (-6) Mtr | Boiler | F 2 |  | 91 | 91.6 | 1.3 |  | 0.6 | 6 | 4.68
| (-3) to (-6) Mtr | Boiler | Raft |  | 91 | 91.75 |  | 8.7 | 0.75 | 2 | 13.05
| (-3) to (-6) Mtr | Boiler | F 2 |  | 91 | 91.6 |  | 1.3 | 0.6 | 6 | 4.68
| Total 0 to +/- 3 Mtr | [9 empty] | 58.41 | Sqm