## Abstract
To
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Estimate
ESP
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill Claimed |  | Estimated Value
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | [5 empty] | 764.0949 | 137537.0785
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | [5 empty] | 152.819 | 33620.1748
3 |  | Soil Dressing | m2 | 60 | [5 empty] | 109.0281 | 6541.683
4 |  | Backfilling | m3 | 80 | [5 empty] | 853.4549 | 68276.3892
5 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 all heights and depths above and below pliths to require materials, tools and plants, labour complete 3 to 6 Mtr | m3 | 2599 | [5 empty] | 10.9028 | 28336.3902
6 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | [5 empty] | 35.3125 | 109733.5938
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | [5 empty] | 52.5562 | 144529.5142
7 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering 0 to +/- 3M. | m2 | 400 | [5 empty] | 208.52 | 83408.012
8 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering+/- 3M to +/- 6 Mtr | m2 | 452 | [5 empty] | 141.25 | 63845
9 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | [5 empty] | 3.4611 | 31149.5913
10 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | [5 empty] | 4.4917 | 45681.0975
[7 empty] | 0 |  | 0 |  | 752658.5245

## Measurement Sheet
Sl No | Description | Block | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit
[5 empty] | From | To
Excavation & Backfilling
1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | ESP | Raft |  | 94.5 | 91.5 | 22.02 | 10.236 | 3 | 1 | 676.1902 | Cum
| Total | [9 empty] | 676.1902
2 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | ESP | Raft |  | 91.5 | 90.9 | 22.02 | 10.236 | 0.6 | 1 | 135.238 | Sqm
| Total | [9 empty] | 135.238
Soil Dressing
3 | Soil Dressing | ESP | Footing |  | 90.9 | 90.9 | 2.7 | 2.7 |  | 10 | 72.9
| Soil Dressing | ESP | Plinth Beam(long) |  | 93.85 | 93.85 | 12.62 | 0.5 |  | 2 | 12.62
| Soil Dressing | ESP | Plinth Beam (short) |  | 93.85 | 93.85 | 4.386 | 0.5 |  | 5 | 10.965
| Backfilling | [9 empty] | 96.485
4 | Total Excavation | [9 empty] | 811.4282
| Deduction of cooling tower upto NGL | [9 empty] | 46.5099
| Deduction of PCC | [9 empty] | 9.6485
[11 empty] | 755.2698 | m3
Plain & reinforced Cement Concrete
5 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 all heights and depths above and below pliths to require materials, tools and plants, labour complete 3 to 6 Mtr | ESP | Footing |  | 90.9 | 91 | 2.7 | 2.7 | 0.1 | 10 | 7.29 | Cum
|  | ESP | Plinth Beam(long) |  | 93.85 | 93.95 | 12.62 | 0.5 | 0.1 | 2 | 1.262 | Cum
|  | ESP | Plinth Beam (short) |  | 93.85 | 93.95 | 4.386 | 0.5 | 0.1 | 5 | 1.0965 | Cum
[11 empty] | 9.6485 | Cum
6 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | ESP | Footing |  | 91 | 91.5 | 2.5 | 2.5 | 0.5 | 10 | 31.25 | Cum
31.25
7 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | ESP | Footing |  | 91.5 | 91.75 | 2.5 | 2.5 | 0.25 | 10 | 15.625 | Cum
|  | ESP | Column |  | 91.75 | 94.8 | 0.85 | 0.85 | 3.05 | 10 | 22.0362 | Cum
|  | ESP | Plinth Beam(long) |  | 93.95 | 94.5 | 12.62 | 0.3 | 0.55 | 2 | 4.1646 | Cum
|  | ESP | Plinth Beam (short) |  | 93.95 | 94.5 | 4.386 | 0.3 | 0.55 | 5 | 3.6184 | Cum
|  | ESP | Footing F2 |  | 94 | 94.8 | 1.665 | 0.8 | 0.8 | 1 | 1.0656 | Cum
46.5099
Formwork (Shuttering)
8 | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering 0 to +/- 3M. | ESP | Footing |  | 91.5 | 91.75 | 2.5 |  | 0.25 | 20 | 12.5 | Cum
|  | ESP | Column |  | 91.75 | 94.8 | 0.85 |  | 3.05 | 20 | 51.85 | Cum
|  | ESP | Footing F2 |  | 94 | 94.8 | 1.665 |  | 0.8 | 2 | 2.664 | Cum
|  | ESP | Footing |  | 91.5 | 91.75 |  | 2.5 | 0.25 | 20 | 12.5 | Cum
|  | ESP | Column |  | 91.75 | 94.8 |  | 0.85 | 3.05 | 20 | 51.85 | Cum
|  | ESP | Plinth Beam(long) |  | 93.95 | 94.5 | 12.62 |  | 0.55 | 4 | 27.764 | Cum
|  | ESP | Plinth Beam (short) |  | 93.95 | 94.5 | 4.386 |  | 0.55 | 10 | 24.123 | Cum
|  | ESP | Footing F2 |  | 94 | 94.8 |  | 0.8 | 0.8 | 2 | 1.28 | Cum
[11 empty] | 184.531 | Sqm
9 | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering+/- 3M to +/- 6 Mtr | ESP | Footing |  | 91 | 91.5 | 2.5 | 2.5 | 0.5 | 40 | 125 | Sqm
[11 empty] | 125 | Sqm