## RA1
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-8th July 2023
Work order No: SNIPIPL/WO/2022-23/041 | [9 empty] | Date of Finalizing-10th August 2023
Bill No RA1
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Day Bin | 160 | m3 | [6 empty] | 0 | 0
2 | 2 | Backfilling in all posisison & hieght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Day Bin | 85 | m3 | [6 empty] | 0 | 0
3 | 2 (a) | Ordinary filling (Typeof Backfilling) in layers in 300 mm of thickness as specified with watering and normal compaction | Day Bin | 60 | m3 |  |  |  |  | 151.37 | 9082.2 | 151.37 | 9082.2
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (0--3)Mtr | Day Bin | 2300 | m3 | [6 empty] | 0 | 0
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (3--6) Mtr | Day Bin | 2530 | m3 |  |  |  |  | 74.06 | 187371.8 | 74.06 | 187371.8
5 | 7 | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | Day Bin | 2750 | m3 | [6 empty] | 0 | 0
| E | Formwork (Shuttering)
8 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | Day Bin | 400 | m2 | [6 empty] | 0 | 0
9 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | Day Bin | 440 | m2 |  |  |  |  | 16.17 | 7114.8 | 16.17 | 7114.8
Soling Hardcore & Others
10 | 33 | Providing and fixing of PVC water bar 230 | Day Bin |  | M | [6 empty] | 0 | 0
11 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Day Bin |  | m2 | [6 empty] | 0 | 0
12 |  | Pocket Fixing work | Day Bin |  | Nos | [6 empty] | 0 | 0
| C | REINFORCEMENT WORK
13 | 16 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Day Bin |  | MT | [6 empty] | 0 | 0
| * | Total | [6 empty] | 0 |  | 203568.8 |  | 203568.8
2234195.1429

## RA 2
Nakoda Pipe Implex | [12 empty] | Bill No RA2
Tilda, Chattisgarh | [9 empty] | Date of Submission-8th August 2023
Work order No: SNIPIPL/WO/2022-23/041 | [9 empty] | Date of Finalizing-10th August 2023
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Day Bin | 180 | m3 | [6 empty] | 0 | 0
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Day Bin | 85 | m3 | [6 empty] | 0 | 0
3 | 2 (a) | Watering & Consolidation | Day Bin | 60 | m3 |  |  | 151.37 | 9082.2 |  |  | 151.37 | 9082.2
|  | Soil Dressing | Day Bin | 25 | m2 |  |  |  |  | 504.56 | 12614 | 504.56 | 12614
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (0--3)Mtr | Day Bin | 2300 | m3 | [6 empty] | 0 | 0 | 775 | 139.5 | 914.5
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (3--6) Mtr | Day Bin | 2530 | m3 |  |  | 74.06 | 187371.8 |  |  | 74.06 | 187371.8 |  |  |  | \
6 | 13 | RCC Work(0--3)Mtr | Day Bin | 2750 | m3 | [6 empty] | 0 | 0
7 | 11 | RCC Work(3--6)Mtr | Day Bin | 3025 | m3 | [6 empty] | 0 | 0
7 | 11 | RCC Work(3--6)Mtr | Day Bin | 3300 | m3 |  |  |  |  | 289.8 | 956340 | 289.8 | 956340
| E | Formwork (Shuttering)
8 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | Day Bin | 400 | m2 | [6 empty] | 0 | 0
9 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | Day Bin | 440 | m2 |  |  | 16.17 | 7114.8 |  |  | 16.17 | 7114.8
|  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | Day Bin | 480 | m2 |  |  |  |  | 80.67 | 38721.6 | 80.67 | 38721.6
Soling Hardcore & Others
10 | 33 | Providing and fixing of PVC water bar 230 | Day Bin | 220 | M | [6 empty] | 0 | 0
11 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Day Bin | 130 | m2 | [6 empty] | 0 | 0
12 |  | Pocket Fixing work | Day Bin | 500 | Nos | [6 empty] | 0 | 0
| C | REINFORCEMENT WORK
13 | 16 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.(0--3)Mtr | Day Bin | 8500 | MT | [6 empty] | 0 | 0
|  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.(3--6)Mtr | Day Bin | 9350 | MT
|  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. (6--9) Mtr | Day Bin | 10200 | MT |  |  |  |  | 100.2893 | 1022950.7429
| * | Total | [6 empty] | 203568.8 |  | 2030626.3429 |  | 1211244.4
2234195.1429
2140498.86
93696.2829

## RA 3
Nakoda Pipe Implex | [12 empty] | Bill No RA3
Tilda, Chattisgarh | [9 empty] | Date of Submission-8th September 2023
Work order No: SNIPIPL/WO/2022-23/041 | [9 empty] | Date of Finalizing-8th September 2023
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
| A | Earthwork & Filling
1 | 1 (a) | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all hieghts and descents within a lead upto 1000 Mtr including all | Day Bin | 180 | m3 |  |  | 0 |  |  | 0 | 0 | 0
2 | 2 | Backfilling in all posisison & hieeght & descent in foundation, pits, pie trenches, tunnel, sewer line around foundation & structures etc with approved material within a lead f 1000 M including reclaiming from spoil heapsat all hieght transporting, depositing and dressing completed as directed | Day Bin | 85 | m3 |  |  | 0 |  | 2311.689 | 196493.565 | 2311.689 | 196493.565
3 | 2 (a) | Watering & Consolidation | Day Bin | 60 | m3 |  |  | 151.37 | 9082.2 |  | 0 | 151.37 | 9082.2
|  | Soil Dressing | Day Bin | 25 | m2 |  |  | 504.56 | 12614 | 104.205 | 2605.125 | 608.765 | 15219.125
| B | Plain & reinforced Cement Concrete
4 | 6 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (0--3)Mtr | Day Bin | 2300 | m3 |  |  | 0 |  | 7.7435 | 17810.05 | 7.7435 | 17810.05
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) (3--6) Mtr | Day Bin | 2530 | m3 |  |  | 74.06 | 187371.8 |  | 0 | 74.06 | 187371.8
6 | 13 | RCC Work(0--3)Mtr | Day Bin | 2750 | m3 |  |  | 0 | 0 | 205.3177 | 564623.8125 | 205.3177 | 564623.8125
7 | 11 | RCC Work(3--6)Mtr | Day Bin | 3025 | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
7 | 11 | RCC Work(3--6)Mtr | Day Bin | 3300 | m3 |  |  | 289.8 | 956340 |  | 0 | 289.8 | 956340
| E | Formwork (Shuttering)
8 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | Day Bin | 400 | m2 |  |  | 0 |  | 558.507 | 223402.8 | 558.507 | 223402.8
9 | 21 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | Day Bin | 440 | m2 |  |  | 16.17 | 7114.8 |  | 0 | 16.17 | 7114.8
|  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | Day Bin | 480 | m2 |  |  | 80.67 | 38721.6 |  | 0 | 80.67 | 38721.6
Soling Hardcore & Others
10 | 33 | Providing and fixing of PVC water bar 230 | Day Bin | 220 | M |  |  | 0 |  |  |  | 0 | 0
11 | 57 | Trimix flooring with vaccum dewatering including finishing power trowel | Day Bin | 130 | m2 |  |  | 0 |  |  |  | 0 | 0
12 |  | Pocket Fixing work | Day Bin | 500 | Nos |  |  | 0 |  |  |  | 0 | 0
| C | REINFORCEMENT WORK
13 | 16 | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.(0--3)Mtr | Day Bin | 8500 | MT |  |  | 0 |  | 14.1486 | 120263.1377 | 14.1486 | 120263.1377
|  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.(3--6)Mtr | Day Bin | 9350 | MT | [5 empty] | 0
|  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. (6--9) Mtr | Day Bin | 10200 | MT | [5 empty] | 0
| * | Total | [6 empty] | 1211244.4 |  | 1125198.4902 |  | 2336442.8902

## RA 3 Measurement
To Nakoda Pipe Impex Pvt Ltd | [7 empty] | Bill No:- RA 5
Structure:- Day Bin | [7 empty] | Mill Month:- August 2023
Vendor:- AGI
DESCRIPTION | Structure | Grid | NOS | L | B | H/D | QTY | REMARK
1. Back Filling Work
| D-Bin Building |  | 1 | 49 | 16.7 | 3.53 | 2888.599 | Cum
| Deduction For Pcc Qty. | [5 empty] | -74.06 | Cum
| Deduction For RCC Raft Qty. | [5 empty] | -289.8 | Cum
| Deduction For RCC Raft Beam Qty. | [5 empty] | -133.2 | Cum
| Deduction For RCC Column Qty. | [5 empty] | -37.13 | Cum
| Deduction For PCC Plinth Beam Qty. | [5 empty] | -7.74 | Cum
| Deduction For RCC Plinth Beam Qty. | [5 empty] | -34.98 | Cum
Total Qty. for Back Filling Work | [6 empty] | 2311.689 | Cum
2. Dressing Work
| Below Plinth Beam PB1-Grid-1-A-B-10-A-B |  | 2 | 7 | 0.8 |  | 11.2
| Below Plinth Beam PB1-Grid-A-B-2-9 |  | 8 | 6.9 | 0.8 |  | 44.16
| Below Plinth Beam PB1-Grid-A-B-11 |  | 1 | 7.15 | 0.8 |  | 5.72
| Below Plinth Beam PB1-Grid-A-B |  | 2 | 28.75 | 0.75 |  | 43.125
Total Qty. for Dressing Work | [6 empty] | 104.205 | Sqm
3. PCC Work
0--3 Mtr | Below Plinth Beam PB1-Grid-1-A-B-10-A-B |  | 2 | 7 | 0.6 | 0.1 | 0.84
0--3 Mtr | Below Plinth Beam PB1-Grid-A-B-2-9 |  | 8 | 6.9 | 0.6 | 0.1 | 3.312
0--3 Mtr | Below Plinth Beam PB1-Grid-A-B-11 |  | 1 | 7.15 | 0.6 | 0.1 | 0.429
0--3 Mtr | Below Plinth Beam PB2-Grid-A-B |  | 2 | 28.75 | 0.55 | 0.1 | 3.1625
Total Qty. for PCC Work | [6 empty] | 7.7435 | CUM
4. RCC Work
0--3 Mtr | Raft Beam -RB1 | A1/A11 & B1/B11 | 2 | 42 | 1.1 | 0.65 | 60.06
0--3 Mtr | Raft Beam -RB1 |  | 11 | 11.5 | 1.1 | 0.65 | 90.4475
0--3 Mtr | Column Deduction C1 |  | -22 | 1.1 | 1.1 | 0.65 | -17.303
0--3 Mtr | 1st Lift Column C1up to plinth beam top(0.90+0.75=1.65) |  | 16 | 1.1 | 1 | 1.65 | 29.04
0--3 Mtr | 1st Lift Column C2up to plinth beam top |  | 4 | 1 | 0.95 | 1.65 | 6.27
0--3 Mtr | 1st Lift Column C3up to plinth beam top |  | 2 | 0.65 | 0.85 | 1.65 | 1.8232
0--3 Mtr | Plinth Beam PB1-Grid-1-A-B-10-A-B |  | 2 | 7 | 0.4 | 0.75 | 4.2
0--3 Mtr | Plinth Beam PB1-Grid-A-B-2 TO 9 |  | 8 | 6.9 | 0.4 | 0.75 | 16.56
0--3 Mtr | Plinth Beam PB1-Grid-A-B-11 |  | 1 | 7.15 | 0.4 | 0.75 | 2.145
0--3 Mtr | Plinth Beam PB2-Grid-A-B-1-2-9-10 |  | 4 | 3.025 | 0.35 | 0.6 | 2.541
0--3 Mtr | Plinth Beam PB2-Grid-A-B-2 to9 |  | 14 | 3 | 0.35 | 0.6 | 8.82
0--3 Mtr | Plinth Beam PB2-Grid-A-B-10-11 |  | 2 | 1.7 | 0.35 | 0.6 | 0.714
Total Qty. for PCC Work | [6 empty] | 205.3177 | CUM
5. Shuttring Work
0--3 Mtr | Raft Beam -RB1 Grid -A-B |  | 4 | 42 |  | 0.65 | 109.2
0--3 Mtr | Stoper |  | 4 | 1.1 |  | 0.65 | 2.86
0--3 Mtr | Inner side Beam Deduction |  | -22 | 1.16 |  | 0.65 | -16.588
0--3 Mtr | Raft Beam -RB1 Grid -A-B-1 to 11 |  | 22 | 11.5 |  | 0.65 | 164.45
0--3 Mtr |  |  | -44 | 1.1 |  | 0.65 | -31.46
0--3 Mtr | 1st Lift Column C1up to plinth beam top(0.90+0.75=1.65)(1.1+1.1+1+1=4.20) |  | 16 | 4.2 |  | 1.65 | 110.88
0--3 Mtr | 1st Lift Column C2up to plinth beam top(1+1+0.95+0.95=3.90) |  | 4 | 3.9 |  | 1.65 | 25.74
0--3 Mtr | 1st Lift Column C3up to plinth beam top(0.65+0.65+0.85+0.85=3.0) |  | 2 | 3 |  | 1.65 | 9.9
0--3 Mtr | Plinth Beam PB1-Grid-1-A-B-10-A-B |  | 4 | 7 |  | 0.75 | 21
0--3 Mtr | Plinth Beam PB1-Grid-A-B-2 TO 9 |  | 16 | 6.9 |  | 0.75 | 82.8
0--3 Mtr | Plinth Beam PB1-Grid-A-B-11 |  | 2 | 7.15 |  | 0.75 | 10.725
0--3 Mtr | Plinth Beam PB2-Grid-A-B-1-2-9-10 |  | 8 | 3.025 |  | 0.6 | 14.52
0--3 Mtr | Plinth Beam PB2-Grid-A-B-2 to9 |  | 28 | 3 |  | 0.6 | 50.4
0--3 Mtr | Plinth Beam PB2-Grid-A-B-10-11 |  | 4 | 1.7 |  | 0.6 | 4.08
Total Qty. for Shuttring Work | [6 empty] | 558.507 | SQM

## RA 3 BBS
BAR BENDING SCHEDULE (D-BIN)-3RD RA AUG-2023
S.No | Structure | Description | Dia in MM | No of member | No. of Bar | Cutting Length | DIA WISE LENGTH OF REINFORCEMENT IN METER
[7 empty] | 8MM | 10MM | 12MM | 16MM | 20MM | 25MM | 32MM
| C1 | Up To Plinth Beam Top
|  | VERTICAL BAR | 25 | 16 | 13 | 3.35 | [5 empty] | 696.8
|  | VERTICAL BAR | 25 | 16 | 13 | 3.35 | [5 empty] | 696.8
|  | RING-10 MM DIA-200 C/C TO RAFT TOP | 10 | 16 | 6 | 4.08 |  | 391.68
|  | RING-10 MM DIA-200 C/C | 10 | 16 | 5 | 2.91 |  | 232.8
|  | RING-10 MM DIA-200 C/C | 10 | 16 | 5 | 2.852 |  | 228.16
| COLUMN -C2 | (1.0X0.95)
|  | VERTICAL BAR | 25 | 4 | 12 | 3.35 | [5 empty] | 160.8
|  | VERTICAL BAR | 25 | 4 | 12 | 3.35 | [5 empty] | 160.8
|  | RING-10 MM DIA-200 C/C TO RAFT TOP | 10 | 4 | 6 | 3.74 |  | 89.76
|  | RING-10 MM DIA-200 C/C | 10 | 4 | 5 | 2.552 |  | 51.04
|  | RING-10 MM DIA-200 C/C | 10 | 4 | 5 | 2.62 |  | 52.4
COLUMN -C3(0.65X0.85)
|  | VERTICAL BAR | 20 | 2 | 10 | 3.35 |  |  |  |  | 67
|  | VERTICAL BAR | 20 | 2 | 10 | 3.35 |  |  |  |  | 67
|  | RING-10 MM DIA-200 C/C TO RAFT TOP | 10 | 2 | 6 | 2.88 |  | 34.56
|  | RING-10 MM DIA-200 C/C | 10 | 2 | 5 | 1.852 |  | 18.52
PLINTH BEAM PB1
|  | BOTTOM & TOP BAR | 20 | 11 | 12 | 9.7 |  |  |  |  | 1280.4
|  | SPACER BAR | 20 | 11 | 8 | 0.4 |  |  |  |  | 35.2
|  | MIDDLE BAR | 16 | 11 | 4 | 8.9 |  |  |  | 391.6
|  | RING-200 C/C | 10 | 11 | 36 | 2.3 |  | 910.8
PLINTH BEAM PB2
|  | BOTTOM & TOP BAR | 20 | 2 | 8 | 40 |  |  |  |  | 640
|  | OVERLAP | 20 | 2 | 24 | 1 |  |  |  |  | 48
|  | SPACER BAR | 20 | 2 | 29 | 0.4 |  |  |  |  | 23.2
|  | RING-200 C/C | 10 | 2 | 144 | 1.9 |  | 547.2
[6 empty] | RMT | 0 | 2556.92 | 0 | 391.6 | 2160.8 | 1715.2 | 0
[6 empty] | UNIT. W | 0.395 | 0.617 | 0.888 | 1.58 | 2.469 | 3.858 | 6.32
[7 empty] | 0 | 1577.6196 | 0 | 618.728 | 5335.0152 | 6617.2416 | 0
[7 empty] | TOTAL.MT |  | 14148.6044
[5 empty] | Total Qty.Mt |  |  | A | 14.1486