## RA 1
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-10th April 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-17tth April 2023
Bill No RA1
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 0 to 3 Mtr hieghts and descents within a lead upto 500 Mtr including all | Cooling Tower 1st Bill | 180 | m3 |  |  |  |  | 153.9638 | 27713.4878 | 153.9638 | 27713.4878
3 | 46 | Dressing & Levelling | Cooling Tower 1st Bill | 25 | m2 |  |  |  |  | 73.6669 | 1841.6725 | 73.6669 | 1841.6725
3 | 47 | Hard Rock Solng | Cooling Tower 1st Bill | 900 | m3 |  |  |  |  | 11.05 | 9945.0315 | 11.05 | 9945.0315
|  | Plain & reinforced Cement Concrete | [8 empty] | 0 | 0 | 0
4 | 25 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Cooling Tower 1st Bill | 2300 | m3 |  |  |  |  | 5.1463 | 11836.467 | 5.1463 | 11836.467
5 | 11-a | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | Cooling Tower 1st Bill | 2750 | m3 |  |  |  |  | 12.1527 | 33419.9938 | 12.1527 | 33419.9938
|  | Formwork (Shuttering) | [8 empty] | 0 | 0 | 0
6 | 23 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | Cooling Tower 1st Bill | 400 | m2 |  |  |  |  | 9.921 | 3968.4 | 9.921 | 3968.4
|  | REINFORCEMENT WORK | [8 empty] | 0 | 0 | 0
9 | 17-a | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Cooling Tower 1st Bill | 9000 | MT |  |  |  |  | 1.4285 | 12856.2293 | 1.4285 | 12856.2293
| * | Total | [8 empty] | 101581.2819 |  | 101581.2819

## RA 2
To
Nakoda Pipe Implex
Tilda, Chattisgarh
Work order No: SNIPIPL/WO/2022-23/010
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 0 to 3 Mtr hieghts and descents within a lead upto 500 Mtr including all | Cooling Tower (SID) | 180 | m3 |  |  | 153.9638 | 27713.4878 | -59.3019 | -10674.3338 | 94.662 | 17039.154
2 | 46 | Dressing & Levelling | Cooling Tower 2nd Bill | 25 | m2 |  |  | 73.6669 | 1841.6725 | 6.73 | 168.25 | 80.3969 | 2009.9225
3 | 47 | Hard Rock Solng | Cooling Tower 2nd Bill | 900 | m3 |  |  | 11.05 | 9945.0315 | 0 | 0 | 11.05 | 9945.0315
|  | Plain & reinforced Cement Concrete | [5 empty] | 0
4 | 25 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | Cooling Tower (SID) | 2300 | m3 |  |  | 5.1463 | 11836.467 | 0 | 0 | 5.1463 | 11836.467
5 | 11-a | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | Cooling Tower (SID) | 6500 | m3 |  |  | 12.1527 | 78992.7125 | 21.33 | 138645 | 33.4827 | 217637.7125
|  | Formwork (Shuttering) | [5 empty] | 0
6 | 23 | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | Cooling Tower 2nd Bill | 450 | m2 |  |  | 9.921 | 4464.45 | 191.14 | 86013 | 201.061 | 90477.45
|  | REINFORCEMENT WORK | [5 empty] | 0
7 | 17-a | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | Cooling Tower (SID) | 10000 | MT |  |  | 1.4285 | 14284.6993 | 1.4 | 14000 | 2.8285 | 28284.6993
| * | Total | [6 empty] | 149078.5205 |  | 228151.9162 |  | 377230.4367