## RA 1
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-10th April 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-17th April 2023
RA 1
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 0 to 3 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 1st Bill | 180 | m3 |  |  |  |  | 1550.67 | 279120.6
2 | 2 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 3 to 6 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 1st Bill | 220 | m3 |  |  |  |  | 46.0032 | 10120.7062
3 | 46 | Dressing & Levelling | DRI 1st Bill | 25 | m2 |  |  |  |  | 516.89 | 12922.25
4 | 9 | Sand Filling | DRI 1st Bill | 1180 | [5 empty] | 0 | 0
|  | Plain & reinforced Cement Concrete | [8 empty] | 0
5 | 25 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 3 To 6 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI 1st Bill | 2599 | m3 |  |  |  |  | 26.8945 | 69898.7145
6 | 11-a | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | DRI 1st Bill | 2750 | m3 |  |  |  |  | 162.6115 | 447181.6213
|  | Formwork (Shuttering) | [8 empty] | 0
7 | 23 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | DRI 1st Bill | 400 | m2 |  |  |  |  | 427.1941 | 170877.6533
|  | REINFORCEMENT WORK | [8 empty] | 0
9 | 17-a | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | DRI 1st Bill | 9000 | MT |  |  |  |  | 17.9211 | 161289.873
| * | Total | [6 empty] | 0 |  | 1151411.4183 |  | 0

## RA 2
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-9th May 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-19th May 2023
RA 2
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 0 to 3 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 3rd Bill | 180 | m3 |  |  | 1550.67 | 279120.6 |  | 0 | 1550.67 | 279120.6
2 | 2 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 3 to 6 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 3rd Bill | 220 | m3 |  |  | 46.0032 | 10120.7062 |  | 0 | 46.0032 | 10120.7062
3 | 46 | Dressing & Levelling | DRI 3rd Bill | 25 | m2 |  |  | 516.89 | 12922.25 | 57.1 | 1427.5 | 573.99 | 14349.75
4 | 9 | Sand Filling | DRI 3rd Bill | 1180 | m3 |  |  | 4.348 | 5130.699 | 5.71 | 6737.8 | 10.058 | 11868.499
|  | Hard Rock Excavation 0-3 | DRI 3rd Bill | 1050 | m3 |  |  | 0 | 0 |  | 0 | 0 | 0
Plain & reinforced Cement Concrete
5 | 25 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 3 To 6 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI 3rd Bill | 2599 | m3 |  |  | 30.2185 | 78537.8815 | -3.324 | -8639.167 | 26.8945 | 69898.7145
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI 3rd Bill | 2300 | m3 |  |  |  |  | 3.324 | 7645.2805 | 3.324 | 7645.2805
6 | 11-a | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | DRI 3rd Bill | 2750 | m3 |  |  | 185.9955 | 511487.5938 | 3.7543 | 10324.3525 | 189.7498 | 521811.9463
Formwork (Shuttering)
7 | 23 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | DRI 3rd Bill | 400 | m2 |  |  | 552.5898 | 221035.92 | 128.6998 | 51479.9053 | 681.2896 | 272515.8253
|  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3 to 6 | DRI 3rd Bill | 452 | m2 | [6 empty] | 2.8732 | 1298.6864
REINFORCEMENT WORK
9 | 17-a | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete. | DRI 3rd Bill | 9000 | MT |  |  | 21.3988 | 192589.506 | 5.25 | 47250 | 26.6488 | 239839.506
| * | Total | [6 empty] | 1310945.1565 |  | 116225.6714 |  | 1428469.5142

## RA 3
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-28th June 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-26th July 2023
RA 3
Sl No | Item no | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 | 1 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 0 to 3 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 3rd Bill | 180 | m3 |  |  | 1550.67 | 279120.6 |  |  | 1550.67 | 279120.6
2 | 2 | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at all 3 to 6 Mtr hieghts and descents within a lead upto 500 Mtr including all | DRI 3rd Bill | 220 | m3 |  |  | 46.0032 | 10120.7062 |  |  | 46.0032 | 10120.7062
3 | 46 | Dressing & Levelling | DRI 3rd Bill | 25 | m2 |  |  | 573.99 | 14349.75 |  |  | 573.99 | 14349.75
|  | Backfillng | DRI 3rd Bill | 80 | [5 empty] | 556.421 | 44513.68 | 556.421 | 44513.68
4 | 9 | Sand Filling | DRI 3rd Bill | 1180 | m3 |  |  | 10.058 | 11868.499 |  |  | 10.058 | 11868.499
|  | Hard Rock Excavation 0-3 | DRI 3rd Bill | 1050 | m3 |  |  | 0 | 0 | 51.0674 | 53620.77 | 51.0674 | 53620.77
Plain & reinforced Cement Concrete
5 | 25 | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 3 To 6 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI 3rd Bill | 2599 | m3 |  |  | 26.8945 | 69898.7145 |  |  | 26.8945 | 69898.7145
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI 3rd Bill | 2300 | m3 |  |  | 3.324 | 7645.2805 |  |  | 3.324 | 7645.2805
6 | 11-a | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | DRI 3rd Bill | 2750 | m3 |  |  | 189.7498 | 521811.9463 | 18.27 | 50242.5 | 208.0198 | 572054.4463
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 to 6 M heights/depth with proper compaction and curing | DRI 3rd Bill | 3107.5 | m3 |  |  |  |  | 2.071 | 6435.6325 | 2.071 | 6435.6325
Formwork (Shuttering)
7 | 23 | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | DRI 3rd Bill | 400 | m2 |  |  | 681.2896 | 272515.8253 | 127.8 | 51120 | 809.0896 | 323635.8253
|  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3 to 6 | DRI 3rd Bill | 452 | m2 |  |  | 2.8732 | 1298.6864 | 14.484 | 6546.768 | 17.3572 | 7845.4544
REINFORCEMENT WORK
9 | 17-a | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (0-3Mtr) | DRI 3rd Bill | 9000 | MT |  |  | 26.6488 | 239839.506 | 4.18 | 37620 | 30.8288 | 277459.506
|  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (3-6Mtr) | DRI 3rd Bill | 10170 | [5 empty] | 1.955 | 19882.35 | 1.955 | 19882.35
| * | Total | [6 empty] | 1428469.5142 |  | 269981.7005 |  | 1698451.2147

## RA 4
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-16th August 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-9th September 2023
RA 4
Sl No | Item No | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 |  | Excavaton 0--3 Mtr | DRI | 180 | m3 |  |  | 1550.67 | 279120.6 |  |  | 1550.67 | 279120.6
2 |  | Excavaton 3--6 Mtr | DRI | 220 | m3 |  |  | 46.0032 | 10120.7062 |  |  | 46.0032 | 10120.7062
3 |  | Dressing & Levelling | DRI | 25 | m2 |  |  | 573.99 | 14349.75 |  |  | 573.99 | 14349.75
4 |  | Backfillng | DRI | 80 | m3 |  |  | 556.421 | 44513.68 |  |  | 556.421 | 44513.68
5 |  | Sand Filling | DRI | 1180 | m3 |  |  | 10.058 | 11868.499 |  |  | 10.058 | 11868.499
6 |  | Hard Rock Excavation 0-3 | DRI | 1050 | m3 |  |  | 51.0674 | 53620.77 |  |  | 51.0674 | 53620.77
Plain & reinforced Cement Concrete
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 3 To 6 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI | 2599 | m3 |  |  | 26.8945 | 69898.7145 |  |  | 26.8945 | 69898.7145
8 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI | 2300 | m3 |  |  | 3.324 | 7645.2805 |  |  | 3.324 | 7645.2805
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | DRI | 2750 | m3 |  |  | 208.0198 | 572054.4463 | 3.7236 | 10239.7762 | 211.7434 | 582294.2225
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 to 6 M heights/depth with proper compaction and curing | DRI | 3107.5 | m3 |  |  | 2.071 | 6435.6325 | 71.1695 | 221159.3378 | 73.2405 | 227594.9703
Formwork (Shuttering)
11 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | DRI | 400 | m2 |  |  | 809.0896 | 323635.8253 | 31.5552 | 12622.08 | 840.6448 | 336257.9053
12 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3 to 6 | DRI | 452 | m2 |  |  | 17.3572 | 7845.4544 | 602.0182 | 272112.2038 | 619.3754 | 279957.6582
REINFORCEMENT WORK
13 |  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (0-3Mtr) | DRI | 9000 | MT |  |  | 30.8288 | 277459.506 | 0.54 | 4860 | 31.3688 | 282319.506
14 |  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (3-6Mtr) | DRI | 10170 |  |  |  | 1.955 | 19882.35 | 15.12 | 153770.4 | 17.075 | 173652.75
Fixing of Inserts
15 |  | Fixing of MS inserts and ISA | DRI | 25000 | MT |  |  | 0 | 0 | 0.85 | 21250 | 0.85 | 21250
|  | Total | [6 empty] | 1698451.2147 |  | 696013.7978 |  | 2373215.0126
191707
[11 empty] | 754951 |  | 2564922.0126
[11 empty] | 58937.2022 |  | 790746
3355668.0126

## RA 4 Measurement
To Nakoda Pipe Impex Pvt Ltd | [12 empty] | Division:- S.I.D
Bill Name: DRI | [12 empty] | Billing Month:- August 2023
Bill No:- RA 4 | [12 empty] | Vendor: Aquaplast Infracon Pvt Ltd
Sl No | Description | Block | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed IN
[5 empty] | From | To
RCC {0--3} Mtr
1 | 0--3 Mtr | DRI | Staircase | Waist Slab | NA | NA | 4.2 | 1.2 | 0.15 | 2 | 1.512 | Cum | RA 4
2 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 | 0.9 | 0.15 | 1 | 0.35775 | Cum | RA 4
3 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 | 2.17 | 0.15 | 1 | 0.86257 | Cum | RA 4
4 | 0--3 Mtr | DRI | Staircase | Stair Steps | NA | NA | 0.0875 | 0.3 | 1.2 | 14 | 0.441 | Cum | RA 4
5 | 0--3 Mtr | DRI | Staircase | Stair Steps | NA | NA | 0.0785 | 0.3 | 1.2 | 13 | 0.36738 | Cum | RA 4
6 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 | 0.23 | 0.3 | 1 | 0.18285 | Cum | RA 4
| RCC {Total 0--3 Mtr} | [9 empty] | 3.7236 | Cum | RA 4
7 | 3--6 Mtr | DRI | Roof slab |  | 102.35 | 102.225 | 37.73 | 10.23 | 0.125 | 1 | 48.2472 | Cum | RA 4
8 | 3--6 Mtr | DRI |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 | 0.125 | 10 | 5.875 | Cum | RA 4
9 | 3--6 Mtr | DRI |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 | 0.125 | 2 | 0.675 | Cum | RA 4
10 | 3--6 Mtr | DRI |  | (-) Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 | 0.125 | 1 | 2.5448 | Cum | RA 4
39.1525
11 | 3--6 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 | 0.575 | 9 | 13.6568 | Cum | RA 4
12 | 3--6 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 | 0.325 | 18 | 1.3689 | Cum | RA 4
13 | 3--6 Mtr | DRI | B2 | B1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 | 0.325 | 8 | 0.8502 | Cum | RA 4
14 | 3--6 Mtr | DRI | B2 | 7'A-8'A (Stair Beam) | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
15 | 3--6 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 | 0.325 | 18 | 8.1608 | Cum | RA 4
16 | 3--6 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
17 | 3--6 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 | 0.325 | 2 | 0.7215 | Cum | RA 4
18 | 3--6 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 | 0.325 | 2 | 6.2059 | Cum | RA 4
| RCC {Total 3--6 Mtr} | [9 empty] | 71.1695 | m³ | RA 4
Shuttering {0--3} Mtr
27 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA | 4.2 | 1.2 |  | 2 | 10.08 | Sqm | RA 4
28 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 | 0.9 |  | 1 | 2.385 | Sqm | RA 4
29 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 | 2.17 |  | 1 | 5.7505 | Sqm | RA 4
30 | 0--3 Mtr | DRI | Staircase | Stair Steps {Riser} | NA | NA | 0.175 |  | 1.2 | 14 | 2.94 | Sqm | RA 4
31 | 0--3 Mtr | DRI | Staircase | Stair Steps {Riser} | NA | NA | 0.157 |  | 1.2 | 13 | 2.4492 | Sqm | RA 4
32 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 |  | 0.3 | 2 | 1.59 | Sqm | RA 4
47 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA | 4.2 |  | 0.15 | 4 | 2.52 | Sqm | RA 4
48 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA |  | 1.2 | 0.15 | 4 | 0.72 | Sqm | RA 4
49 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Sqm | RA 4
50 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA |  | 0.9 | 0.15 | 2 | 0.27 | Sqm | RA 4
51 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Sqm | RA 4
52 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA |  | 2.17 | 0.15 | 2 | 0.651 | Sqm | RA 4
53 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 | 0.23 |  | 1 | 0.6095 | Sqm | RA 4
| Shuttering {Total 0--3 Mtr} | [9 empty] | 31.5552 | Sqm | RA 4
25 | 3--6 Mtr | DRI | Roof slab (1st Level) |  | 102.35 | 102.5 | 37.73 | 10.23 |  | 1 | 385.9779 | Sqm | RA 4
| 3--6 Mtr | DRI |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 |  | 10 | 47 | Sqm | RA 4
| 3--6 Mtr | DRI |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 |  | 2 | 5.4 | Sqm | RA 4
| 3--6 Mtr | DRI
| 3--6 Mtr | DRI |  | (-) Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 |  | 1 | 20.358 | Sqm | RA 4
26 | 3--6 Mtr | DRI | Area Remaining of roof slab | [7 empty] | 313.2199 | Sqm | RA 4
| 3--6 Mtr | DRI
41 | 3--6 Mtr | DRI | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 | 37.73 |  | 0.125 | 2 | 9.4325 | Sqm | RA 4
42 | 3--6 Mtr | DRI | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 |  | 10.23 | 0.125 | 2 | 2.5575 | Sqm | RA 4
43 | 3--6 Mtr | DRI | Cutouts | Side Shuttering | 102.35 | 102.5 | 4.7 |  | 0.125 | 20 | 11.75 | Sqm | RA 4
44 | 3--6 Mtr | DRI | Cutouts | Side Shuttering | 102.35 | 102.5 |  | 1 | 0.125 | 20 | 2.5 | Sqm | RA 4
45 | 3--6 Mtr | DRI | Cutouts | Side Shuttering | 102.35 | 102.5 | 2.7 |  | 0.125 | 4 | 1.35 | Sqm | RA 4
46 | 3--6 Mtr | DRI | Cutouts | Side Shuttering | 102.35 | 102.5 |  | 1 | 0.125 | 4 | 0.5 | Sqm | RA 4
17 | 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 |  | 0.575 | 9 | 39.0195 | Sqm | RA 4
18 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 |  | 0.325 | 18 | 4.563 | Sqm | RA 4
19 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 |  | 0.325 | 8 | 2.834 | Sqm | RA 4
20 | 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
21 | 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 |  | 0.325 | 18 | 27.2025 | Sqm | RA 4
22 | 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
23 | 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 |  | 0.325 | 2 | 2.405 | Sqm | RA 4
24 | 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 |  | 0.325 | 2 | 20.6863 | Sqm | RA 4
33 | 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 |  | 18 | 47.502 | Sqm | RA 4
34 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 |  | 36 | 8.424 | Sqm | RA 4
35 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 |  | 16 | 5.232 | Sqm | RA 4
36 | 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
37 | 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 |  | 36 | 50.22 | Sqm | RA 4
38 | 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
39 | 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 |  | 4 | 4.44 | Sqm | RA 4
40 | 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 |  | 4 | 38.19 | Sqm | RA 4
| Shuttering {Total 3--6 Mtr} | [9 empty] | 602.0182 | Sqm | RA 4
Fixing of Insert & Jigs
| Insert Plate | DRI |  |  |  |  | 0.15 | 0.15 | 0.012 | 80 | 0.16956 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  |  | 7.4 |  | 8.9 | 2 | 0.13172 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  |  | 11.4 |  | 8.9 | 10 | 1.0146 | MT | RA 4
| Fixing of Insert & Jigs | [9 empty] | 1.3159 | MT | RA 4

## RA 5
To
Nakoda Pipe Implex
Tilda, Chattisgarh | [9 empty] | Date of Submission-16th August 2023
Work order No: SNIPIPL/WO/2022-23/010 | [9 empty] | Date of Finalizing-9th September 2023
RA 4
Sl No | Item No | Description | Block | Rate | Unit | As per Work order |  | Upto last bill |  | This Bill |  | Total
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount
Earthwork & Filling
1 |  | Excavaton 0--3 Mtr | DRI | 180 | m3 |  |  | 1550.67 | 279120.6 |  |  | 1550.67 | 279120.6
2 |  | Excavaton 3--6 Mtr | DRI | 220 | m3 |  |  | 46.0032 | 10120.7062 |  |  | 46.0032 | 10120.7062
3 |  | Dressing & Levelling | DRI | 25 | m2 |  |  | 573.99 | 14349.75 |  |  | 573.99 | 14349.75
4 |  | Backfillng | DRI | 80 | m3 |  |  | 556.421 | 44513.68 |  |  | 556.421 | 44513.68
5 |  | Sand Filling | DRI | 1180 | m3 |  |  | 10.058 | 11868.499 |  |  | 10.058 | 11868.499
6 |  | Hard Rock Excavation 0-3 | DRI | 1050 | m3 |  |  | 51.0674 | 53620.77 |  |  | 51.0674 | 53620.77
Plain & reinforced Cement Concrete
7 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 3 To 6 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI | 2599 | m3 |  |  | 26.8945 | 69898.7145 |  |  | 26.8945 | 69898.7145
8 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at 0 To 3 Mtr heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) | DRI | 2300 | m3 |  |  | 3.324 | 7645.2805 |  |  | 3.324 | 7645.2805
9 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M heights/depth with proper compaction and curing | DRI | 2750 | m3 |  |  | 211.7434 | 582294.2225 |  | 0 | 211.7434 | 582294.2225
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 to 6 M heights/depth with proper compaction and curing | DRI | 3107.5 | m3 |  |  | 73.2405 | 227594.9703 | 11.994 | 37271.355 | 85.2345 | 264866.3253
10 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 to 6 M heights/depth with proper compaction and curing | DRI | 3465 | m3 |  |  | 73.2405 | 253778.4624 | 12.1 | 41926.5 | 85.3405 | 295704.9624
Formwork (Shuttering)
11 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | DRI | 400 | m2 |  |  | 840.6448 | 336257.9053 |  | 0 | 840.6448 | 336257.9053
12 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3 to 6 | DRI | 452 | m2 |  |  | 619.3754 | 279957.6582 | 85.62 | 38700.24 | 704.9954 | 318657.8982
12 |  | Provinding and fixing qhuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3 to 6 | DRI | 504 | m2 |  |  | 619.3754 | 312165.1764 | 86.505 | 43598.52 | 705.8804 | 355763.6964
REINFORCEMENT WORK
13 |  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (0-3Mtr) | DRI | 9000 | MT |  |  | 31.3688 | 282319.506 |  | 0 | 31.3688 | 282319.506
14 |  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (3-6Mtr) | DRI | 10170 | MT |  |  | 17.075 | 173652.75 | 2.2833 | 23221.161 | 19.3583 | 196873.911
15 |  | Taking delivery transporting within site area placing and fixing in postion steel Reinforcement iat all levels above and below plinth level for RCC including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. (3-6Mtr) | DRI | 11340 | MT |  |  | 18.075 | 204970.5 | 2.31 | 26195.4 | 20.385 | 231165.9
Fixing of Inserts
15 |  | Fixing of MS inserts and ISA | DRI | 25000 | MT |  |  | 0.85 | 0 |  | 0 | 0.85 | 21250
|  | Total | [6 empty] | 2939158.6514 |  | 210913.176 |  | 3123876.4274

## RA 5 Measurement
Sl No | Description | Block | Structure | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed IN
|  |  |  | From | To
1 | 3--6 Mtr | DRI | C1 | 99.5 | 101.54 | 0.55 | 0.7 | 2.04 | 8 | 6.2832 | Cum | RA 5
2 | 3--6 Mtr | DRI | C2 | 99.5 | 101.54 | 0.4 | 0.7 | 2.04 | 10 | 5.712 | Cum | RA 5
| RCC {Total 3--6 Mtr} | [8 empty] | 11.9952 | Cum | RA 5
1 | 6--9 Mtr | DRI | C1 | 101.54 | 103.6 | 0.55 | 0.7 | 2.06 | 8 | 6.3448 | Cum | RA 5
2 | 6--9 Mtr | DRI | C2 | 101.54 | 103.6 | 0.4 | 0.7 | 2.06 | 10 | 5.768 | Cum | RA 5
| RCC {Total 6--9 Mtr} | [8 empty] | 12.1128 | Cum | RA 5
1 | 3--6 Mtr | DRI | C1 | 99.5 | 101.54 | 0.55 |  | 2.04 | 16 | 17.952 | Sqm | RA 5
2 | 3--6 Mtr | DRI | C2 | 99.5 | 101.54 | 0.4 |  | 2.04 | 20 | 16.32 | Sqm | RA 5
3 | 3--6 Mtr | DRI | C1 | 99.5 | 101.54 |  | 0.7 | 2.04 | 16 | 22.848 | Sqm | RA 5
4 | 3--6 Mtr | DRI | C2 | 99.5 | 101.54 |  | 0.7 | 2.04 | 20 | 28.56 | Sqm | RA 5
| Shuttering {Total 3--6 Mtr} | [8 empty] | 85.68 | Sqm | RA 5
1 | 6--9 Mtr | DRI | C1 | 101.54 | 103.6 | 0.55 |  | 2.06 | 16 | 18.128 | Sqm | RA 5
2 | 6--9 Mtr | DRI | C2 | 101.54 | 103.6 | 0.4 |  | 2.06 | 20 | 16.48 | Sqm | RA 5
1 | 6--9 Mtr | DRI | C1 | 101.54 | 103.6 |  | 0.7 | 2.06 | 16 | 23.072 | Sqm | RA 5
2 | 6--9 Mtr | DRI | C2 | 101.54 | 103.6 |  | 0.7 | 2.06 | 20 | 28.84 | Sqm | RA 5
| Shuttering {Total 6--9 Mtr} | [8 empty] | 86.52 | Sqm | RA 5
| Shuttering {Total 3--6 Mtr} | [8 empty] | 310.128 | Sqm | RA 5
Fixing of Insert & Jigs
| Insert Plate | DRI |  |  |  | 0.15 | 0.15 | 0.012 | 80 | 0.16956 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  | 7.4 |  | 8.9 | 2 | 0.13172 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  | 11.4 |  | 8.9 | 10 | 1.0146 | MT | RA 4
| Fixing of Insert & Jigs | [8 empty] | 1.3159 | MT | RA 4