## Abstract + 10%
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Division: -S.I.D
Sl No | Item No | Description | Block | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Estimated Value
[7 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
Excavation & Backfilling
1 |  | Excavation 0-3 Mtr | DRI | m3 | 180 | SID |  |  |  |  | 1872.8531 | 337113.5625
2 |  | Excavation 3-6 Mtr | DRI | m3 | 220 | SID |  |  |  |  | 55.5613 | 12223.4881
3 |  | Excavation 6-9 Mtr | DRI | m3 | 203.4 | SID
4 |  | Soil Dressing | DRI | m2 | 25 | SID |  |  |  |  | 709.1235 | 17728.0881
5 |  | Hard Rock breaking 0-3 | DRI | m3 | 1050 | SID |  |  |  |  | 56.1741 | 58982.847
6 |  | Hard Rock breaking 3-6 | DRI | m3 | 1150 | SID
7 |  | Hard Rock breaking 6-9 | DRI | m3 | 1186.5 | SID
8 |  | Sand Filling | DRI | m3 | 1180 | SID |  |  |  |  | 12.1404 | 14325.6171
9 |  | Aggregate Filling | DRI | m3 | 1700 | SID
10 |  | Rock Soling | DRI | m3 | 900 | SID |  |  |  |  | 73.5899 | 66230.8763
11 |  | Backfilling | DRI | m3 | 80 | SID |  |  |  |  | 1647.3409 | 131787.274
Plain cement concrete
12 |  | PCC 0-3 Mtr | DRI | m3 | 2300 | SID
13 |  | PCC 3-6 Mtr | DRI | m3 | 2599 | SID |  |  |  |  | 8.2583 | 21463.1918
14 |  | PCC 3-9 Mtr | DRI | m3 | 2898 | SID |  |  |  |  | 33.2404 | 96330.5343
|  | Reinforced cement concrete | [10 empty] | 41.4986
15 |  | RCC 0-3 Mtr | DRI | m3 | 2750 | SID |  |  |  |  | 143.9518 | 395867.5627
16 |  | RCC 3-6 Mtr | DRI | m3 | 3107.5 | SID |  |  |  |  | 176.4612 | 548353.05
17 |  | RCC 6-9 Mtr | DRI | m3 | 3465 | SID |  |  |  |  | 295.749 | 1024770.4554
18 |  | RCC 9-12 Mtr | DRI | m3 | 3822.5 | SID |  |  |  |  | 4.774 | 18248.615
19 |  | RCC 12-15 Mtr | DRI | m3 | 4180 | SID |  |  |  |  | 17.6195 | 73649.6145 |  | 638.5556
Formwork & Shuttering
20 |  | 0--3 Mtr | DRI | m2 | 400 | SID |  |  |  |  | 1016.7709 | 406708.346
21 |  | 3--6 Mtr | DRI | m2 | 452 | SID |  |  |  |  | 1268.439 | 573334.4461
22 |  | 6--9 Mtr | DRI | m2 | 504 | SID |  |  |  |  | 945.6105 | 476587.687
23 |  | 9--12 Mtr | DRI | MT | 556 | SID |  |  |  |  | 53.658 | 29833.848
24 |  | 12--15 Mtr | DRI | MT | 608 | SID |  |  |  |  | 130.0035 | 79042.128
Reinforcement of TMT Bars
25 |  | 0--3 Mtr | DRI | MT | 9000 | SID |  |  |  |  | 22.6004 | 203403.9513
26 |  | 3--6 Mtr | DRI | MT | 10170 | SID |  |  |  |  | 27.7044 | 281753.7672
27 |  | 6--9 Mtr | DRI | MT | 11340 | SID |  |  |  |  | 46.4326 | 526545.6922
28 |  | 9--12 Mtr | DRI | MT | 12510 | SID |  |  |  |  | 0.74952 | 9376.4702
29 |  | 12--15 Mtr | DRI | MT | 13680 | SID |  |  |  |  | 2.7663 | 37842.511
Brickwork
30 | 27 | 0--3 | DRI | Cum | 3300 | SID |  |  |  |  | 102.4636 | 338129.9625
31 | 28 | 3--6 | DRI | Cum | 3762 | SID |  |  |  |  | 108.4208 | 407879.0966
32 | 28 | 6--9 | DRI | Cum | 4224 | SID |  |  |  |  | 67.9119 | 286860.024
33 | 28 | 9--12 | DRI | Cum | 4686 | SID |  |  |  |  | 20.6456 | 96745.3987
Plaster
30 | 31 | 0--3 | DRI | Sqm | 220 | SID |  |  |  |  | 1836.4799 | 404025.5703
31 | 32 | 3--6 | DRI | Sqm | 250.8 | SID |  |  |  |  | 1376.8599 | 345316.451
32 | 32 | 6--9 | DRI | Sqm | 281.6 | SID |  |  |  |  | 1488.906 | 419275.9268
33 | 32 | 9--12 | DRI | Sqm | 312.4 | SID |  |  |  |  | 218.823 | 68360.3052
34 | 32 | 12--15 | DRI | Sqm | 343.2 | SID |  |  |  |  | 130.0035 | 44617.2012
7852713.5601

## Measurement Sheet
Estimate value sheet
DRI
Division: SID
Sl No | Description | Block | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed IN
[5 empty] | To | From
Excavation & Backfilling
1 | 0--3 | DRI | Raft |  | 92.54 | 95.54 | 40.625 | 13.97 | 3 | 1 | 1702.5938 | Cum | Cum
| Total | [9 empty] | 1702.5938 | Cum | Cum
2 | 3--6 | DRI | Raft |  | 92.451 | 92.54 | 40.625 | 13.97 | 0.089 | 1 | 50.5103 | Cum | Cum
| Total | [9 empty] | 50.5103 | Cum | Cum
2 | Soil Dressing | DRI | Raft |  | 91.5 | 91.5 | 40.625 | 13.97 |  | 1 | 567.5312 | Sqm | Sqm
|  | DRI | Beam |  | 94.75 | 94.75 | 8.27 | 0.55 |  | 9 | 40.9365
|  | DRI | Beam |  | 94.75 | 94.75 | 32.9 | 0.55 |  | 2 | 36.19
| Total | [9 empty] | 644.6578 | 0 | 0
3 | Hard Rock Excavation 0-3 Mtr | DRI | Raft |  | 92.451 | 93.191 | 6.7 | 10.3 | 0.74 | 1 | 51.0674 | Cum | Cum
| Total | [9 empty] | 51.0674 | Cum | Cum
| Sand Filling | DRI | Beam |  | 94.65 | 94.75 | 8.27 | 0.55 | 0.1 | 9 | 4.0937 | Sqm | Sqm
| Sand Filling | DRI | Beam |  | 94.65 | 94.75 | 32.9 | 0.55 | 0.1 | 2 | 3.619 | Sqm | Sqm
| Sand Filling | DRI | F1 | A-B | 92.351 | 92.451 | 4.65 | 4.65 | 0.1 | 10 | 2.1783 | Cum | Cum
| Sand Filling | DRI | F2 | B-E | 92.351 | 92.451 | 6.4 | 4.4 | 0.1 | 4 | 1.1458 | Cum | Cum
| Total | [9 empty] | 11.0367 | Cum | Cum
| Rock Soling | DRI | Floor Slab |  | 89.35 | 89.5 | 35.35 | 7.57 | 0.25 | 1 | 66.8999 | Cum | Cum
| Total | [9 empty] | 66.8999 | Cum | Cum
Backfilling
| Total Excavation | DRI | [8 empty] | 1753.104
| Total Hard Rock | DRI | [8 empty] | 51.0674
| Total PCC | DRI | [8 empty] | 37.726
| Total RCC | DRI | [8 empty] | 268.8628
| Total | [9 empty] | 1395.4479 | 0 | 0
Plain & reinforced Cement Concrete
PCC
| 3--6 Mtr | DRI | F1 | A-B | 92.551 | 92.451 | 4.45 | 4.45 | 0.1 | 10 | 19.8025 | Cum | Cum
| 3--6 Mtr | DRI | F2 | B-E | 92.551 | 92.451 | 6.2 | 4.2 | 0.1 | 4 | 10.416 | Cum | Cum
| Total 3-6 Mtr | [9 empty] | 30.2185 | Cum | Cum
| Total 0-3 Mtr | DRI | Beam |  | 91.851 | 91.751 | 7.27 | 0.55 | 0.1 | 10 | 3.9985 | Cum | Cum
| Total 0-3 Mtr | DRI | Beam |  | 91.851 | 91.751 | 31.9 | 0.55 | 0.1 | 2 | 3.509 | Cum | Cum
| Total 3-6 Mtr | [9 empty] | 7.5075 | Cum | Cum
RCC
| 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 | 0.575 | 9 | 13.6568 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 | 0.325 | 18 | 1.3689 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 | 0.325 | 4 | 0.4251 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 | 0.325 | 18 | 8.1608 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 | 0.325 | 2 | 0.7215 | Cum | RA 4
| 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 | 0.325 | 2 | 6.2059 | Cum | RA 4 |  | 0.31
| 0--3 Mtr | DRI | C1 |  | 91.5 | 93.85 | 0.5 | 0.7 | 2.35 | 10 | 8.225 | Cum | RA 4 | RA5
| 0--3 Mtr | DRI | C2 |  | 91.5 | 93.85 | 0.4 | 0.7 | 2.35 | 8 | 5.264 | Cum | RA 4 | RA5
| 0--3 Mtr | DRI | C1 |  | 94 | 97.4 | 0.5 | 0.7 | 3.4 | 10 | 11.9 | Cum | RA 4 | RA5
| 0--3 Mtr | DRI | C2 |  | 94 | 97.4 | 0.4 | 0.7 | 3.4 | 8 | 7.616 | Cum | RA 4 | RA5
| 0--3 Mtr | DRI | Roof slab (1st Level) |  | 102.35 | 102.5 | 37.73 | 10.23 | 0.125 | 1 | 48.2472 | Cum | RA 4
|  |  |  | Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 | 0.125 | 10 | 5.875 | Cum | RA 4
|  |  |  | Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 | 0.125 | 2 | 0.675 | Cum | RA 4
|  |  |  | Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 | 0.125 | 1 | 2.5448 | Cum | RA 4
RA 4
|  |  | Volume Remaining of roof slab | [7 empty] | 39.1525 | Cum | RA 4
[13 empty] | RA 4 |  | 10.3
| 0--3 Mtr | DRI |  | Wiast Slab | NA | NA | 4.2 | 1.2 | 0.15 | 2 | 1.512 | Cum | RA 4 |  | 11.3
| 0--3 Mtr | DRI |  | Landing 1 | NA | NA | 2.65 | 0.9 | 0.15 | 1 | 0.35775 | Cum | RA 4 | 0.9 Claimed By Aua
| 0--3 Mtr | DRI |  | Landing 2 | NA | NA | 2.65 | 2.17 | 0.15 | 1 | 0.86257 | Cum | RA 4
| 0--3 Mtr | DRI |  | Stair Steps | NA | NA | 0.0875 | 0.3 | 1.2 | 14 | 0.441 | Cum | RA 4
| 0--3 Mtr | DRI |  | Stair Steps | NA | NA | 0.0785 | 0.3 | 1.2 | 13 | 0.36738 | Cum | RA 4
|  |  |  | Stair Beam | NA | NA | 2.65 | 0.23 | 0.3 | 1 | 0.18285 | Cum | RA 4 |  | 0.62
| 0--3 Mtr | [9 empty] | 106.9228 | Cum |  |  | 0.94
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 7.27 | 0.35 | 0.45 | 10 | 11.4503 | Cum |  |  | 1.56
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 31.9 | 0.35 | 0.45 | 2 | 10.0485 | Cum |  |  | 1.68
| 3--6 Mtr | DRI | Floor Slab |  | 89.35 | 89.5 | 35.35 | 7.57 | 0.15 | 1 | 40.1399 | Cum |  |  | 1.8
| 3--6 Mtr | DRI | Roof slab |  | 97.95 | 98.1 | 38.08 | 10.23 | 0.15 | 1 | 58.4338 | Cum |  |  | 1.74
| 3--6 Mtr | DRI | Beam | B1 | 97.4 | 97.95 | 7.05 | 0.35 | 0.55 | 10 | 13.5713 | Cum |  |  | 153.12
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 0.98 | 0.35 | 0.55 | 20 | 3.773 | Cum
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 1.115 | 0.35 | 0.55 | 4 | 0.85855 | Cum
| 3--6 Mtr | DRI | Beam | B3 | 97.25 | 97.95 | 23.25 | 0.35 | 0.7 | 1 | 5.6962 | Cum |  |  | 162.8-
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 13.6 | 0.35 | 0.55 | 2 | 5.236 | Cum
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 10.95 | 0.35 | 0.55 | 2 | 4.2157 | Cum
| 3--6 Mtr | DRI | Stair | Wiast Slab | NA | NA | 1.25 | 2.65 | 0.15 | 2 | 0.99375 | Cum
| 3--6 Mtr | DRI | Stair | Stair Slab | NA | NA | 1.325 | 5.3 | 0.15 | 4 | 4.2135 | Cum
| 3--6 Mtr | DRI | Stair | Stair Steps | NA | NA | 1.325 | 0.075 | 0.3 | 60 | 1.7887 | Cum
|  | DRI | C1 |  | 91.5 | 93.85 | 0.5 | 0.7 | 2.35 | 10 | 8.225 | Cum | RA 5
|  | DRI | C2 |  | 91.5 | 93.85 | 0.4 | 0.7 | 2.35 | 8 | 5.264 | Cum | RA 5
|  | DRI | C1 |  | 94 | 97.4 | 0.5 | 0.7 | 3.4 | 10 | 11.9 | Cum | RA 5
|  | DRI | C2 |  | 94 | 97.4 | 0.4 | 0.7 | 3.4 | 8 | 7.616 | Cum | RA 5
| Total 3-6 Mtr | [9 empty] | 160.4192 | Cum
4 | 6--9 Mtr | DRI | F1 | Pyramydal frustrum volume | 86 | 86.4 | 1.1292 | 4.55 | 0.13333 | 10 | 7.5722 | Cum
| 6--9 Mtr | DRI | F1 |  | 85.6 | 86 | 4.25 | 4.25 | 0.4 | 10 | 72.25 | Cum
| 6--9 Mtr | DRI | F2 |  | 88.8 | 89.55 | 6 | 4 | 0.75 | 4 | 72 | Cum
| 6--9 Mtr | DRI | C1 |  | 86.4 | 88.5 | 0.5 | 0.7 | 2.1 | 10 | 7.35 | Cum
| 6--9 Mtr | DRI | C2 |  | 86.4 | 88.5 | 0.4 | 0.7 | 2.1 | 8 | 4.704 | Cum
| 6--9 Mtr | DRI | Roof slab |  | 102.35 | 102.5 | 38.08 | 10.23 | 0.15 | 1 | 58.4338 | Cum
| 6--9 Mtr | DRI |  | B1 | 101.8 | 102.35 | 7.05 | 0.35 | 0.55 | 10 | 13.5713 | Cum
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 0.98 | 0.35 | 0.55 | 20 | 3.773 | Cum
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 1.115 | 0.35 | 0.55 | 4 | 0.85855 | Cum
| 6--9 Mtr | DRI |  | B3 | 101.65 | 102.35 | 23.25 | 0.35 | 0.7 | 1 | 5.6962 | Cum
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 13.6 | 0.35 | 0.55 | 2 | 5.236 | Cum
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 10.95 | 0.35 | 0.55 | 2 | 4.2157 | Cum
| 6--9 Mtr | DRI |  | C1 | 100.5 | 101.8 | 0.5 | 0.7 | 1.3 | 10 | 4.55 | Cum | RA 5
| 6--9 Mtr | DRI |  | C2 | 100.5 | 101.8 | 0.4 | 0.7 | 1.3 | 8 | 2.912 | Cum | RA 5
| 6--9 Mtr | DRI |  | C1 | 102.5 | 103.5 | 0.5 | 0.7 | 1 | 10 | 3.5 | Cum | RA 5
| 6--9 Mtr | DRI |  | C2 | 102.5 | 103.5 | 0.4 | 0.7 | 1 | 8 | 2.24 | Cum | RA 5
| 6--9 Mtr | [9 empty] | 268.8628 | Cum
| 9--12 Mtr | DRI | C1 |  | 103.5 | 106.5 | 0.5 | 0.7 | 3 | 2 | 2.1 | Cum
| 9--12 Mtr | DRI | C2 |  | 104.5 | 106.5 | 0.4 | 0.7 | 2 | 4 | 2.24 | Cum
| 9--12 Mtr | [9 empty] | 4.34 | Cum
| 12--15 Mtr | DRI | B1 |  | 106.3 | 106.85 | 7.05 | 0.35 | 0.55 | 6 | 8.1428 | Cum
| 12--15 Mtr | DRI | Roof slab |  | 106.85 | 107 | 7 | 7.5 | 0.15 | 1 | 7.875 | Cum
| 12--15 Mtr | [9 empty] | 16.0177 | Cum
Formwork & Shuttering
| 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 |  | 0.575 | 9 | 39.0195 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 |  | 0.325 | 18 | 4.563 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 |  | 0.325 | 4 | 1.417 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 |  | 0.325 | 18 | 27.2025 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 |  | 0.325 | 2 | 2.405 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 |  | 0.325 | 2 | 20.6863 | Sqm | RA 4
| 0--3 Mtr | DRI | C1 |  | 91.5 | 93.85 | 0.5 |  | 2.35 | 20 | 23.5 | Sqm
| 0--3 Mtr | DRI | C2 |  | 91.5 | 93.85 | 0.4 |  | 2.35 | 16 | 15.04 | Sqm
| 0--3 Mtr | DRI | C1 |  | 94 | 97.4 | 0.5 |  | 3.4 | 20 | 34 | Sqm
| 0--3 Mtr | DRI | C2 |  | 94 | 97.4 | 0.4 |  | 3.4 | 16 | 21.76 | Sqm
| 0--3 Mtr | DRI | Roof slab (1st Level) |  | 102.35 | 102.5 | 37.73 | 10.23 |  | 1 | 385.9779 | Sqm | RA 4
|  |  |  | Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 |  | 10 | 47 | Sqm | RA 4
|  |  |  | Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 |  | 2 | 5.4 | Sqm | RA 4
|  |  |  | Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 |  | 1 | 20.358 | Sqm | RA 4
RA 4
|  |  | Area Remaining of roof slab | [7 empty] | 313.2199 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Wiast Slab | NA | NA | 4.2 | 1.2 |  | 2 | 10.08 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Landing 1 | NA | NA | 2.65 | 0.9 |  | 1 | 2.385 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Landing 2 | NA | NA | 2.65 | 2.17 |  | 1 | 5.7505 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Stair Steps {Riser} | NA | NA | 0.175 |  | 1.2 | 14 | 2.94 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Stair Steps {Riser} | NA | NA | 0.157 |  | 1.2 | 13 | 2.4492 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Stair Beam | NA | NA | 2.65 |  | 0.3 | 2 | 1.59 | Sqm | RA 4
| 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 |  | 18 | 47.502 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 |  | 36 | 8.424 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 |  | 8 | 2.616 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 |  | 36 | 50.22 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 |  | 4 | 4.44 | Sqm | RA 4
| 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 |  | 4 | 38.19 | Sqm | RA 4
| 0--3 Mtr | DRI | C1 |  | 91.5 | 93.85 |  | 0.7 | 2.35 | 20 | 32.9 | Sqm
| 0--3 Mtr | DRI | C2 |  | 91.5 | 93.85 |  | 0.7 | 2.35 | 16 | 26.32 | Sqm
| 0--3 Mtr | DRI | C1 |  | 94 | 97.4 |  | 0.7 | 3.4 | 20 | 47.6 | Sqm
| 0--3 Mtr | DRI | C2 |  | 94 | 97.4 |  | 0.7 | 3.4 | 16 | 38.08 | Sqm
| 0--3 Mtr | DRI | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 | 37.73 |  | 0.125 | 2 | 9.4325 | Sqm | RA 4
|  |  | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 |  | 10.23 | 0.125 | 2 | 2.5575 | Sqm | RA 4
|  |  | Cutouts | Side Shuttering | 102.35 | 102.5 | 4.7 |  | 0.125 | 20 | 11.75 | Sqm | RA 4
[5 empty] | 102.35 | 102.5 |  | 1 | 0.125 | 20 | 2.5 | Sqm | RA 4
|  |  | Cutouts | Side Shuttering | 102.35 | 102.5 | 2.7 |  | 0.125 | 4 | 1.35 | Sqm | RA 4
|  |  | Cutouts | Side Shuttering | 102.35 | 102.5 |  | 1 | 0.125 | 4 | 0.5 | Sqm | RA 4
| 0--3 Mtr | DRI |  | Wiast Slab | NA | NA | 4.2 |  | 0.15 | 4 | 2.52 | Cum | RA 4
| 0--3 Mtr | DRI |  | Wiast Slab | NA | NA |  | 1.2 | 0.15 | 4 | 0.72 | Cum | RA 4
| 0--3 Mtr | DRI |  | Landing 1 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Cum | RA 4
| 0--3 Mtr | DRI |  | Landing 1 | NA | NA |  | 0.9 | 0.15 | 2 | 0.27 | Cum | RA 4
| 0--3 Mtr | DRI |  | Landing 2 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Cum | RA 4
| 0--3 Mtr | DRI |  | Landing 2 | NA | NA |  | 2.17 | 0.15 | 2 | 0.651 | Cum | RA 4
| 0--3 Mtr | DRI |  | Stair Beam | NA | NA | 2.65 | 0.23 |  | 1 | 0.6095 | Cum | RA 4
| 0--3 Mtr | [9 empty] | 868.7403 | Cum
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 7.27 | 0.35 |  | 10 | 25.445 | Sqm
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 31.9 | 0.35 |  | 2 | 22.33 | Sqm
| 3--6 Mtr | DRI | Floor Slab |  | 89.35 | 89.5 | 35.35 | 7.57 |  | 1 | 267.5995 | Sqm
| 3--6 Mtr | DRI | Roof slab |  | 97.95 | 98.1 | 38.08 | 10.23 |  | 1 | 389.5584 | Sqm
| 3--6 Mtr | DRI | Beam | B1 | 97.4 | 97.95 | 7.05 | 0.35 |  | 10 | 24.675 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 0.98 | 0.35 |  | 20 | 6.86 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 1.115 | 0.35 |  | 4 | 1.561 | Sqm
| 3--6 Mtr | DRI | Beam | B3 | 97.25 | 97.95 | 23.25 | 0.35 |  | 1 | 8.1375 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 13.6 | 0.35 |  | 2 | 9.52 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 10.95 | 0.35 |  | 2 | 7.665 | Sqm
| 3--6 Mtr | DRI | Stair | Wiast Slab | NA | NA | 1.25 | 2.65 |  | 2 | 6.625 | Sqm
| 3--6 Mtr | DRI | Stair | Stair Slab | NA | NA | 1.325 | 5.3 |  | 4 | 28.09 | Sqm
| 3--6 Mtr | DRI | Stair | Stair Steps | NA | NA | 1.325 |  | 0.15 | 60 | 11.925 | Sqm
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 7.27 |  | 0.45 | 20 | 65.43 | Sqm
| 3--6 Mtr | DRI | Beam |  | 88.9 | 89.35 | 31.9 |  | 0.45 | 4 | 57.42 | Sqm
| 3--6 Mtr | DRI | Floor Slab |  | 89.35 | 89.5 |  | 7.57 | 0.15 | 2 | 2.271 | Sqm
| 3--6 Mtr | DRI | Floor Slab |  | 89.35 | 89.5 | 35.35 |  | 0.15 | 2 | 10.605 | Sqm
| 3--6 Mtr | DRI | Roof slab |  | 97.95 | 98.1 | 38.08 |  | 0.15 | 2 | 11.424 | Sqm
| 3--6 Mtr | DRI | Roof slab |  | 97.95 | 98.1 |  | 10.23 | 0.15 | 2 | 3.069 | Sqm
| 3--6 Mtr | DRI | Beam | B1 | 97.4 | 97.95 | 7.05 |  | 0.55 | 20 | 77.55 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 0.98 |  | 0.55 | 40 | 21.56 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 1.115 |  | 0.55 | 8 | 4.906 | Sqm
| 3--6 Mtr | DRI | Beam | B3 | 97.25 | 97.95 | 23.25 |  | 0.7 | 2 | 32.55 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 13.6 |  | 0.55 | 4 | 29.92 | Sqm
| 3--6 Mtr | DRI | Beam | B2 | 97.4 | 97.95 | 10.95 |  | 0.55 | 4 | 24.09 | Sqm
| 3--6 Mtr | DRI | Stair | Wiast Slab | NA | NA | 1.25 |  | 0.15 | 4 | 0.75 | Sqm
| 3--6 Mtr | DRI | Stair | Wiast Slab | NA | NA |  | 2.65 | 0.15 | 4 | 1.59 | Sqm
| 3--6 Mtr | [9 empty] | 1153.1264 | Sqm
| 6--9 Mtr | DRI | F1 |  | 85.6 | 86 | 4.25 |  | 0.4 | 20 | 34 | Sqm
| 6--9 Mtr | DRI | F2 |  | 88.8 | 89.55 | 6 |  | 0.75 | 8 | 36 | Sqm
| 6--9 Mtr | DRI | C1 |  | 86.4 | 88.5 | 0.5 |  | 2.1 | 20 | 21 | Sqm | RA 5
| 6--9 Mtr | DRI | C2 |  | 86.4 | 88.5 | 0.4 |  | 2.1 | 16 | 13.44 | Sqm | RA 5
| 6--9 Mtr | DRI | Roof slab |  | 102.35 | 102.5 | 38.08 | 10.23 |  | 1 | 389.5584 | Sqm
| 6--9 Mtr | DRI |  | B1 | 101.8 | 102.35 | 7.05 | 0.35 |  | 10 | 24.675 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 0.98 | 0.35 |  | 20 | 6.86 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 1.115 | 0.35 |  | 4 | 1.561 | Sqm
| 6--9 Mtr | DRI |  | B3 | 101.65 | 102.35 | 23.25 | 0.35 |  | 1 | 8.1375 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 13.6 | 0.35 |  | 2 | 9.52 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 10.95 | 0.35 |  | 2 | 7.665 | Sqm
| 6--9 Mtr | DRI |  | C1 | 100.5 | 101.8 | 0.5 |  | 1.3 | 20 | 13 | Sqm
| 6--9 Mtr | DRI |  | C2 | 100.5 | 101.8 | 0.4 |  | 1.3 | 16 | 8.32 | Sqm
| 6--9 Mtr | DRI |  | C1 | 102.5 | 103.5 | 0.5 |  | 1 | 20 | 10 | Sqm
| 6--9 Mtr | DRI |  | C2 | 102.5 | 103.5 | 0.4 |  | 1 | 16 | 6.4 | Sqm
| 6--9 Mtr | DRI | F1 |  | 85.6 | 86 |  | 4.25 | 0.4 | 20 | 34 | Sqm
| 6--9 Mtr | DRI | F2 |  | 88.8 | 89.55 |  | 4 | 0.75 | 8 | 24 | Sqm | RA5
| 6--9 Mtr | DRI | C1 |  | 86.4 | 88.5 |  | 0.7 | 2.1 | 20 | 29.4 | Sqm | RA5
| 6--9 Mtr | DRI | C2 |  | 86.4 | 88.5 |  | 0.7 | 2.1 | 16 | 23.52 | Sqm
| 6--9 Mtr | DRI | Roof slab |  | 102.35 | 102.5 | 38.08 |  | 0.15 | 2 | 11.424 | Sqm
| 6--9 Mtr | DRI | Roof slab |  | 102.35 | 102.5 |  | 10.23 | 0.15 | 2 | 3.069 | Sqm
| 6--9 Mtr | DRI |  | B1 | 101.8 | 102.35 | 7.05 |  | 0.55 | 20 | 77.55 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 0.98 |  | 0.55 | 40 | 21.56 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 1.115 |  | 0.55 | 8 | 4.906 | Sqm
| 6--9 Mtr | DRI |  | B3 | 101.65 | 102.35 | 23.25 |  | 0.7 | 2 | 32.55 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 13.6 |  | 0.55 | 4 | 29.92 | Sqm
| 6--9 Mtr | DRI |  | B2 | 101.8 | 102.35 | 10.95 |  | 0.55 | 4 | 24.09 | Sqm
| 6--9 Mtr | DRI |  | C1 | 100.5 | 101.8 |  | 0.7 | 1.3 | 20 | 18.2 | Sqm | RA 5
| 6--9 Mtr | DRI |  | C2 | 100.5 | 101.8 |  | 0.7 | 1.3 | 16 | 14.56 | Sqm | RA 5
| 6--9 Mtr | DRI |  | C1 | 102.5 | 103.5 |  | 0.7 | 1 | 20 | 14 | Sqm | RA 5
| 6--9 Mtr | DRI |  | C2 | 102.5 | 103.5 |  | 0.7 | 1 | 16 | 11.2 | Sqm | RA 5
| 6--9 Mtr | [9 empty] | 859.6459 | Sqm
| 12--15 Mtr | DRI | B1 |  | 106.3 | 106.85 | 7.05 | 0.35 |  | 6 | 14.805 | Sqm
| 12--15 Mtr | DRI | Roof slab |  | 106.85 | 107 | 7 | 7.5 |  | 1 | 52.5 | Sqm
| 12--15 Mtr | DRI | B1 |  | 106.3 | 106.85 | 7.05 |  | 0.55 | 12 | 46.53 | Sqm
| 12--15 Mtr | DRI | Roof slab |  | 106.85 | 107 | 7 |  | 0.15 | 2 | 2.1 | Sqm
| 12--15 Mtr | DRI | Roof slab |  | 106.85 | 107 |  | 7.5 | 0.15 | 2 | 2.25 | Sqm
| 12--15 Mtr | [9 empty] | 118.185 | Sqm
Brick Work & Plaster
Brick Work
| 0--3 Mtr | DRI |  |  | 95 | 97.5 | 36 | 0.25 | 2.5 | 2 | 45 | Cum
| 0--3 Mtr | DRI |  |  | 95 | 97.5 | 7.325 | 0.25 | 2.5 | 2 | 9.1562 | Cum
| 0--3 Mtr | DRI |  |  | 91.5 | 93.3 | 36 | 0.25 | 1.8 | 2 | 32.4 | Cum
| 0--3 Mtr | DRI |  |  | 91.5 | 93.3 | 7.325 | 0.25 | 1.8 | 2 | 6.5925 | Cum
| 0--3 Mtr | [9 empty] | 93.1487 | Cum
| 3--6 Mtr | DRI |  |  | 98.1 | 100.5 | 36 | 0.25 | 2.4 | 2 | 43.2 | Cum
| 3--6 Mtr | DRI |  |  | 98.1 | 100.5 | 7.325 | 0.25 | 2.4 | 2 | 8.79 | Cum
| 3--6 Mtr | DRI |  |  | 89.35 | 91.5 | 36 | 0.25 | 2.15 | 2 | 38.7 | Cum
| 3--6 Mtr | DRI |  |  | 89.35 | 91.5 | 7.325 | 0.25 | 2.15 | 2 | 7.8744 | Cum
| 3--6 Mtr | [9 empty] | 98.5644 | Cum
| 6--9 Mtr | DRI |  |  | 100.5 | 102.35 | 36 | 0.25 | 1.85 | 2 | 33.3 | Cum
| 6--9 Mtr | DRI |  |  | 100.5 | 102.35 | 7.325 | 0.25 | 1.85 | 2 | 6.7756 | Cum
| 6--9 Mtr | DRI | Parapet |  | 103 | 104 | 36 | 0.25 | 1 | 2 | 18 | Cum
| 6--9 Mtr | DRI | Parapet |  | 103 | 104 | 7.325 | 0.25 | 1 | 2 | 3.6625 | Cum
| 6--9 Mtr | [9 empty] | 61.7381 | Cum
| 9--12 Mtr | DRI |  |  | 103 | 105.75 | 6.15 | 0.25 | 2.75 | 2 | 8.4562 | Cum
| 9--12 Mtr | DRI |  |  | 103 | 105.75 | 7.5 | 0.25 | 2.75 | 2 | 10.3125 | Cum
| 9--12 Mtr | [9 empty] | 18.7687 | Cum
Plaster
| 0--3 Mtr | DRI |  |  | 95 | 97.5 | 36 |  | 2.5 | 4 | 360 | Sqm
| 0--3 Mtr | DRI |  |  | 95 | 97.5 | 7.325 |  | 2.5 | 4 | 73.25 | Sqm
| 0--3 Mtr | DRI |  |  | 91.5 | 93.3 | 36 |  | 1.8 | 4 | 259.2 | Sqm
| 0--3 Mtr | DRI |  |  | 91.5 | 93.3 | 7.325 |  | 1.8 | 4 | 52.74 | Sqm
| 0--3 Mtr | [9 empty] | 745.19 | Sqm
| 3--6 Mtr | DRI |  |  | 98.1 | 100.5 | 36 |  | 2.4 | 4 | 43.2 | Sqm
| 3--6 Mtr | DRI |  |  | 98.1 | 100.5 | 7.325 |  | 2.4 | 4 | 8.79 | Sqm
| 3--6 Mtr | DRI |  |  | 89.35 | 91.5 | 36 |  | 2.15 | 4 | 38.7 | Sqm
| 3--6 Mtr | DRI |  |  | 89.35 | 91.5 | 7.325 |  | 2.15 | 4 | 7.8744 | Sqm
| 3--6 Mtr | [9 empty] | 98.5644 | Sqm
| 6--9 Mtr | DRI |  |  | 100.5 | 102.35 | 36 |  | 1.85 | 4 | 266.4 | Sqm
| 6--9 Mtr | DRI |  |  | 100.5 | 102.35 | 7.325 |  | 1.85 | 4 | 54.205 | Sqm
| 6--9 Mtr | DRI | Parapet |  | 103 | 104 | 36 |  | 1 | 4 | 144 | Sqm
| 6--9 Mtr | DRI | Parapet |  | 103 | 104 | 7.325 |  | 1 | 4 | 29.3 | Sqm
| 6--9 Mtr | [9 empty] | 493.905 | Sqm
| 9--12 Mtr | DRI |  |  | 103 | 105.75 | 6.15 |  | 2.75 | 4 | 67.65 | Sqm
| 9--12 Mtr | DRI |  |  | 103 | 105.75 | 7.5 |  | 2.75 | 4 | 82.5 | Sqm
| 9--12 Mtr | [9 empty] | 150.15 | Sqm
Fixing of Insert & Jigs
Fixing of Insert & Jigs
| Insert Plate | DRI |  |  | 95 | 97.5 | 0.15 | 0.15 | 0.012 | 80 | 0.16956 | MT | RA 4
| ISA 75*75*8 | DRI |  |  | 95 | 97.5 | 7.4 |  | 8.9 | 2 | 0.13172 | MT | RA 4
| ISA 75*75*8 | DRI |  |  | 91.5 | 93.3 | 11.4 |  | 8.9 | 10 | 1.0146 | MT | RA 4

## RA 4 Measurement
To Nakoda Pipe Impex Pvt Ltd | [12 empty] | Division:- S.I.D
Bill Name: DRI | [12 empty] | Biling Month:- August 2023
Bill No:- RA 4 | [12 empty] | Financial Year:-2023-2024
Vendor: Aquaplast Infracon Pvt Ltd | [12 empty] | Reduced level DRI:- +94.00 M= {0.00}
Sl No | Description | Block | Structure | Grid | Reduced Level |  | L | B | H | Nos | Quantity | Unit | Claimed IN
RCC {0--3} Mtr
1 | 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 | 0.575 | 9 | 13.6568 | Cum | RA 4
2 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 | 0.325 | 18 | 1.3689 | Cum | RA 4
3 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 | 0.325 | 4 | 0.4251 | Cum | RA 4
4 | 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
5 | 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 | 0.325 | 18 | 8.1608 | Cum | RA 4
6 | 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 | 0.325 | 2 | 0.5265 | Cum | RA 4
7 | 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 | 0.325 | 2 | 0.7215 | Cum | RA 4
8 | 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 | 0.325 | 2 | 6.2059 | Cum | RA 4
9 | 0--3 Mtr | DRI | Roof slab |  | 102.35 | 102.5 | 37.73 | 10.23 | 0.125 | 1 | 48.2472 | Cum | RA 4
| 0--3 Mtr |  |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 | 0.125 | 10 | 5.875 | Cum | RA 4
| 0--3 Mtr |  |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 | 0.125 | 2 | 0.675 | Cum | RA 4
| 0--3 Mtr |  |  | (-) Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 | 0.125 | 1 | 2.5448 | Cum | RA 4
10 | 0--3 Mtr |  | Volume Remaining of roof slab | [7 empty] | 39.1525 | Cum | RA 4
11 | 0--3 Mtr | DRI | Staircase | Waist Slab | NA | NA | 4.2 | 1.2 | 0.15 | 2 | 1.512 | Cum | RA 4
12 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 | 0.9 | 0.15 | 1 | 0.35775 | Cum | RA 4
13 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 | 2.17 | 0.15 | 1 | 0.86257 | Cum | RA 4
14 | 0--3 Mtr | DRI | Staircase | Stair Steps | NA | NA | 0.0875 | 0.3 | 1.2 | 14 | 0.441 | Cum | RA 4
15 | 0--3 Mtr | DRI | Staircase | Stair Steps | NA | NA | 0.0785 | 0.3 | 1.2 | 13 | 0.36738 | Cum | RA 4
16 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 | 0.23 | 0.3 | 1 | 0.18285 | Cum | RA 4
| RCC {Total 0--3 Mtr} | [9 empty] | 74.468 | Cum | RA 4
Shuttering {0--3} Mtr
17 | 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 |  | 0.575 | 9 | 39.0195 | Sqm | RA 4
18 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 |  | 0.325 | 18 | 4.563 | Sqm | RA 4
19 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 |  | 0.325 | 4 | 1.417 | Sqm | RA 4
20 | 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
21 | 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 |  | 0.325 | 18 | 27.2025 | Sqm | RA 4
22 | 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 |  | 0.325 | 2 | 1.755 | Sqm | RA 4
23 | 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 |  | 0.325 | 2 | 2.405 | Sqm | RA 4
24 | 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 |  | 0.325 | 2 | 20.6863 | Sqm | RA 4
25 | 0--3 Mtr | DRI | Roof slab (1st Level) |  | 102.35 | 102.5 | 37.73 | 10.23 |  | 1 | 385.9779 | Sqm | RA 4
|  |  |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 4.7 | 1 |  | 10 | 47 | Sqm | RA 4
|  |  |  | (-) Deduction of Cutouts | 102.35 | 102.5 | 2.7 | 1 |  | 2 | 5.4 | Sqm | RA 4
Shuttering {0--3} Mtr
|  |  |  | (-) Deduction of Staricase | 102.35 | 102.5 | 7.54 | 2.7 |  | 1 | 20.358 | Sqm | RA 4
26 |  |  | Area Remaining of roof slab | [7 empty] | 313.2199 | Sqm | RA 4
27 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA | 4.2 | 1.2 |  | 2 | 10.08 | Sqm | RA 4
28 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 | 0.9 |  | 1 | 2.385 | Sqm | RA 4
29 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 | 2.17 |  | 1 | 5.7505 | Sqm | RA 4
30 | 0--3 Mtr | DRI | Staircase | Stair Steps {Riser} | NA | NA | 0.175 |  | 1.2 | 14 | 2.94 | Sqm | RA 4
31 | 0--3 Mtr | DRI | Staircase | Stair Steps {Riser} | NA | NA | 0.157 |  | 1.2 | 13 | 2.4492 | Sqm | RA 4
32 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 |  | 0.3 | 2 | 1.59 | Sqm | RA 4
33 | 0--3 Mtr | DRI | B1 |  | 93.275 | 93.85 | 7.54 | 0.35 |  | 18 | 47.502 | Sqm | RA 4
34 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 93.525 | 93.85 | 0.78 | 0.3 |  | 36 | 8.424 | Sqm | RA 4
35 | 0--3 Mtr | DRI | B2 | A1 (Cantilever) | 94.525 | 94.85 | 1.09 | 0.3 |  | 8 | 2.616 | Sqm | RA 4
36 | 0--3 Mtr | DRI | B2 | 7'A-8'A | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
37 | 0--3 Mtr | DRI | B2 | 2'A' | 93.3 | 93.85 | 4.65 | 0.3 |  | 36 | 50.22 | Sqm | RA 4
38 | 0--3 Mtr | DRI | B2 | 8'A' | 93.3 | 93.85 | 2.7 | 0.3 |  | 4 | 3.24 | Sqm | RA 4
39 | 0--3 Mtr | DRI | B2 | 9'A' | 93.3 | 93.85 | 3.7 | 0.3 |  | 4 | 4.44 | Sqm | RA 4
40 | 0--3 Mtr | DRI | B2 | Allthrough (Longer Span) | 93.3 | 93.85 | 31.825 | 0.3 |  | 4 | 38.19 | Sqm | RA 4
41 | 0--3 Mtr | DRI | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 | 37.73 |  | 0.125 | 2 | 9.4325 | Sqm | RA 4
42 | 0--3 Mtr |  | Roof slab (1st Level) | Side Shuttering | 102.35 | 102.5 |  | 10.23 | 0.125 | 2 | 2.5575 | Sqm | RA 4
43 | 0--3 Mtr |  | Cutouts | Side Shuttering | 102.35 | 102.5 | 4.7 |  | 0.125 | 20 | 11.75 | Sqm | RA 4
44 | 0--3 Mtr |  | Cutouts | Side Shuttering | 102.35 | 102.5 |  | 1 | 0.125 | 20 | 2.5 | Sqm | RA 4
45 | 0--3 Mtr |  | Cutouts | Side Shuttering | 102.35 | 102.5 | 2.7 |  | 0.125 | 4 | 1.35 | Sqm | RA 4
46 | 0--3 Mtr |  | Cutouts | Side Shuttering | 102.35 | 102.5 |  | 1 | 0.125 | 4 | 0.5 | Sqm | RA 4
47 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA | 4.2 |  | 0.15 | 4 | 2.52 | Sqm | RA 4
48 | 0--3 Mtr | DRI | Staircase | Wiast Slab | NA | NA |  | 1.2 | 0.15 | 4 | 0.72 | Sqm | RA 4
49 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Sqm | RA 4
50 | 0--3 Mtr | DRI | Staircase | Landing 1 | NA | NA |  | 0.9 | 0.15 | 2 | 0.27 | Sqm | RA 4
51 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA | 2.65 |  | 0.15 | 2 | 0.795 | Sqm | RA 4
52 | 0--3 Mtr | DRI | Staircase | Landing 2 | NA | NA |  | 2.17 | 0.15 | 2 | 0.651 | Sqm | RA 4
53 | 0--3 Mtr | DRI | Staircase | Stair Beam | NA | NA | 2.65 | 0.23 |  | 1 | 0.6095 | Sqm | RA 4
| Shuttering {Total 0--3 Mtr} | [9 empty] | 629.5403 | Sqm | RA 4
Fixing of Insert & Jigs
| Insert Plate | DRI |  |  |  |  | 0.15 | 0.15 | 0.012 | 80 | 0.16956 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  |  | 7.4 |  | 8.9 | 2 | 0.13172 | MT | RA 4
| ISA 75*75*8 | DRI |  |  |  |  | 11.4 |  | 8.9 | 10 | 1.0146 | MT | RA 4
| Fixing of Insert & Jigs | [9 empty] | 1.3159 | MT | RA 4