## RA 1
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA1
Bill Month Jan2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin |  |  | 2225.55 | 400599 | 2225.55 | 400599
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin |  |  | 1530.181 | 336639.82 | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin |  |  | 621.625 | 15540.625 | 621.625 | 15540.625
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin |  |  |  | 0 | 0 | 0
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin |  |  | 510.221 | 586754.15 | 510.221 | 586754.15
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin |  |  | 500.988 | 651033.87 | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin |  |  |  | 0 | 0 | 0
8 |  | Sand Filling | m3 | 1180 | Klin |  |  | 12.877 | 15194.86 | 12.877 | 15194.86
9 |  | Aggregate filling | m3 | 1700 | Klin |  |  | 57.618 | 97950.58 | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin |  |  | 80.4383 | 72394.49 | 80.4383 | 72394.49
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin |  |  | 31.311 | 81377.289 | 31.311 | 81377.289
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin |  |  | 44.829 | 129914.442 | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin |  |  |  | 0 | 0 | 0
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin |  |  | 304.5 | 946233.75 | 304.5 | 946233.75
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9 Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin |  |  | 220.27 | 763235.55 | 220.27 | 763235.55
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin |  |  |  | 0 | 0 | 0
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin |  |  | 93.7533 | 42376.5 | 93.7533 | 42376.5
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin |  |  | 167.3137 | 84326.08 | 167.3137 | 84326.08
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin |  |  | 8.763 | 78867 | 8.763 | 78867
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin |  |  | 28.4651 | 289490.3416 | 28.4651 | 289490.3416
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin |  |  | 36.5432 | 414399.53 | 36.5432 | 414399.53
21 | [9 empty] | 0 | 0
[7 empty] | 0 |  | 5006327.8776 |  | 5006327.8776

## RA 2
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA2
Bill Month March 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 2225.55 | 400599 | 803.3673 | 144606.11 | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 | 0 |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 621.625 | 15540.625 | 126.5 | 3162.5 | 748.125 | 18703.125
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 0 | 0 | 1281.2922 | 1345356.86 | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 510.221 | 586754.15 | 964.911 | 1109647.65 | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 | 0 |  | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 0 | 0 | 0 |  | 0 | 0
8 |  | Sand Filling | m3 | 1180 | Klin | 12.877 | 15194.86 | 0 |  | 12.877 | 15194.86
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 | 0 |  | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 | 0 |  | 80.4383 | 72394.49
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 31.311 | 81377.289 | 11.016 | 28630.58 | 42.327 | 110007.869
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 | 0 |  | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 0 | 0 | 71.5797 | 196844.18 | 71.5797 | 196844.18
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 304.5 | 946233.75 | 166.3131 | 516817.96 | 470.8131 | 1463051.71
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9 Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 220.27 | 763235.55 | 0 |  | 220.27 | 763235.55
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 0 | 0 | 151.4067 | 60562.68 | 151.4067 | 60562.68
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 93.7533 | 42376.5 | 235.0805 | 106256.39 | 328.8338 | 148632.89
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 167.3137 | 84326.08 | 78.5181 | 39573.1 | 245.8317 | 123899.18
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 8.763 | 78867 | 4.3504 | 39153.35 | 13.1134 | 118020.35
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 28.4651 | 289490.3416 | 12.8774 | 130962.84 | 41.3425 | 420453.1816
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 36.5432 | 414399.53 |  |  | 36.5432 | 414399.53
21 | [5 empty] | 0 |  |  |  | 0 | 0
[7 empty] | 5006327.8776 |  | 3721574.2 |  | 8727902.0776
12614
9990.29
204408.36
177985.5
970830
42150.35
7062
1223389.48
2648429.98

## RA 3
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA3
Bill Month March 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 748.125 | 18703.125 |  |  | 748.125 | 18703.125
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  |  | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  |  | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  |  | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 0 | 0 | 3246.1502 | 259692.012 | 3246.1502 | 259692.012
8 |  | Sand Filling | m3 | 1180 | Klin | 12.877 | 15194.86 |  |  | 12.877 | 15194.86
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  |  | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  |  | 80.4383 | 72394.49
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 42.327 | 110007.869 | 15.8138 | 41099.9363 | 58.1407 | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  |  | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 71.5797 | 196844.18 | 81.5912 | 224375.8 | 153.1709 | 421219.98
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 470.8131 | 1463051.71 | 76.025 | 236247.6875 | 546.8381 | 1699299.3975
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9 Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 220.27 | 763235.55 |  |  | 220.27 | 763235.55
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 151.4067 | 60562.68 | 301.302 | 120520.8 | 452.7087 | 181083.48
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 328.8338 | 148632.89 | 149.04 | 67366.08 | 477.8738 | 215998.97
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 245.8317 | 123899.18 |  |  | 245.8317 | 123899.18
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 13.1134 | 118020.35 | 25.5713 | 230142.0066 | 38.6847 | 348162.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 41.3425 | 420453.1816 | 6.137 | 62413.2975 | 47.4795 | 482866.4791
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 36.5432 | 414399.53 |  |  | 36.5432 | 414399.53
21 | [5 empty] | 0 |  |  |  | 0 | 0
[7 empty] | 8727902.0776 |  | 1241857.6199 |  | 9969759.6975

## RA 4
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA4
Bill Month April 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
[6 empty] | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 748.125 | 18703.125 |  |  | 748.125 | 18703.125
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  |  | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  |  | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  |  | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 3246.1502 | 259692.012 | 206.4356 | 16514.8453 | 3452.5857 | 276206.8573
8 |  | Sand Filling | m3 | 1180 | Klin | 12.877 | 15194.86 |  |  | 12.877 | 15194.86
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  |  | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  |  | 80.4383 | 72394.49
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 58.1407 | 151107.8053 |  | 0 | 58.1407 | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  |  | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 153.1709 | 421219.98 | 218.46 | 600765 | 371.6309 | 1021984.98
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 546.8381 | 1699299.3975 | 2.77 | 8607.775 | 549.6081 | 1707907.1725
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9 Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 220.27 | 763235.55 |  |  | 220.27 | 763235.55
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 452.7087 | 181083.48 | 438.6872 | 175474.88 | 891.3959 | 356558.36
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 477.8738 | 215998.97 | 39.6976 | 17943.3152 | 517.5714 | 233942.2852
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 245.8317 | 123899.18 |  |  | 245.8317 | 123899.18
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 38.6847 | 348162.3566 | 28.912 | 260208 | 67.5967 | 608370.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 47.4795 | 482866.4791 | 1.492 | 15173.64 | 48.9715 | 498040.1191
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 36.5432 | 414399.53 |  |  | 36.5432 | 414399.53
21 | [5 empty] | 0 |  |  |  | 0 | 0
[7 empty] | 9969759.6975 |  | 1094687.4555 |  | 11064447.1529

## RA 5
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA5
Bill Month May 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
|  | Excavation |  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 748.125 | 18703.125 | 103.044 | 2576.1 | 851.169 | 21279.225
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  | 0 | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  | 0 | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  | 0 | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 3452.5857 | 276206.8573 |  | 0 | 3452.5857 | 276206.8573
8 |  | Sand Filling | m3 | 1180 | Klin | 12.877 | 15194.86 | 9.675 | 11416.5 | 22.552 | 26611.36
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  | 0 | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  | 0 | 80.4383 | 72394.49
Concrete
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | Klin |  | 0 | 9.675 | 22252.5 | 9.675 | 22252.5
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 58.1407 | 151107.8053 |  | 0 | 58.1407 | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  | 0 | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 371.6309 | 1021984.98 | 70.205 | 193063.75 | 441.8359 | 1215048.73
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 549.6081 | 1707907.1725 | 147.248 | 457573.16 | 696.8561 | 2165480.3325
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 | 3465 |  | 220.27 | 763235.55 |  |  | 220.27 | 763235.55
Shuttering
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 891.3959 | 356558.36 | 186.672 | 74668.8 | 1078.0679 | 431227.16
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 517.5714 | 233942.2852 | 257.984 | 116608.768 | 775.5554 | 350551.0532
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 245.8317 | 123899.18 |  | 0 | 245.8317 | 123899.18
Re- In forcements
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 67.5967 | 608370.3566 | 10.09 | 90810 | 77.6867 | 699180.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 48.9715 | 498040.1191 | 10 | 101700 | 58.9715 | 599740.1191
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 36.5432 | 414399.53 |  | 0 | 36.5432 | 414399.53
21 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 11064447.1529 |  | 1070669.578 |  | 12135116.7309

## RA 6
Nakoda Pipe Impex Pvt Ltd
Civil Work Estimate
Upto Plinth Level
Bill No RA6
Bill Month June 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date |  | Remarks
|  | Excavation |  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11 |  | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82 |  | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 851.169 | 21279.225 |  |  | 851.169 | 21279.225 |  | 21279.225
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  |  | 1281.2922 | 1345356.86 |  | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  |  | 1475.132 | 1696401.8 |  | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  |  | 500.988 | 651033.87 |  | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 3452.5857 | 276206.8573 |  |  | 3452.5857 | 276206.8573 |  | 276206.8573
8 |  | Sand Filling | m3 | 1180 | Klin | 22.552 | 26611.36 |  |  | 22.552 | 26611.36 |  | 26611.36
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  |  | 57.618 | 97950.58 |  | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  |  | 80.4383 | 72394.49 |  | 72394.49
|  | Concrete | [10 empty] | 0
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | Klin | 9.675 | 22252.5 |  |  | 9.675 | 22252.5 |  | 22252.5
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 58.1407 | 151107.8053 |  |  | 58.1407 | 151107.8053 |  | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  |  | 44.829 | 129914.442 |  | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 441.8359 | 1215048.73 | -63.1648 | -173703.0625 | 378.6712 | 1041345.6675 |  | 1215048.73
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 696.8561 | 2165480.3325 | 59.328 | 184361.76 | 756.1841 | 2349842.0925 |  | 2165480.3325
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 220.27 | 763235.55 | 21.082 | 73049.13 | 241.352 | 836284.68 |  | 763235.55
|  | Shuttering | [10 empty] | 0
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 1078.0679 | 431227.16 | 151.7018 | 60680.72 | 1229.7697 | 491907.88 |  | 431227.16
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 775.5554 | 350551.0532 | 226.0503 | 102174.7356 | 1001.6057 | 452725.7888 |  | 350551.0532
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 245.8317 | 123899.18 | 102.326 | 51572.304 | 348.1577 | 175471.484 |  | 123899.18
|  | Re- In forcements | [10 empty] | 0
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 77.6867 | 699180.3566 | 4.388 | 39492 | 82.0747 | 738672.3566 |  | 699180.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 58.9715 | 599740.1191 | 6.357 | 64650.69 | 65.3285 | 664390.8091 |  | 599740.1191
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 36.5432 | 414399.53 | 2.42 | 27442.8 | 38.9632 | 441842.33 |  | 414399.53
21 | [10 empty] | 0
[7 empty] | 12135116.7309 |  | 429721.0771 |  | 12564837.808
82.0747
[10 empty] | 83.6966 | 1.6219
0
65.3285
[10 empty] | 153.2862 | 87.9577
Abhishek Acharya |  |  | Rupesh Verma | [7 empty] | Anirudh Sinha
Billing Engineer |  |  | Site Incharge | [7 empty] | Civil Incharge (S.I.D)
Nakoda Pipe Impex Pvt Ltd |  |  | Aquaplast Infracon | [7 empty] | Nakoda Pipe Impex Pvt Ltd

## RA 7
Nakoda Pipe Impex Pvt Ltd | [10 empty] | Bill No RA 7
Civil Work Estimate | [10 empty] | Bill Month July 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date
|  | Excavation |  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 851.169 | 21279.225 |  |  | 851.169 | 21279.225
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  |  | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  |  | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  |  | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 3452.5857 | 276206.8573 |  |  | 3452.5857 | 276206.8573
8 |  | Sand Filling | m3 | 1180 | Klin | 22.552 | 26611.36 |  |  | 22.552 | 26611.36
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  |  | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  |  | 80.4383 | 72394.49
Concrete
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | Klin | 9.675 | 22252.5 |  | 0 | 9.675 | 22252.5
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 58.1407 | 151107.8053 | 0 | 0 | 58.1407 | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  | 0 | 44.829 | 129914.442
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 378.6712 | 1041345.6675 | 3.76 | 10340 | 382.4312 | 1051685.6675
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 756.1841 | 2349842.0925 | 21.546 | 66954.195 | 777.7301 | 2416796.2875
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 241.352 | 836284.68 | 83.08 | 287872.2 | 324.432 | 1124156.88
Shuttering
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 1229.7697 | 491907.88 | 114 | 45600 | 1343.7697 | 537507.88
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 1001.6057 | 452725.7888 |  | 0 | 1001.6057 | 452725.7888
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 348.1577 | 175471.484 | 249.7575 | 125877.78 | 597.9152 | 301349.264
Re- In forcements
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 82.0747 | 738672.3566 | 0.58 | 5220 | 82.6547 | 743892.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 65.3285 | 664390.8091 | 7.64 | 77698.8 | 72.9685 | 742089.6091
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 38.9632 | 441842.33 | 17.05 | 193347 | 56.0132 | 635189.33
21 |  | Fabrication & Fixing of insert Plates |  | 25000 |  |  |  | 23.173 | 579325 | 23.173 | 579325
|  | JigS & Fixture | MT | 22000 |  |  |  | 0.94 | 20680 | 0.94 | 20680
|  | Fixing of Foundation bolts 32 mm Dia & Above |  | 22000 |  |  |  | 5.62 | 123640 | 5.62 | 123640
[7 empty] | 12564837.808 |  | 1536554.975 |  | 13957072.783
13957072.783
630027
1200030
15787129.783

## RA 8
Nakoda Pipe Impex Pvt Ltd | [10 empty] | Bill No RA 8
Civil Work Estimate | [10 empty] | Bill Month August 2023
Sl No | Item No | Description | UOM | Rate | Division | Upto Prev Bill |  | This Bill |  | Total Till Date
|  | Excavation |  |  |  | Quantity | Amount | Quantity | Amount | Quantity | Amount
1 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 0 to 3 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 180 | Klin | 3028.9173 | 545205.11 |  |  | 3028.9173 | 545205.11
2 |  | Earthwork in Excavation in all type of soil/soft rock & Disposal of the surplus excavated material in spoil dumps, till area at 3 to 6 mtrs hieghts and descents within a lead upto 500 Mtr including all | m3 | 220 | Klin | 1530.181 | 336639.82 |  |  | 1530.181 | 336639.82
3 |  | Soil Dressing | m2 | 25 | Klin | 851.169 | 21279.225 |  |  | 851.169 | 21279.225
4 |  | Hard Rock breaking 0-3 | m3 | 1050 | Klin | 1281.2922 | 1345356.86 |  |  | 1281.2922 | 1345356.86
5 |  | Hard Rock breaking 3-6 | m3 | 1150 | Klin | 1475.132 | 1696401.8 |  |  | 1475.132 | 1696401.8
6 |  | Hard Rock breaking 6-9 | m3 | 1299.5 | Klin | 500.988 | 651033.87 |  |  | 500.988 | 651033.87
7 |  | Backfilling | m3 | 80 | Klin | 3452.5857 | 276206.8573 |  |  | 3452.5857 | 276206.8573
8 |  | Sand Filling | m3 | 1180 | Klin | 22.552 | 26611.36 |  |  | 22.552 | 26611.36
9 |  | Aggregate filling | m3 | 1700 | Klin | 57.618 | 97950.58 |  |  | 57.618 | 97950.58
10 |  | Rock Soling | m3 | 900 | Klin | 80.4383 | 72394.49 |  |  | 80.4383 | 72394.49
Concrete
|  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 0 to 3 Mtr | m3 | 2300 | Klin | 9.675 | 22252.5 |  | 0 | 9.675 | 22252.5
11 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 3 to 6 Mtr | m3 | 2599 | Klin | 58.1407 | 151107.8053 |  | 0 | 58.1407 | 151107.8053
12 |  | Supplying, laying and compacting plain cement concrete (all grade) as defined by IS 456 with graded stone aggregates in all foundation and bed blocks, manholes, chambers, tunnels, floor, pavement, screedings etc. As per the drawings, specification and instruction of the engineer at all heights and depths above and below plniths to require materials, tools and plants, labour complete (use vibrator) 6 to 9Mtr | m3 | 2898 | Klin | 44.829 | 129914.442 |  | 0 | 44.829 | 129914.442 | 16700000
13 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 0 M t o +/-3Mtrs heights/depth with proper compaction and curing | m3 | 2750 | Klin | 382.4312 | 1051685.6675 |  | 0 | 382.4312 | 1051685.6675
14 |  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 3 M t o +/-6Mtrs heights/depth with proper compaction and curing | m3 | 3107.5 | Klin | 777.7301 | 2416796.2875 |  | 0 | 777.7301 | 2416796.2875
|  | Supplying, laying reinforced cement concrete (all grade) as defined by IS 456 up to +/- 6 M t o +/-9Mtrs heights/depth with proper compaction and curing | m3 | 3465 | Klin | 324.432 | 1124156.88 | 53.358 | 184885.47 | 377.79 | 1309042.35
Shuttering
15 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M. | m2 | 400 | Klin | 1343.7697 | 537507.88 |  | 0 | 1343.7697 | 537507.88
16 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 3M to +/- 6 Mtr | m2 | 452 | Klin | 1001.6057 | 452725.7888 |  | 0 | 1001.6057 | 452725.7888
17 |  | Provinding and fixing shuttering in postion with necessary centring, branches , droppings etc. And removing the same after specification periods for all type shuttering for all plain and reinforced cement concrete including all chambers, splays, keys, wedges, nails, brackets, cutting holes for embedded steel/pipes and applying shuttering oil in shuttering surface in contact with concrete, all materials tools , plants and labour complete, shuttering for +/- 6M to +/- 9 Mtr | m2 | 504 | Klin | 597.9152 | 301349.264 | 90.16 | 45440.64 | 688.0752 | 346789.904
Re- In forcements
18 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.0-3 | MT | 9000 | Klin | 82.6547 | 743892.3566 |  | 0 | 82.6547 | 743892.3566
19 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.3-6 | MT | 10170 | Klin | 72.9685 | 742089.6091 |  | 0 | 72.9685 | 742089.6091
20 |  | Taking delivery transporting within site area placing and fixing in postion steel reinforcement including angles/pins provided for the approved welded joint at all levels above and belorh plinth level for RCC and precast reinforced concrete works including cutting, bending cranking, binding tack welding as necessary as per drawing, specification and direction of the engineer including wire, cover blocks, electrodes etc. And strengthening and de coling where necessary all materials, tools and plamts and labour complete.6-9 | MT | 11340 | Klin | 56.0132 | 635189.33 | 12.991 | 147317.94 | 69.0042 | 782507.27
21 |  | Fabrication & Fixing of insert Plates |  | 25000 |  | 23.173 |  | 6.3348 | 158369.825 | 29.5078 | 737694.825
|  | JigS & Fixture | MT | 22000 |  | 0.94 |  | 0.18463 | 4061.904 | 1.1246 | 24741.904
|  | Fixing of Foundation bolts 32 mm Dia & Above |  | 22000 |  | 5.62 |  |  | 0 | 5.62 | 123640
[7 empty] | 13377747.783 |  | 540075.779 |  | 14493086.658

## RA 8 Measurement
MB NO - 8th
Measurement of 8th RA Bill
Name of Work :- SID Axis-01 (KIB, KP-1)
Client :- Shree Nakoda Pipe Impex PVT Ltd.
Vendor Name :- Aquaplast infracon Pvt Ltd | [13 empty] | Date Of Start:-01/07/2023
Date Of Measurmenr :- 07/08/2023 | [13 empty] | Date of Completion :-31/07/2023
Sr. No. | Block | Structure | Discription/Particular | GRID | Reduced Level |  | Nos | Unit/Nos | Length | Width | Hight | Qty. | Unit | Remark
[5 empty] | RL from | RL to
KP-3
1 | RCC UPTO (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL -94.325
| SID | KP-3
|  |  | Column Casting |  | 101.352 | 102.102 | 2 | 1 | 3 | 1.2 | 0.75 | 5.4
|  |  | Deck Slab |  | 102.102 | 104.102 | 1 | 1 | 6.8 | 3 | 2 | 40.8
|  |  | Deck Slab hunch Bottum |  | 101.352 | 102.102 | 2 | 0.5 | 0.75 | 3 | 0.75 | 1.6875
|  |  | Side Hunch 1 B/T KP-2 |  | 102.56 | 103.01 | 4 | 1 | 0.6 | 0.6 | 0.45 | 0.648
|  |  | Tringle Area |  | 102.16 | 102.56 | 4 | 0.5 | 0.6 | 0.6 | 0.4 | 0.288
|  |  | Side hunch 2 |  | 102.312 | 103.012 | 2 | 1 | 0.9 | 1 | 0.7 | 1.26
|  |  | Tringle Area |  | 101.846 | 102.312 | 2 | 0.5 | 0.9 | 1 | 0.466 | 0.4194
| SID | KIB | Column Cap Casting |  | 105.991 | 106.5 | 6 | 1 | 1.1 | 0.85 | 0.509 | 2.8555
[10 empty] | Total |  | 53.3584 | CUM
2 | Insrt Plate UPTO (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL -94.325
|  |  | KP-3 Hunch Near KP-1 & KP-2 |  | 103.049 | 102.199 | 2 | 4 | 0.4 | 0.4 | 0.016 | 0.02048 |  | IP AT FRONT & TOP
|  |  | Lux (50X50X6) |  | 103.049 | 102.199 | 8 | 2 | 0.5 | 0.1 | 0.016 | 0.0128 |  | (103.088+103.012)/2=103.049 AVG
|  |  | Hunch in Froun Of Store |  | 103.049 | 102.199 | 2 | 3 | 0.5 | 0.5 | 0.016 | 0.024
|  |  | Lux (50X50X6) |  | 103.049 | 102.199 | 6 | 2 | 0.5 | 0.1 | 0.016 | 0.0096
|  |  | IP Ficing At Beam 100 lvl top |  | 100 | 99.55 | 5 | 2 | 0.15 | 0.15 | 0.016 | 0.0036
|  |  | Hunch IP Fixing |  | 99.312 | 98.821 | 3 | 2 | 0.5 | 0.5 | 0.491 | 0.7365
[10 empty] | Total |  | 0.80698
[10 empty] | Steel Density |  | 7850
[10 empty] | Total In Wt. (KG) |  | 6334.793
[10 empty] | Total Wt in TON |  | 6.3348 | MT
3 | Kerb UPTO (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL -94.325 |  |  |  | 104.102 | 104.027 | 1 | 2 | 6.8 | 0.15 | 0.008 | 0.01632
|  |  | KP-3 Top leve Deck Kerb Angle Fixing |  | 104.102 | 104.027 | 1 | 2 | 3 | 0.15 | 0.008 | 0.0072
[10 empty] | Total |  | 0.02352
[10 empty] | Steel Density |  | 7850
[10 empty] | Total In Wt. (KG) |  | 184.632
[10 empty] | Total Wt in TON |  | 0.18463 | MT
4 | Embeddad rod fixing (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL
|  |  | KP-1 Deck Slab Embadded Rod |  | 102.102 | 104.102 | 2 | 1 | 3.14 | 0.0009 | 6.24 | 0.035268
[10 empty] | Total |  | 0.035268
[10 empty] | Steel Density |  | 7850
[10 empty] | Total In Wt. (KG) |  | 276.8576
[10 empty] | Total Wt in TON |  | 0.27686 | MT | Rate Not Finalised
5 | Shuttering UPTO (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL
|  |  | Column Side only Hunch hight |  | 102.102 | 101.352 | 2 | 1 | 3 |  | 0.75 | 4.5
|  |  | Column Side only Hunch hight |  | 102.102 | 101.352 | 2 | 2 | 1.35 |  | 0.75 | 4.05
|  |  | hunch Tringle area |  | 102.102 | 101.352 | 4 | 0.5 | 0.75 |  | 0.75 | 1.125
|  |  | hunch Bottum |  | 102.102 | 101.352 | 2 | 1 | 1.06 |  | 3 | 6.36
|  |  | Deck Side Slab |  | 104.102 | 102.102 | 2 | 1 | 6.8 |  | 2 | 27.2
|  |  | Deck Column Above Hunch |  | 104.102 | 102.102 | 2 | 1 | 3 |  | 2 | 12
|  |  | Deck Slab bottum |  | 102.102 | 102.102 | 1 | 1 | 2.9 |  | 3 | 8.7
|  |  | Slab bottum At Slop |  |  |  | 2 | 1 | 1.06 |  | 0.75 | 1.59
|  |  | Side Hunch 1 Squar area |  | 103.088 | 102.638 | 4 | 2 | 0.6 |  | 0.45 | 2.16
|  |  | Hunch front Shuttering |  | 103.088 | 102.638 | 4 | 1 | 0.45 |  | 0.6 | 1.08
|  |  | Hunch Bottum slop |  | 102.638 | 102.238 | 4 | 1 | 0.721 |  | 0.6 | 1.7304
|  |  | Tringle area (4X2) |  |  |  | 8 | 0.5 | 0.6 |  | 0.4 | 0.96
|  |  | Side Hunch 2 Squar area |  | 103.049 | 102.349 | 2 | 2 | 0.9 |  | 0.7 | 2.52
|  |  | Hunch Front |  | 103.049 | 102.349 | 2 | 1 | 0.7 |  | 1 | 1.4
|  |  | Hunch Bottum slop |  | 102.199 | 102.599 | 2 | 1 | 1.077 |  | 1 | 2.154
|  |  | Tringle area (2X2) |  | 102.599 | 102.199 | 4 | 0.5 | 0.9 |  | 0.4 | 0.72
| KIB |  | KIB Column Cap Shuttering |  | 105.991 | 106.5 | 6 | 1 | 3.9 |  | 0.509 | 11.9106
[10 empty] | Total |  | 90.16 | SQM
6 | Pocket fixing UPTO (+/-) 6.0 Mtr TO (+/-) 9.0 Mtr from NGL
|  |  | Pocket at Deck Slab |  | 104.102 | 102.972 | 10 | 2 | 1 |  | 1.13 | 22.6
[10 empty] | Total |  | 22.6 | SQM | Rate not Finalised

## RA 8 BBS
REINFORCEMENT DETAILS
DRG NO | LOCATION | BAR MARK | TYPE | DIA | DIMENSIONS ( IN MM. ) |  |  |  |  | CUTTING LENGTH (MTR.) | QUANTITY |  |  | DIA OF BARS (MM)
|  |  |  | (MM) | a | b | c | d | e/Hook |  | SET | NO/SET | TOTAL | 8 | 10 | 12 | 16 | 20 | 25 | 32 | 60
[10 empty] | 0 |  |  | 0
KP-3 Deck Slab bottum Distribution Bar RL |  |  |  | 32 | 1.34 | 6.72 | 1.34 |  |  | 9.4 | 21 | 1 | 21 | - | - | - | - | - | - | 197.4 | -
Bottum Extra Bar |  |  |  | 25 |  | 6.72 |  |  |  | 6.72 | 21 | 1 | 21 | - | - | - | - | - | 141.12 | - | -
bottum bar Main bar |  |  |  | 32 | 1.34 | 2.92 | 1.86 |  |  | 6.12 | 46 | 1 | 46 | - | - | - | - | - | - | 281.52 | -
| Top Main Bar |  |  | 32 | 1.34 | 2.92 | 1.86 |  |  | 6.12 | 46 | 1 | 46 | - | - | - | - | - | - | 281.52 | -
Top distribution bar |  |  |  | 32 | 1.34 | 6.72 | 1.34 |  |  | 9.4 | 21 | 1 | 21 | - | - | - | - | - | - | 197.4 | -
| inner Ring 1 |  |  | 16 | 0.55 | 1.92 | 0.55 | 1.92 | 0.2 | 5.14 | 46 | 2 | 92 | - | - | - | 472.88 | - | - | - | -
| inner Ring 2 |  |  | 16 | 0.275 | 1.92 | 0.27 | 1.92 | 0.2 | 4.585 | 46 | 1 | 46 | - | - | - | 210.91 | - | - | - | -
| Column Vertical |  | A | 32 | 2.777 |  |  |  |  | 2.777 | 56 | 2 | 112 | - | - | - | - | - | - | 311.024 | -
Column Junction Ring |  |  | E | 16 | 0.64 | 1.12 | 0.6 | 1.12 | 0.2 | 3.68 | 11 | 2 | 22 | - | - | - | 80.96 | - | - | - | -
Column Junction Ring |  |  | E | 16 | 0.64 | 1.12 | 0.6 | 1.12 | 0.2 | 3.68 | 11 | 2 | 22 | - | - | - | 80.96 | - | - | - | -
Column Junction Ring |  |  | E | 16 | 0.64 | 1.12 | 0.6 | 1.12 | 0.2 | 3.68 | 11 | 2 | 22 | - | - | - | 80.96 | - | - | - | -
Column Junction Ring |  |  | E | 16 | 0.64 | 1.12 | 0.6 | 1.12 | 0.2 | 3.68 | 11 | 2 | 22 | - | - | - | 80.96 | - | - | - | -
Column Junction Ring |  |  | E | 16 | 2.92 | 1.12 | 2.9 | 1.12 | 0.2 | 8.26 | 11 | 2 | 22 | - | - | - | 181.72 | - | - | - | -
Slab bottum Hunch inclied Area |  |  | A | 20 | 2.66 |  |  |  |  | 2.66 | 21 | 2 | 42 | - | - | - | - | 111.72 | - | - | -
Hunch main bar Binder |  |  | A | 20 | 2.92 |  |  |  |  | 2.92 | 8 | 2 | 16 | - | - | - | - | 46.72 | - | - | -
| U -Bar For Hunch |  | C | 16 | 2.5 | 2.92 | 2.5 |  |  | 7.92 | 21 | 2 | 42 | - | - | - | 332.64 | - | - | - | -
Outer Hunch Steel main bar Near KP-3, KIB |  |  |  | 25 | 1.25 | 6.04 | 0.37 | 0.641 | 1.25 | 9.551 | 6 | 4 | 24 | - | - | - | - | - | 229.224 | - | -
Binder |  |  |  | 12 | 0.6 | 0.56 | 0.56 | 0.56 | 0.6 | 2.88 | 4 | 4 | 16 | - | - | 46.08 | - | - | - | - | -
Tringle area Binder |  |  |  | 12 | 0.6 | 0.32 | 0.56 | 0.32 | 0.6 | 2.4 | 6 | 4 | 24 | - | - | 57.6 | - | - | - | - | -
Outer Hunch Steel main bar Near KP-3 , KIB |  |  |  | 25 | 1.25 | 0.86 | 0.62 | 0.997 | 1.25 | 4.977 | 6 | 2 | 12 | - | - | - | - | - | 59.724 | - | -
Binder |  |  |  | 12 | 0.6 | 0.96 | 0.82 | 0.96 | 0.6 | 3.94 | 6 | 2 | 12 | - | - | 47.28 | - | - | - | - | -
Tringle area Binder |  |  |  | 12 | 0.6 | 0.49 | 0.82 | 0.49 | 0.6 | 3 | 4 | 2 | 8 | - | - | 24 | - | - | - | - | -
Extra bar for Pocket fixing |  |  |  | 12 | 6.7 |  |  |  |  | 6.7 | 2 | 2 | 4 | - | - | 26.8 | - | - | - | - | -
|  |  |  | 12 | 2.9 |  |  |  |  | 2.9 | 10 | 2 | 20 | - | - | 58 | - | - | - | - | -
Embedded Fixing |  |  |  | 12 | 0.4 | 0.3 | 1.5 | 0.3 | 0.4 | 2.9 | 13 | 1 | 13 | - | - | 37.7 | - | - | - | - | -
Extra Bar At Deck Slab Top |  |  |  | 16 | 0.45 | 5.9 |  |  |  | 6.35 | 1 | 18 | 18 | - | - | - | 114.3 | - | - | - | -
Extra Bar At Deck Slab Top |  |  |  | 16 | 0.45 | 1.6 |  |  |  | 2.05 | 1 | 18 | 18 | - | - | - | 36.9 | - | - | - | -
Extra Bar At Deck Slab Top |  |  |  | 16 | 1.3 |  |  |  |  | 1.3 | 1 | 20 | 20 | - | - | - | 26 | - | - | - | -
Extra Bar At Deck Slab Top |  |  |  | 16 | 0.4 |  |  |  |  | 0.4 | 1 | 40 | 40 | - | - | - | 16 | - | - | - | -
Extra Bar At Deck Slab Top |  |  |  | 16 | 0.45 | 2.9 | 0.45 |  |  | 3.8 | 1 | 22 | 22 | - | - | - | 83.6 | - | - | - | -
KIB Column Cap Steel C1 |  |  |  | 25 | 0.509 |  |  |  |  | 0.509 | 6 | 18 | 108 | - | - | - | - | - | 54.972 | - | -
Master Ring |  |  |  | 10 | 0.92 | 0.67 | 0.92 | 0.67 | 0.2 | 3.38 | 3 | 6 | 18 | - | 60.84 | - | - | - | - | - | -
Sub Ring |  |  |  | 10 | 0.34 | 0.92 | 0.34 | 0.92 | 0.2 | 2.72 | 3 | 6 | 18 | - | 48.96 | - | - | - | - | - | -
[8 empty] | DIA WISE TOTAL LENGTH IN M. | [5 empty] | 0 | 109.8 | 297.46 | 1798.79 | 158.44 | 485.04 | 1268.864 | 0
[8 empty] | DIA WISE UNIT WEIGHT KG PER M. | [5 empty] | 0.39 | 0.62 | 0.89 | 1.58 | 2.47 | 3.86 | 8.127 | 22.2222
[8 empty] | DIA WISE TOTAL WEIGHT IN KG. | [5 empty] | 0 | 68.076 | 264.7394 | 2842.0882 | 391.3468 | 1872.2544 | 10312.0376 | 0 | 15750.5424
[8 empty] | TOTAL REINFORCE MENT QUANTITY IN M.T. | [5 empty] | 15.7505
125
[11 empty] | 67.1 |  |  | 12 | 110 | Kg
[16 empty] | 276.8 | 1.58
[16 empty] | 16 | 437.344 | KG
0.61444

## Total Upto Date
Sl No | Div | Block | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | Total | Total Estmated Value | Balance
1 | S.I.D | Klin | RA-1 | RA-2 | RA-3 | RA-4 | RA-5 | RA-6 | RA-7 | RA-8 | RA-9 | RA-10 | RA-11 | RA-12
|  |  | 2023-01-01: 5006327.8776; 2023-02-01: 3721574.2; 2023-03-01: 1241857.6199; 2023-04-01: 1094687.4555; 2023-05-01: 1070669.578; 2023-06-01: 429721.0771 | 12564837.808 | 15277426.3718 | 2712588.5637
2 | S.I.D | DRI | 2023-04-01: RA 1; 2023-06-01: RA 3
|  |  | 2023-04-01: 1151411.4183; 2023-06-01: 269981.7005 | 1421393.1188 | 7852713.5601 | 6431320.4412
3 | S.I.D | PSSB
[15 empty] | 0 | 3664853.1605 | 3664853.1605
4 | S.I.D | Cooling Tower
[15 empty] | 0 |  | 0
5 | S.I.D | Iron Circuit
[15 empty] | 0 | 295773.875 | 295773.875
6 | S.I.D | Over Head Tank | 2023-03-01: RA 1
|  |  | 2023-03-01: 80825.5893 | 80825.5893 | 892087.9012 | 811262.312
7 | S.I.D | Day Bin
0